## Programme Profile
Read Me First
Programme Name | Please enter the Name of the Programme (Max 20 words) See the guidance on the approach to the Programme and Project Planning | Species Conservation Programme
Program Lead | Please enter the Name of the Program Lead | Pierre Kafando
Program Team Member | Please list the name of Program Staff. This will be the list of staff who will have access to the Program information in the new PMEL system. | Laurent Somé Bruce Deguene Yoann Galeran Njunkeng Fualefac Ghislain Bellha Stef de Bethune Amandine Toumbou Antoine Edé Frédéric Singa Alphonsine Colombe Claude Bengono
Program Duration | Please indicate the duration of Program. Minimum Duration of the Program is 5 years. | FROM: | FY2026
|  | TO: | FY2030
Programme Description | Please enter a short description of the Programme (Max 200 words) |  | The Species Programme in the Central African Republic aims to conserve biodiversity and improve the well-being of Indigenous Peoples and Local Communities (IPLCs) by 2035. It focuses on forest elephants, great apes, and other threatened species across the Dzanga-Sangha and Ngotto landscapes. Key goals include stabilizing or increasing elephant and great ape populations, and reducing poaching signs by 25%. The programme promotes inclusive governance, sustainable livelihoods, and ecological resilience. Strategies involve strengthening law enforcement, enhancing human-wildlife conflict mitigation, and supporting alternative livelihoods. Education and health are also prioritized, with targets to increase school completion rates and eliminate zoonotic disease spillover through a One Health approach. The initiative emphasizes IPLC empowerment, secure land tenure, and policy advocacy. By 2030, it aims to implement at least two new biodiversity-positive policies and significantly reduce human rights abuses in conservation areas. Through this integrated, rights-based approach, the programme seeks to build resilient ecosystems and empowered communities across CAR. Key goals include stabilizing or increasing elephant and great ape populations, and reducing poaching signs by 25%. The programme promotes inclusive governance, sustainable livelihoods, and ecological resilience. Strategies involve strengthening law enforcement, enhancing human-wildlife conflict mitigation, and supporting alternative livelihoods. Education and health are also prioritized, with targets to increase school completion rates and eliminate zoonotic disease spillover through a One Health approach. The initiative emphasizes IPLC empowerment, secure land tenure, and policy advocacy. By 2030, it aims to implement at least two new biodiversity-positive policies and significantly reduce human rights abuses in conservation areas. Through this integrated, rights-based approach, the programme seeks to build resilient ecosystems and empowered communities across CAR.
Program Focus / Focal Area | Please select one or more Conservation and/or Human well being Focus areas that your program will be focusing on. Please make sure this is a subset of what's selected in the OSP. | Forest Elephant Great Apes Dense forest High Conservation Value forests Adaptation to climate change Policy and advocacy Human well-being
Geographic Scope (Landscape) | Please list all the operational land/seascapes that are within the scope of the Program. For each land/seascape, provide short description of why the scape is critical in the context of this Program (max 200 words per land/seascape). Example: Name of the land/seascape: Description max 200 words. All land/seascapes must must apply ESSF. Guidance on landscape definition is here | Name of land/seascape | Description (Max 200 words)
|  | Dzanga-Sangha Protected Areas (DSPA) | The Dzanga-Sangha Protected Areas Complex (DSPA) in the Central African Republic spans 4,381 km² and plays a vital role in biodiversity conservation and supporting local communities through sustainable practices and ecotourism. Established in 1990, it includes the Dzanga-Ndoki National Park and the Dzanga-Sangha Special Dense Forest Reserve, hosting endangered species like forest elephants, gorillas, and chimpanzees. The DSPA's diverse habitats, including tropical forests and mineral-rich clearings, are critical for ecosystem connectivity, with the Sangha River being central to local fisheries. The region's population is ethnically diverse, with the BaAka indigenous people making up 21% and the Bilo migrant population 79%. Local governance involves both formal authorities and traditional land chiefs. The economy is driven by subsistence agriculture, fishing, artisanal mining, and hunting, though illegal activities like poaching and mining threaten conservation efforts. Despite improvements in infrastructure, health and education access remains limited, with common health issues including infectious diseases and malnutrition. Conservation faces challenges from resource extraction and climate change. Ecotourism offers economic opportunities, though its financial benefits remain modest. Balancing development and conservation is essential to ensure the region's sustainability.
|  | Ngotto Forest | The Ngotto Forest Complex in southwestern Central African Republic spans approximately 780,000 hectares, comprising the Mbaéré-Bodingué National Park (MBNP) and three surrounding logging concessions, with the broader landscape potentially extending to over one million hectares when including Dzanga-Sangha National Park (DSNP). The area forms a vital transition zone between savannah and tropical forest and supports rich biodiversity, including forest elephants, great apes, endemic species, and RAMSAR-listed wetlands. A 2024 survey recorded 27 mammal species, over 900 great apes, and 323 woody plant species, though small primates have declined sharply. Around 31,000 people—among them indigenous Bofi and 18 ethnic groups—depend on the landscape for subsistence agriculture, logging, mining, and bushmeat. However, the park alone is too small to ensure ecological integrity, making a conservation focus solely on MBNP impractical. Effective conservation must include the surrounding concessions, though this significantly increases the budgetary and logistical requirements. Key threats include illegal logging, poaching, deforestation, mining, climate change, and population pressure. Despite a history of political instability and underfunded conservation, recent ecological data and a landscape-scale approach offer renewed opportunities for integrated biodiversity protection and sustainable land management.
Thematic Scope (Practices) | Please list all the thematic that are relevant to the scope of the OSP. (Choice: Finance & Administration, Fundraising, Communications, P&C, Partnership, PMEL, etc.). For each theme, provide short description of why the theme is critical in the context of the OSP (max 200 words per theme). Example: Name of the theme: Description max 200 words. See Guidance by PPMS Step - Element 1.2 | Name of Thematic Scope | Description (Max 200 words)
|  | Species Conservation Programme | The Species Programme, focused on the Dzanga-Sangha Protected Areas (DSPA), the Mbaéré-Bodingué National Park (MBNP), and the Ngotto Forest Landscape, aims to stabilize or increase populations of Forest Elephants and Great Apes by 2030, while enhancing the well-being of Indigenous Peoples and Local Communities (IPLCs) through inclusive, rights-based conservation. In these biodiverse yet vulnerable areas, elephants and great apes face critical threats from poaching, habitat degradation, and human-wildlife conflict. At the same time, IPLCs endure poverty, limited access to services, and marginalization. This initiative tackles these challenges through strengthened law enforcement and improved protected area management, targeting a 25% reduction in poaching signs by 2030. Anti-poaching patrols, legal reform, and community-based ranger networks form the backbone of this strategy. The Conflict to Coexistence (C2C) approach addresses human-elephant conflict, aiming to reduce retaliatory killings by 25% and improve community perceptions by 50%. The programme also invests in sustainable livelihoods—including ecotourism, agroforestry, and non-timber forest products—to boost household incomes by 10%. Education support and One Health interventions will enhance school completion rates and eliminate zoonotic disease transmission. Through strengthened local governance and biodiversity-positive policies, this programme envisions thriving wildlife and resilient communities across Dzanga-Sangha and Ngotto.

## Situation Analysis
Read Me First
Political | Please enter the concise analysis (narrative) of context and trends (political, social, economic, climate & environmental, and institutional) in country that has effects on the scope of the Programme. Depending on the nature of the program, some context may be more relevant than the others. (See Guidance by PPMS Step - Element 1.3, and IUCN-CMP Unified classification of Threat 2.0s) | • Government Stability and Capacity: CAR has experienced prolonged political instability, conflict, and weak governance. These factors undermine effective conservation enforcement, coordination, and long-term planning. • Security Risks: Armed groups, cross-border poaching networks, and illegal logging are facilitated by insecurity in and around DSPAs and Ngotto, threatening both wildlife and staff safety. • International Partnerships: Conservation programmes in DSPAs (co-managed with WWF) benefit from political support via international conservation agreements (e.g. CITES, CBD), but local political will remains inconsistent. • Decentralization and Local Governance: Ongoing efforts to devolve natural resource management to local authorities and communities can enhance ownership but also face capacity and corruption challenges.
Social |  | • Community Engagement and Customary Rights: Indigenous groups (e.g. BaAka) and rural communities have deep ties to forest resources. Exclusion or top-down conservation approaches have led to marginalization and conflict. • Education and Awareness: Low literacy and environmental awareness hinder local participation in conservation programmes, though community-based education initiatives in DSPAs are improving. • Cultural Practices: Traditional hunting practices can conflict with species protection, but also offer opportunities for culturally grounded conservation models when communities are empowered. • Demographic Pressure: Population growth, migration, and returnees (post-conflict) increase pressure on forest resources around Ngotto and the DSPAs.
Economic |  | • Poverty and Livelihood Dependency: High poverty levels in CAR push local communities to depend on forest resources (e.g. hunting, logging) for survival, creating tension with conservation goals. • Donor Dependence: Conservation in DSPAs and Ngotto is heavily reliant on external funding (e.g. EU, GEF), which makes programmes vulnerable to shifting donor priorities and financial sustainability risks. • Ecotourism Potential: DSPAs, especially the Dzanga Bai, have high ecotourism value (e.g. lowland gorillas, forest elephants), but fragile security and poor infrastructure limit economic benefits. • Informal Economy and Illicit Trade: Illegal logging, bushmeat trade, and trafficking of ivory or endangered species generate informal revenues that undermine conservation and divert economic gains from legal conservation-linked ventures.
Climate & Environmental |  | • Governance & Institutional Framework: Co-management model in DSPAs (WWF + government), but weak government presence and institutional structures in Ngotto. • Capacity Issues: Limited staffing, skills gaps, and underfunded conservation institutions, particularly in remote areas like Ngotto. • Coordination Challenges: Weak inter-ministerial and local governance coordination; transboundary cooperation exists in DSPAs but is often fragmented. • Funding & Sustainability: High reliance on external donors for DSPAs; Ngotto lacks stable funding and national resource allocation. • Legal & Enforcement Gaps: Weak judicial systems, limited law enforcement capacity (e.g., eco-guards), and corruption hinder effective conservation law enforcement. • Community Engagement: Stronger community-based conservation initiatives in DSPAs; Ngotto has less community organization and institutional support from NGOs.
Institutional |  | • Governance & Institutional Framework: Co-management model in DSPAs (WWF + government), but weak government presence and institutional structures in Ngotto. • Capacity Issues: Limited staffing, skills gaps, and underfunded conservation institutions, particularly in remote areas like Ngotto. • Coordination Challenges: Weak inter-ministerial and local governance coordination; transboundary cooperation exists in DSPAs but is often fragmented. • Funding & Sustainability: High reliance on external donors for DSPAs; Ngotto lacks stable funding and national resource allocation. • Legal & Enforcement Gaps: Weak judicial systems, limited law enforcement capacity (e.g., eco-guards), and corruption hinder effective conservation law enforcement. • Community Engagement: Stronger community-based conservation initiatives in DSPAs; Ngotto has less community organization and institutional support from NGOs.

## Stakeholder Analysis
| Stakeholder Name | Stakeholder Description | Stakeholder Type | Engagement Stage (planning, Implementation, MEL) | Engagement methods & strategies | Due Diligence (Y/N)
READ Me First | Please list key groups of stakeholders (people and organizations) who will be influenced by, have an impact on, or will help implement conservation to engage during the Programme planning, implementation, monitoring, and learning. Max 20 words. See Guidance by PPMS Step - Element 1.4 | Please briefly explain the significance of engaging with the stakeholder, and what you expect from the effective engagement. max 200 words | Please indicate the type of stakeholders (individual or organization): - Indigenous People & Local Communities - Civil Society Organization - Government's / Public Sector Organization - Companies / Private Sector - Universities / Research Organization - Other | Please indicate what stage each stakeholder group will be engaged - Programme planning, implementation, M&E, and Learning, etc. | Please describe how each stakeholder group will be engaged. Make sure that stakeholders will have regular access to the Programme information and, as appropriate, are aware of complaints procedures and feedback mechanisms. | For corporate & philanthropic partners (major donors, trusts, and foundations), please indicate if the due diligence is already conducted or not. For Other stakeholders, put NA. Corporate Partnership Rules & Guidelines Philanthropy Due Diligence
| MEFCP | National authority of co-management | Government's / Public Sector Organization |  | Responsible, within the framework of the general policy defined by the Government, for drawing up and implementing national policy in the fields of Water, Forests, Hunting and Fishing.
| MACT | National authority of management | Government's / Public Sector Organization
| MEDD | National authority of management | Government's / Public Sector Organization |  | Responsible, within the framework of the general policy defined by the Government, for drawing up and implementing national policy in the fields of Environment and Sustainable Development,
FTNS
UE
MEFP
| Ndima Kali |  | Indigenous People & Local Communities
Radio Njokou
| GDRNE |  | Civil Society Organization

## Focus & Goals
| Conservation Focus | Relevant OSP Goals | Key Assumptions
READ Me First | Please list each conservation focus / focal interest. Biodiversity Focal Interests can be focal species or habitats/ ecological systems. Human Wellbeing Focal Interests can be those component of human wellbeing affected by the status of biodiversity focal interests (material and non-material benefits obtained by ecosystem. Please ensure that focus / focal interest is a subset of those selected under the OSP. You may define further detail. | Based on the focus / focal interest selected, Please select the OSP Goal that your program is aiming to deliver. Please list the OSP Goal statement. | Please identify the key assumptions that underpin the logical sequences linking strategies to one or more focal interests. Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment.
Example | Coral Reef in Beta seascape. | Live coral reef covers at least 25% of the reef within the priority coastal seascapes in country Y. | WWF or its partner organization can monitor the live coral reef coverage in the coastal Beta seascape with proper funding.
| Forest Elephant | By 2035, Number of Forest Elephants in the DSPAs, MBNP and their peripheries are at least stabilize relatively to the 2020 (DSPA) and 2024 (Ngotto) baseline. | 1. No sudden environmental disturbances that could lead to mortality of elephants 2. Government policies remain in favour of endagered and protected species External pressures such as illegal ivory markets, mining, or infrastructure development are mitigated or redirected away from critical elephant habitats. No major outbreaks of conflict or instability disrupt conservation operations or increase vulnerability of elephant populations.
| Great Apes | In 2035, number of Great Apes populations in the DSPA, the PNMB and their peripheries increase compared to the 2020 (DSPA) and 2024 (Ngotto) baseline. | 1. No sudden environmental disturbances that could lead to mortality of Great Apes 2. Government policies remain in favour of endangered and protected species External pressures such as illegal ivory markets, mining, or infrastructure development are mitigated or redirected away from critical Great Apes habitats. No major outbreaks of conflict or instability disrupt conservation operations or increase vulnerability of Great Apes populations.
| Human wellbeing | By 2035, the well-being and resilience of targeted communities is improved by at least 10% relative to 2025 baseline

## Narrative TOC
| Read Me First | Species Programme ToC
Narrative Theory of Change | Please articulate the Theory of Change in Narrative. A Theory of Change (ToC) should be underpinned by evidence of the logic. Articulate the causal pathway that leads from the current to the desired situation, describing how the Programme activities will deliver the envisioned Programme Outputs and Outcomes, and ultimately the Programme/OSP Goals. Key risks associated with the key assumptions along the Theory of Change to achieve its Programme Outcomes and Goals must be articulated. A risk is potential future event that may impact achievement of goals. Assumptions are explicit statements of what the CO assumes is true. The logical sequences must link activities to one or more focal interests as reflected in a theory of change. Assumptions may also express how external variables may influence the achievement of results. Max. 500 words See Guidance by PPMS Step - Element 2.1 | The overarching goal of this initiative is to ensure that by 2030, elephant and great ape populations in Central African Republic (CAR) are stabilized or increased, while Indigenous Peoples and Local Communities (IPLCs) benefit from improved well-being through sustainable livelihoods, education, and participation in conservation efforts. CAR’s biodiversity, especially its elephant and great ape populations, faces significant threats from poaching, human-wildlife conflict, and habitat degradation. Local communities also face economic marginalization, with limited access to education, healthcare, and sustainable livelihoods. These challenges are exacerbated by weak governance and environmental pressures that threaten both species and human well-being. This initiative adopts an integrated, rights-based approach that centers IPLCs in conservation efforts while addressing the root causes of biodiversity loss and community vulnerability. By enhancing law enforcement and improving protected area management, the initiative aims to reduce poaching and illegal wildlife trade. A 25% reduction in poaching signs for elephants and great apes is targeted by 2030. Rangers will be trained and better equipped, community patrols will be strengthened, and the judicial system will be engaged to ensure effective prosecution of wildlife crimes. To mitigate human-wildlife conflict, particularly between elephants and local communities, the program will enhance human-elephant conflict mitigation strategies. Through the Conflict to Coexistence (C2C) approach, local attitudes toward wildlife will be improved by 50%, with a focus on reducing retaliatory killings. Support for local leadership and women’s groups will ensure inclusive decision-making processes. The initiative will introduce alternative income-generating activities, including sustainable ecotourism, agroforestry, and non-timber forest products. These efforts aim for a 10% increase in household incomes by 2030, reducing dependence on unsustainable natural resource use and fostering long-term economic resilience for IPLCs. The program will support education for sustainable development, infrastructure improvements, and attendance incentives. By 2030, the goal is to increase primary school completion to 50% and secondary school completion to 20% among children in the targeted communities. Recognizing the zoonotic risks in biodiverse regions, the initiative will implement a One Health approach, integrating human, animal, and environmental health surveillance. The aim is to reduce zoonotic disease spillover while improving local health and sanitation practices. The program will engage government and traditional authorities to adopt biodiversity-positive policies and protect the rights of IPLCs. By 2030, at least two new or strengthened environmental policies will be implemented, with a significant reduction in human rights abuses in conservation areas.
Opportunities for Innovation | Please articulate priority areas of innovation and research where needed. Innovation and Research activities must be included in the Programme Implementation Plan, Max. 500 words

## Program M&E Plan
RESULT LEVEL | PROGRAMMES | Relevant Geographic Scope | PROG_ID | FOCUS | Priority Threats / Other Factors | RESULT_ID | Statement | Indicator | Description | Means of Verification (Source of data) | Data Collection & Analysis Methodology | Frequency of Measurement | Assumptions & Risks | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Location | Responsible
GOAL | Species Conservation |  | 1 | Forest Elephant |  | 1.1 | By 2035, Number of Forest Elephants in the DSPAs, MBNP and their peripheries are at least stabilize relatively to the 2020 (DSPA) and 2024 (Ngotto) baseline. | Number of individual elephants in the area | Measurement of the Population size | Elephant Survey Data (With validated analyses and report) | Line Transect Distance Sampling, Camera Trap Distance Sampling, DNA Capture-Recapture | Endline (Once) | 1. No sudden environmental disturbances that could lead to mortality of elephants 2. Government policies remain in favour of endagered and protected species External pressures such as illegal ivory markets, mining, or infrastructure development are mitigated or redirected away from critical elephant habitats. No major outbreaks of conflict or instability disrupt conservation operations or increase vulnerability of elephant populations. | DSPA: 830 (2020) Ngotto: 108 (2024) |  |  |  |  | DSPA: 830 Ngotto: 108 | DSPA & Ngotto
GOAL | [7 empty] | Number of elephants per surface area in sqkm | Density (n/sqkm) | Elephant Survey Data (With validated analyses and report) | Line Transect Distance Sampling, Camera Trap Distance Sampling, DNA Capture-Recapture | Endline (Once) |  | DSPA: 0.17 (2020) Ngotto: 0.014 (2024) |  |  |  |  | DSPA: 0.17 Ngotto: 0.014 | DSPA & Ngotto
GOAL | [7 empty] | Number of sightings of elephants in an area per unit of sampling distance in km | Encounter rate (n/km) | Elephant Survey Data (With validated analyses and report) | Line Transect Distance Sampling, Walk Reconnaissance Survey | Midline (Twice) |  | DSPA : 7.8 (2020) Ngotto : 0.33 (2024) |  |  |  |  | DSPA : 7.8 Ngotto : 0.33 | DSPA & Ngotto
GOAL | [7 empty] | Proportion of surface area occupied by elephants in an area | Occupancy rate (%) or Spatial distribution | Elephant Survey Data (With validated analyses and report) | Line Transect Distance Sampling, Camera Trap Occupancy | Midline (Twice) |  | DSPA: 0.62 (2020) Ngotto : N/A |  |  |  |  | DSPA: 0.62 Ngotto : N/A | DSPA & Ngotto
GOAL | [7 empty] | Number of independent detection events of elephants captured with camera traps per unit of sampling day | Capture rate (# independent events/day) | Elephant Survey Data (With validated analyses and report) | Camera Trap Occupancy, Camera Trap Reconnaissance survey | Midline (Twice) |  | Propose to remove this indicator | [5 empty] | DSPA & Ngotto
GOAL |  |  |  | Great Apes |  | 1.2 | In 2035, number of Great Apes populations in the DSPA, the PNMB and their peripheries increase at least 2% compared to the 2020 (DSPA) and 2024 (Ngotto) baseline. | Number of individual great apes in the area | Measurement of the Population size | Great apes Survey Data (With validated analyses and report) | Line Transect Distance Sampling, Camera Trap Distance Sampling, DNA Capture-Recapture | Endline (Once) | 024) | DSPA : 2702 (2020) Ngotto: 931 (2024) |  |  |  |  | DSPA : 2757 Ngotto : 949 | DSPA & Ngotto
GOAL | [7 empty] | Number of great apes per surface area in sqkm | Density (n/sqkm) | Great apes Survey Data (With validated analyses and report) | Line Transect Distance Sampling, Camera Trap Distance Sampling, DNA Capture-Recapture | Endline (Once) |  | DSPA : 0.56 (2020) Ngotto : 0.12 (2024) |  |  |  |  | DSPA: 0.56 Ngotto: 0.3 | DSPA & Ngotto
GOAL |  |  | 1 |  |  |  |  | Number of sightings of great apes in an area per unit of sampling distance in km | Encounter rate (n/km) | Great apes Survey Data (With validated analyses and report) | Line Transect Distance Sampling, Walk Reconnaissance Survey | Midline (Twice) |  | DSPA : 1 (2020) Ngotto : 0.28 (2024) |  |  |  |  | DSPA : 1 Ngotto : 0.28 | DSPA & Ngotto
GOAL | [7 empty] | Proportion of surface area occupied by great apes in an area | Occupancy rate (%) or Spatial distribution | Great apes Survey Data (With validated analyses and report) | Line Transect Distance Sampling, Camera Trap Occupancy | Midline (Twice) |  | DSPA: 0,57 (2020) Ngotto: 0.58 (2024) |  |  |  |  | DSPA : 0,58 Ngotto : 0.59 | DSPA & Ngotto
GOAL | [7 empty] | Number of independent detection events of great apes captured with camera traps per unit of sampling day | Capture rate (# independent events/day) | Great apes Survey Data (With validated analyses and report) | Camera Trap Occupancy, Camera Trap Reconnaissance survey | Midline (Twice) |  | Propose to remove this indicator | [5 empty] | DSPA & Ngotto
GOAL | Wellbeing |  | 1 | Human wellbeing |  | 3.1 | By 2035, the well-being and resilience of targeted communities is improved by at least 10% relative to 2025 baseline | Wellbeing score | Wellbeing includes materials for good life, social cohesion, rights, access to natural resources/5 categories of wellbeing Targeted communities - IPLCs targeted in the APDS and the Ngotto Forest | Wellbeing survey data (with linked database) | Socioeconomic survey related to supported wellbeing aspects | Endline |  | DSPA: 64% (2025) Ngotto: 39 % (2024) |  |  |  |  | DSPA: 74% Ngotto: 49 % | DSPA & Ngotto
OUTCOME | Species Conservation | DSPA landscape; Ngotto landscape | 1 | Elephants | Poaching for ivory | 1.1.1 | By 2030, incidences of negative impacts (on people and wildlife) from human elephant conflict in our intervention areas in the DSPA and Ngotto landscapes are reduced by at least 25% compared to the baseline established in 2025 (By 2030, revenge killings of elephants in our intervention areas in the DSPA and Ngotto landscapes are reduced by at least 25% compared to the baseline established in 2025) | % of HEC incidents that have resulted in retaliatory killings of elephants | Numerator: Number of HEC incidents that have resulted in 1 or more elephants being killed. Divided by: Denominator: Number of reported HEC incidents | HEC database | Monitoring of HEC | Annually | 1. Targeted interventions (SAFE) is effective in adressing the HEC problem. | DSPA (2024) : 0% Ngotto : (2024): 0% | DSPA: 0% Ngotto: 0% | DSPA: 0% Ngotto: 0% | DSPA: 0% Ngotto: 0% | DSPA: 0% Ngotto: 0% | DSPA: 0% Ngotto: 0% | DSPA & Ngotto
OUTCOME | [7 empty] | Total number of elephants killed as a result of HEC retaliatory killings |  | HEC database | Monitoring of HEC | Annually |  | DSPA : 1.15 (2021) Ngotto: 0 (2024) | DSPA: 1.09 Ngotto: 0 | DSPA: 1.03 Ngotto: 0 | DSPA: 0.97 Ngotto: 0 | DSPA: 0.91 Ngotto: 0 | DSPA: 0.085 Ngotto: 0 | DSPA & Ngotto
OUTCOME | Species Conservation | DSPA landscape; Ngotto landscape | 1 | Elephants | Poaching/illegal hunting; Habitat destruction; Human elephant conflict | 1.1.2 | By 2030, the positive perception of HEC in our intervention areas in the DSPA and Ngotto landscapes is improved by at least 50% compared to the baseline established in 2025 | HEC perception score |  | Perception survey data | Perception Survey | Annually | 1. IPLC are willing to change there Perception on elephants positively | DSPA: TBD (2024) Ngotto: TBD (2024) | DSPA: TBD Ngotto: TBD | DSPA: 04 Ngotto:
OUTCOME | [7 empty] | % of reported complaints recorded each year linked to HEC | Numerator: The number of complaints linked to HEC each year Divided by: Denominator: The total number of reported complaints each year | Grievance mechanism database | Grievance mechanism system | Annually |  | DSPA: 04 (2024) Ngotto: 0 (2025) | DSPA: 02 Ngotto: 0 | DSPA: 04 Ngotto: 0 | DSPA: 03 Ngotto: 0 | DSPA: 02 Ngotto: 0 | DSPA: 02 Ngotto: 0 | DSPA & Ngotto
OUTCOME | Species Conservation |  | 1 | Elephants, Great Apes | Elephant poaching for ivory; Great apes poaching for bushmeat | 1.1.3 | By 2030, the number of poaching signs per unit of effort (n/km) in targeted landscapes (DPA, MBNP and its peripheries) is reduced by at least 25% compared to 2024 data | Number of poaching signs recorded per unit effort (n/km) | The outcome refers to all the focus species (elephants, great apes); the indicator refers to the encounter rate of poaching signs | Species Survey Database (With validated analyses and report) | Line Transect Distance Sampling, Camera Trap Distance Sampling, Walk Reconnaissance Survey | Midline (only measured half way and at the end) | 1. There is sufficient resources to support an integrated wildlife management strategy 2. The mandated authority successfully fullfil their madate 3. WWF International and NOs support and fund Law Enforcement activities | Ngotto (2024): 1.62 DSPA (2021): 1,15 | DSPA: 1.09 Ngotto: 1.52 | DSPA: 1.03 Ngotto: 1.42 | DSPA: 0.97 Ngotto: 1.32 | DSPA: 0.91 Ngotto: 1.22 | DSPA: 0.85 Ngotto: 1.12 | DSPA & Ngotto
OUTCOME | Species Conservation | DSPA landscape; Ngotto landscape | 1 | Elephants, Great Apes | Poaching/illegal hunting; Weak management | 1.1.4 | By 2030, supported protected areas (DSPA and MBNP) have improved their management effectivenes by at least 10% relative to the 2024 baseline. | Management effectiveness score per PA | Insert link to IMET page | IMET scoring database for PAs | IMET Score | Midline (only measured half way and at the end) | 1. PA staff apply their knowledge and skills in the management of PAs. 2. The results of IMET can be used for adaptive management | DSPA : 75% (2021) MBNP : 35% (2023) | NA | NA | DSPA : 80% MBNP : 40% | NA | DSPA : 75% MBNP : 45% | DSPA & Ngotto
OUTCOME | Species Conservation | DSPA landscape; Ngotto landscape | 1 | Elephants, Great Apes | Zoonoses | 1.1.5 | By 2030, the known transmission of zoonotic pathogens in the targeted areas (DSPA and Ngotto) is reduced compared to the 2025 baseline. | Number of individual persons affected by zoonotic cases | The known transmission of zoonotic pathogen agents [Mpox,Yellow fever, H1N5, Brucellosis, Lassa Fever, HIV]. Transmission can go in both ways or among themselves. One reported case includes 1 affected individual. | Landscape lab database (With validated analyses and report) | Lab test analysis | Annually | 1. Local populations and animal handlers adopt safer practices related to wildlife, livestock, and land use that reduce zoonotic spillover risks. | DSPA: 0 (2023) Ngotto (2025): 0 | DSPA & Ngotto: 0 | DSPA & Ngotto: 0 | DSPA & Ngotto: 0 | DSPA & Ngotto: 0 | DSPA & Ngotto: 0 | DSPA & Ngotto
OUTCOME | [7 empty] | Number of individual animals affected by zoonotic cases | The known transmission of zoonotic pathogen agents [Mpox,Yellow fever, H1N5, Brucellosis, Lassa Fever, HIV]. Transmission can go in both ways or among themselves. One reported case includes 1 affected individual animal. | Landscape lab database (With validated analyses and report) | Lab test analysis | Annually |  | DSPA: 0 (2023) Ngotto (2025): 0 | DSPA & Ngotto: 0 | DSPA & Ngotto: 0 | DSPA & Ngotto: 0 | DSPA & Ngotto: 0 | DSPA & Ngotto: 0 | DSPA & Ngotto
|  | DSPA & Ngotto |  |  | Human rights abuse | 3.1.1 | By 2030, the percentage of conservation related complaints related to WWF's supported conservation activities in target landscapes is reduced to 75% compared to the 2024 baseline | % of conservation related complaints related to CARCO conservation activities | This will be mesured on national level not on program level. Numerator: Number of conservation related complaints related to CCO conservation activities Divided by: Denominator: Number of conservation related complaints | Grievance mechanism database | Grievance mechanism system | Annually | The GRM in place is well-managed, used and not abused | DSPA: 100% (4/4) (2024) Ngotto: 0 (2025) | DSPA: 75% Ngotto: 0 | DSPA: 75% Ngotto: 0 | DSPA: 50% Ngotto: 0 | DSPA: 25% Ngotto: 0 | DSPA: 25% Ngotto: 0 | DSPA & Ngotto
OUTCOME
|  | DSPA & Ngotto |  |  | Limited support to conservation efforts | 3.1.2 | By 2030, at least 80% of targeted IP&LCs in WWF CAR-supported landscapes have a positive perception towards conservation projects/ideas. | % of IPLCs expressing positive perception towards conservation project/ideas | Landcapes - IP & LCs living around APDS and Ngotto | Survey data | Perception Survey | Annually | Conservation efforts produce tangible social or economic benefits for IPLCs (e.g., jobs, ecosystem services, access rights) | DSPA (2021) : 70% Ngotto: 60% | DSPA : 72% Ngotto: 64 | DSPA : 74% Ngotto: 68% | DSPA : 76% Ngotto: 72 % | DSPA : 78 % Ngotto: 76 % | DSPA : 80% Ngotto: 80 % | DSPA & Ngotto
|  | DSPA & Ngotto |  |  | Poverty; | 3.1.3 | By 2030, at least 50% of supported pupils/students complete primary education and at least 20% complete secondary education in their respective cohort | % supported primary school pupils that have completed their primary education |  | School records | School records | Annually | Parents/guardians and communities value and support education—especially for girls and IPs No major disruptions (e.g., political instability, natural disasters, pandemics) impact schooling | DSPA (2024) : 50% (768/1537) Ngotto : N/A | DSPA : 58% Ngotto : N/A | DSPA : 66% Ngotto : N/A | DSPA : 74% Ngotto : N/A | DSPA : 82% Ngotto : N/A | DSPA : 90% Ngotto : N/A | DSPA
[8 empty] | % supported secondary school students that have completed their secondary education |  | School records | School records | Annually |  | DSPA (2024) : 20 % (4/18) Ngotto : N/A | DSPA : 30% (5/18) Ngotto : N/A | DSPA : 35% (6/18) Ngotto : N/A | DSPA : 40% (7/18) Ngotto : N/A | DSPA : 45% (8/18) Ngotto : N/A | DSPA : 50 % (9/18) Ngotto : N/A | DSPA
[5 empty] | Poverty; Unemployment | 3.1.4 | By 2030, targeted IPLC gain at least a 10% increase in household income from WWF-supported activities compared to the 2025 baseline | Average household income of targeted IPLC | Household income could be derived from IGA value chains, tourism, etc | Household survey data (with linked database) | Household survey on WWF-supported activities | Annually | Markets remain stable or grow for the products/services linked to WWF-supported activities Climate and environmental conditions do not severely disrupt production (e.g., droughts, disease, flooding) | DSPA : 420 000 XAF Ngotto : 300 000 XAF | DSPA : 4 28400 XAF Ngotto : 306 000 XAF | DSPA : 436800 XAF Ngotto : 312 000 XAF | DSPA : 445200 XAF Ngotto : 318 000 XAF | DSPA : 453600 XAF Ngotto : 324 000 XAF | DSPA : 462 000 XAF Ngotto : 330 000 XAF | DSPA & Ngotto
[8 empty] | Average total annual income gained by IPLC through direct employment in conservation related activities | The income that is paid to IPLC directly from conservation activities | HR salary data (with linked database) | HR salary checks | Annually |  | DSPA (2022): 1080000XAF Ngotto (2025) : 960000 | DSPA: 1101600 XAF Ngotto : 984000 XAF | DSPA: 1123200 XAF Ngotto : 1008000 XAF | DSPA: 1144800 XAF Ngotto : 1032000 XAF | DSPA: 1166400 XAF Ngotto : 1032000 XAF | DSPA: 1188000 XAF Ngotto : 1056000 XAF | DSPA & Ngotto
|  | DSPA & Ngotto |  |  | Poverty | 3.1.5 | By 2030, the number of targeted IPLC communities in WWF-supported landscapes having access to materials of good life has increased by at least 50% relative to the 2025 baseline | % of targeted IPLC communities in the WWF-supported landscapes that have access to materials of good life | Access means the ability for the targeted group to make use of the materials. Materials of good life include portable water, health care, natural resources, food, education. Communities refers to a group of people living in one village. Numerator: Number of targeted communities with access to the materials of a good life Divided by: Denominator: Number of targeted communities | Community survey as well as program data (with linked database) | Community surveys and program progress reports | Annually | Communities are not subjected to conflict, displacement, or governance instability that disrupt access to basic needs or services. | DSPA : 42 % (8226/19586) Ngotto : 30 % (9329/31097) | DSPA : 52 % (10184/19586) Ngotto : 40 % (12438/31097) | DSPA : 62 % (12142/19586) Ngotto : 50 % (15547/31097) | DSPA : 72 % (14100/19586) Ngotto : 60 % (18656/31097) | DSPA : 72 % (14100/19586) Ngotto : 60 % (18656/31097) | DSPA : 72 % (14100/19586) Ngotto : 60 % (18656/31097) | DSPA & Ngotto
[5 empty] | Poverty | 3.1.6 | By 2030, the annual revenues generated by ecotourism activities contribute at least 10% of the DSPA operating budget and 10% to support socio-economic development of IPLCs | % of annual ecotourism revenue allocated to support APDS operating budget |  | Ecotourism allocation data | Ecotourism allocation data | Annually | 1. National and local policies remain supportive of ecotourism development and revenue-sharing with conservation areas and IPLCs. 2. Domestic, regional, and international tourists maintain or increase interest in visiting the DSPA due to its unique natural and cultural offerings. 3. Major external disruptions (e.g. pandemics, conflicts, climate disasters) do not severely impact travel or DSPA operations for extended periods. | DSPA (2024) : 9 % (37567656/417418400) Ngotto : N/A | DSPA : 9 % (37567656/417418400) Ngotto : N/A | DSPA : 9.5 % (39654748/417418400) Ngotto : N/A | DSPA : 9.5 % (39654748/417418400) Ngotto : N/A | DSPA : 10 % (41741840/417418400) Ngotto : N/A | DSPA : 10 % (41741840/417418400) Ngotto : N/A | DSPA
[8 empty] | % of annual ecotourism revenue allocated to support IPLC projects |  | Ecotourism allocation data | Ecotourism allocation data | Annually |  | DSPA (2024) : 7 % (29219288/417418400) Ngotto : N/A | DSPA : 7 % (29219288/417418400) Ngotto : N/A | DSPA : 8 % (33393472/417418400) Ngotto : N/A | DSPA : 9 % (37567656/417418400) Ngotto : N/A | DSPA : 9 % (37567656/417418400) Ngotto : N/A | DSPA : 10 % (41741840/417418400) Ngotto : N/A | DSPA
[5 empty] | Weak governance | 3.1.7 | By 2030, at least one new or revised policies or decisions promoting the rights and interests of IPLC enacted with with WWF support | Number of new or revised policy or decisions promoting the rights and interests of IPLC enacted with with WWF support | Policies include decrees or other circular decisions | Policy and advocacy database (With validated analyses and report) | Policy and advocacy activities | Annually | The government is willing to engage WWF and partners in the propositions, enacting and reviewing process | 0 | 0 | 1 | 1 | 1 | 1 | National
OUTCOME |  |  |  | This will be included under OM and mesured at national lebel. Please do not conside it under programs | Weak governance | 3.1.8 | By 2030, at least two national policies/ strategies or decrees of applications on biodiversity and environmental management are enacted or reviewed with support of WWF | Number of decrees enacted or reviewed with support of WWF | enacted and review is about getting a decree that supports the operationalisation of the law. | Policy and advocacy database (With validated analyses and report) | Policy and advocacy activities | Annually | The government is willing to engage WWF and partners in the propositions, enacting and reviewing process | 0 | 0 | 1 | 1 | 0 | 2 | National
[8 empty] | Number of national policies, strategies enacted or reviewed with support of WWF | This also includes international conventions (COPs) and national laws/decrees (NBSAP, NDC, CBD30x30). | Policy and advocacy database (With validated analyses and report) | Policy and advocacy activities | Annually |  | 0 | 1 | 0 | 1 | 1 | 3 | National
Programme Outputs (High level) Refers to the non-negotiable outputs that are critical for the success of the programme, based on the Theory of Change | [5 empty] | 1.1.1 | By 2030, Incidences of negative impacts (on people and wildlife) from human elephant conflict in our intervention areas in the DSPA and Ngotto landscapes are reduced by at least 25% compared to the baseline established in 2025
| Species Conservation |  |  |  | Retaliatory killing | 1.1.1.1 | By December 2026, an HEC management framework is operational in priority PAs in DSPA and Ngotto | Number of priority PAs with an operational HEC management framework | [5 empty] | DSPA: 0 (2025) Ngotto: 0 (2025) | DSPA: 0 Ngotto: 0 | DSPA: 1 Ngotto: 0 | DSPA: 1 Ngotto: 0 | DSPA: 1 Ngotto: 0 | DSPA: 1 Ngotto: 1 | DSPA & Ngotto | DSPA director & Ngotto Project Manager
[6 empty] | 1.1.1.2 | By 2030, dialogue and trust-building platforms between communities and conservation authorities are strenghtened | Number of functional HEC platforms established between communities and conservation authorities in target areas | [5 empty] | DSPA: 2 (2025) Ngotto: 1 (2025) | DSPA: 0 Ngotto: 2 | DSPA: 3 Ngotto: 5 | DSPA: 0 Ngotto: 5 | DSPA: 0 Ngotto: 5 | DSPA: 5 Ngotto: 18 | DSPA & Ngotto | DSPA director & Ngotto Project Manager
[8 empty] | Number of meetings held between communities and consevation authorities on HEC per year | [5 empty] | DSPA: xxx (2025) Ngotto: xxxx (2025) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto
[6 empty] | 1.1.1.3 | By 2030, awareness among local communities on elephant behavior, ecological importance, and non-lethal conflict resolution is increased | Number of outreach/awareness sessions on HEC mitigation conducted annually in target areas | [5 empty] | DSPA: 01 (2025) Ngotto: 1000 (2025) | DSPA: 4 Ngotto: 3000 | DSPA: 4 Ngotto: 4000 | 4 4000 | 4 4000 | 20 23000 | DSPA & Ngotto | DSPA director & Ngotto Project Manager
[8 empty] | Number of people participating in HEC awareness campaigns disagregated by theme and gender | [5 empty] | DSPA: 1000 (2024) Ngotto: xx (2024) | DSPA: 3000 Ngotto: 0 | DSPA: 4000 Ngotto: 0 | DSPA: 4000 Ngotto: 0 | DSPA: 4000 Ngotto: 0 | DSPA: 4000 Ngotto: 0 | DSPA & Ngotto
[6 empty] | 1.1.1.4 | By 2030, rapid response teams for managing human-elephant conflicts are trained and operational | Number of trained and equipped rapid response teams operational in target areas | [5 empty] | DSPA: 0 (2024) Ngotto: 0 (2024) | DSPA: 0 Ngotto: 0 | DSPA: 41 Ngotto: 0 | DSPA: 41 Ngotto: 0 | DSPA: 41 Ngotto: 0 | DSPA: 41 Ngotto: 0 | DSPA & Ngotto | DSPA director & Ngotto Project Manager
Average response time to HEC incidents
[6 empty] | 1.1.2 | By 2030, the positive perception of HEC in our intervention areas in the DSPA and Ngotto landscapes is improved by at least 50% compared to the baseline established in 2025
| Species Conservation |  |  |  | Negative perception on elephant | 1.1.2.1 | By December 2028, at least three community outreach and education programs on human-elephant coexistence are conducted annually in all target areas | # of community outreach and education program sessions on human-elephant co-existence conducted per year | [5 empty] | DSPA: 0 (2025) Ngotto: 0 (2025) | DSPA: 0 Ngotto: 0 | DSPA: 2 6000 | DSPA: 2 7000 | DSPA: 2 6000 | DSPA: 6 25000 | DSPA & Ngotto | DSPA director & Ngotto Project Manager
[6 empty] | 1.1.2.2 | By December 2026, community members are actively engaged in at least three elephant conservation and HEC mitigation initiatives per target area, through structured participation mechanisms | # of community members participating in the conservation and HEC mitigation initiatives | [5 empty] | DSPA: 0 (2024) Ngotto:0 (2024) | DSPA: 0 Ngotto: 0 | DSPA: 40 Ngotto: 0 | DSPA: 60 Ngotto: 0 | DSPA: 80 Ngotto: 0 | DSPA: 100 Ngotto: 0 | DSPA & Ngotto | DSPA director & Ngotto Project Manager
[8 empty] | # of elephant conservation and HEC mitigation initiatives conducted in target areas | [5 empty] | DSPA: 0 (2024) Ngotto: 0 (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto
[6 empty] | 1.1.2.3 | By December 2028, recognition and incentive schemes are established and implemented in all target communities to reward adoption of effective human-elephant coexistence practices | # of target communities with functioning recognition/incentive schemes | [5 empty] | DSPA: 0 (2024) Ngotto: 0 (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto | DSPA director & Ngotto Project Manager
[8 empty] | # of community groups recognized annually for coexistence practices | [5 empty] | DSPA: 0 (2024) Ngotto: 0 (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto
[6 empty] | 1.1.2.4 | By December 2026, surveys and participatory assessments are conducted annually in all target communities to monitor perceptions and inform adaptive communication strategies on human-elephant coexistence | # of annual surveys and or participatory assessments conducted in target communitites | [5 empty] | DSPA: 0 (2024) Ngotto: 0 (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto | DSPA director & Ngotto Project Manager
[6 empty] | 1.1.2.5 | By December 2027, support is provided to at least three alternative livelihood initiatives per target community that align with elephant conservation priorities, such as eco-tourism and beekeeping | # of community members benefiting from supported alternative livelihood initiatives | [5 empty] | DSPA: 220 (2024) Ngotto: 0 (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: 10 Ngotto: | DSPA: 20 Ngotto: | DSPA: 30 Ngotto: | DSPA & Ngotto | DSPA director & Ngotto Project Manager
[8 empty] | # of alternative livelihood initiatives supported in target communities | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto
[6 empty] | 1.1.3 | By 2030, the number of poaching signs per unit of effort (n/km) in targeted landscapes (DSPA, MBNP and its peripheries) is reduced by at least 25% compared to 2024 data
| Species Conservation |  |  |  | Key species poaching | 1.1.3 .1 | By December 2027, ethical law enforcement capacity is enhanced through training and deployment of rangers, and compliance with protected area regulations is monitored monthly using patrol data and incident reports | # of monthly patrol reports and incident summaries submitted | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | 32 | 128 | 224 | 320 | 416 | Ngotto forest
[8 empty] | % patrol coverage of the Protected area | [5 empty] | DSPA: 75%(2024) Ngotto: xx (2024) | DSPA: 75% Ngotto: xx% | DSPA: 75% Ngotto: xx% | DSPA: 75% Ngotto: xx% | DSPA: 75% Ngotto: xx% | DSPA: 75% Ngotto: xx% | Ngotto forest
[8 empty] | # of poaching signs per unit effort (n/km) | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) |  | 1.4 | 1.2 | 1 | 0.8 | Ngotto forest
[8 empty] | % of trained rangers that are deployed in target areas | [5 empty] | DSPA: 92% (80/87)(2024) Ngotto: 0% (2024) | DSPA: xxx% Ngotto: xxx% | DSPA: xxx% Ngotto: xxx% | DSPA: xxx% Ngotto: xxx% | DSPA: xxx% Ngotto: xxx% | DSPA: xxx% Ngotto: xxx% | Ngotto forest
[6 empty] | 1.1.3 .2 | By December 2028, formal collaboration mechanisms are established and operational with law enforcement agencies, judicial institutions, and TNS partners to support coordinated responses to wildlife crime and human-elephant conflict | # of minutes (PV) forwarded to the Public Prosecutor's Office/total number of minutes (PV) issued | [5 empty] | DSPA: 0 (2024) Ngotto: 0 (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto
[8 empty] | # of poachers convicted | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[6 empty] | 1.1.3 .3 | By December 2026, structured community engagement programs are implemented in all target areas to support active participation in wildlife and natural resource protection activities | # of community engagement programs implemented in target areas | [5 empty] | DSPA: 0 (2025) Ngotto: TDB (2025) | DSPA: 30 Ngotto: 0 | DSPA: 40 Ngotto: 0 | DSPA: 40 Ngotto: 0 | DSPA: 40 Ngotto: 0 | DSPA: 40 Ngotto: 20 | DSPA & Ngotto
[8 empty] | # of community members participating in protection-related activities | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto
[8 empty] | # of voluntary deposits of weapons per year. | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto
[6 empty] | 1.1.3 .4 | By December 2027, advanced tools and technologies—such as drones, camera traps, and real-time monitoring systems—are deployed and operational in all priority areas to enhance anti-poaching efforts | # of priority areas equipped with at least one advanced monitoring tool | [5 empty] | DSPA: 100% Ngotto 0 (2025) | Ngotto: 0 | Ngotto: 50% | 100% | 100% | 100% | DSPA & Ngotto
[8 empty] | # of incidents or poaching attempts detected through technological tools | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA & Ngotto
[6 empty] | 1.1.3 .5 | By December 2028, ethical law enforcement staff in all target areas receive training on human rights standards | # of law enforcement personnel trained on human rights standards | [5 empty] | 1. DSPA: 87 (2025) - Ngotto: 0 2. xxx | 1. 113 2. xxx | 1. 133 2. xxx | 1. 153 2. xxx | 1. 153 2. xxx | 1.153 2. xxx | DSPA & Ngotto
# of cases of human right violation in link with law enforcement activities
[6 empty] | 1.1.4 | By 2030, supported protected areas (DSPA and MBNP) have improved their management effectivenes by at least 5% relative to the 2024 (Ngotto) & 2023 (DSPA) baseline.
| Species Conservation |  |  |  | Poor PA management | 1.1.4.1 | By December 2029, a shared vision and governance framework for landscape management is developed and endorsed by key stakeholders, with operational cross-border cooperation mechanisms established and functioning across the transboundary landscape | # of governance frameworks extablished | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of cross-border cooperation mechanisms established and functioning | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[6 empty] | 1.1.4.2 | By December 2027, evaluations of protected area management effectiveness are conducted annually using the IMET tool, with results documented and action plans developed and shared with relevant stakeholders | IMET scores reported and shared | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of IMET assessments completed annually in protected areas | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of action plans developed and shared based on IMET results | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[6 empty] | 1.1.4.3 | By December 2028, education programs and materials promoting sustainable development are implemented in all target communities | # of education programs delivered | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of education materials distributed | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of pupils and students supported who complete their primary, secondary or university education in the WWF target areas | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[6 empty] | 1.1.4.4 | By December 2027, operational biological and socio-economic monitoring systems are established in all target areas, with data collected and reported annually to inform adaptive management | # of monitoring systems established in target areas | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of monitoring systems established and functional in target areas | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of annual monitoring reports produced and shared | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[6 empty] | 1.1.4.5 | By 2027, Gorilla and Mangabeys groups are monitored daily and data available for tourists and researchers to see, generating income for continuity and progress towards financial autonomy. | # of gorilla groups monitored daily | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of Mangabeys groups monitored daily | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of monitoring reports available for tourists and researchers | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[6 empty] | 1.1.4.6 | By June 2030, sustainable financing mechanisms are established and functioning in all target protected areas, providing consistent financial support for long-term management and conservation activities | # of sustainable financing mechanisms established in target protected areas | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | # of sustainable financing mechanisms established in target protected areas that are operational | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[8 empty] | % of annual management costs in target protected areas covered by sustainable financing sources | [5 empty] | DSPA: xxx(2024) Ngotto: xx (2024) | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto: | DSPA: Ngotto:
[6 empty] | 1.1.5 | By 2030, the known transmission of zoonotic pathogens in the targeted areas (DSPA and Ngotto) is reduced compared to the 2025 baseline.
| Species Conservation |  |  |  | Zoonotics disease outbreak | 1.1.5.1 | By December 2027, local health and veterinary personnel in all target areas are trained and equipped to implement early detection and response protocols for zoonotic diseases | # of health and veterinary personnel trained and equipped in target areas | [5 empty] | DSPA: 0 (2024) Ngotto: 0 (2024) | DSPA: 10 Ngotto: 0 | DSPA: 15 Ngotto: 0 | DSPA: 15 Ngotto:3 | DSPA: 15 Ngotto: 5 | DSPA: 15 Ngotto: 5 | DSPA & Ngotto
[8 empty] | # of carcasses sampled | [5 empty] | DSPA: xxx (2024) Ngotto: 0 (2024) | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA & Ngotto
[8 empty] | # of carcasses observed by field teams | [5 empty] | DSPA: xxx (2024) Ngotto: 0 (2024) | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA & Ngotto
[6 empty] | 1.1.5.2 | By December 2027, targeted training and awareness campaigns on biosecurity practices are conducted for communities, hunters, and bushmeat handlers in all high-risk areas | # of biosecurity training sessions conducted in high-risk areas | [5 empty] | DSPA: xxx (2024) Ngotto: 0 (2024) | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA & Ngotto
[8 empty] | # of training participants | [5 empty] | DSPA: 30 (2024) Ngotto: 0 (2024) | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: 50 Ngotto: xxxx | DSPA & Ngotto
[8 empty] | # of positive AVADARs alerts | [5 empty] | DSPA: xxx (2024) Ngotto: 0 (2024) | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA & Ngotto
[8 empty] | # of total AVADARs alerts | [5 empty] | DSPA: xxx (2024) Ngotto: 0 (2024) | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA: xxxx Ngotto: xxx | DSPA & Ngotto
[6 empty] | 1.1.5.3 | By December 2026, community awareness and education campaigns on zoonotic disease risks and prevention measures are implemented in all target areas | # of awareness campaigns conducted in target areas | [5 empty] | DSPA: 1 (2024) Ngotto: 0 (2024) | DSPA: 1 Ngotto: 0 | DSPA: 2 Ngotto: 0 | DSPA: 2 Ngotto: 1 | DSPA: 2 Ngotto: 1 | DSPA: 7 Ngotto: 3 | DSPA & Ngotto
[6 empty] | 1.1.5.4 | By December 2028, intersectoral One Health coordination mechanisms are established and operational in all target regions, | # of regions with functional One Health coordination mechanisms | [5 empty] | DSPA: 0 (2024) Ngotto: 0 (2024) | DSPA:1 Ngotto: 0 | DSPA:1 Ngotto: 0 | DSPA:1 Ngotto: 1 | DSPA:1 Ngotto: 1 | DSPA:1 Ngotto: 1 | DSPA & Ngotto
[8 empty] | # of quarterly joint planning and response meetings held | [5 empty] | DSPA: 0 (2024) Ngotto: 0 (2024) | DSPA:1 Ngotto: 0 | DSPA:4 Ngotto: 0 | DSPA:4 Ngotto: 2 | DSPA:4 Ngotto: 4 | DSPA:17 Ngotto: 10 | DSPA & Ngotto
[6 empty] | 1.1.5.5 | By December 2027, improved waste management and sanitation systems are established and operational in all key wildlife-human interface areas | # of improved waste management and sanitation systems established | [5 empty] | DSPA: 0 (2024) Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA
[8 empty] | # of interface areas with operational waste management and sanitation systems | [5 empty] | DSPA: 0 (2024) Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA: xxxx Ngotto: N/A) | DSPA
[6 empty] | 3.1.1 | By 2030, the percentage of conservation related complaints related to WWF's supported conservation activities in target landscapes is reduced by at least 90% compared to the 2024 baseline
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.1.1 | By December 2029, Local Development Plans are implemented in 20 IPLC communities with at least 70% community participation in planning and monitoring processes | Number of IPLC communities with Local Development Plans implemented | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 3 Ngotto : 3 | DSPA : 5 Ngotto : 8 | DSPA : 8 Ngotto : 12 | DSPA & Ngotto
[8 empty] | Percentage of community members participating in planning and monitoring activities | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 1 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 30 Ngotto : 20 | DSPA : 50 Ngotto : 50 | DSPA : 70 Ngotto : 70 | DSPA & Ngotto
[6 empty] | 3.1.1.2 | By June 2027, community-based conflict management and resolution mechanisms are operational in 15 target communities | Number of communities with operational conflict resolution committees or structures | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 3 | DSPA : 3 Ngotto : 5 | DSPA : 4 Ngotto : 7 | DSPA : 6 Ngotto : 9 | DSPA & Ngotto
[8 empty] | Number of community members trained in conflict resolution and mediation | [5 empty] | DSPA (2025): 7 Ngotto (2025) : 7 | DSPA : 7 Ngotto : 7 | DSPA : 14 Ngotto : 21 | DSPA : 21 Ngotto : 35 | DSPA : 28 Ngotto : 49 | DSPA : 42 Ngotto : 63 | DSPA & Ngotto
[6 empty] | 3.1.1.3 | By December2026, a functional grievance and escalation system for human rights and GBV is established in all intervention areas | Number of intervention areas with functional grievance and escalation mechanisms | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto
[8 empty] | Number of grievances received through the system | [5 empty] | DSPA (2025): 4 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 3 Ngotto : 1 | DSPA : 2 Ngotto : 1 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA & Ngotto
[8 empty] | Number of grievances addressed through the system | [5 empty] | DSPA (2025): 4 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 3 Ngotto : 1 | DSPA : 2 Ngotto : 1 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA & Ngotto
[6 empty] | 3.1.1.4 | By June 2026, standardized data monitoring systems are established and operational iin 10 partner institutions | Number of partner institutions using standardized data monitoring tools | [5 empty] | National (2025) : 0 | 0 | 2 | 5 | 8 | 10 | National
[8 empty] | Number of staff from partner institutions trained in data collection and reporting protocols | [5 empty] | National (2025) : 0 | 0 | 6 | 15 | 24 | 30 | National
[6 empty] | 3.1.1.5 | By December 2028, at least 10 human rights awareness campaigns are conducted across intervention areas | Number of human rights awareness campaigns conducted | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 0 | DSPA : 3 Ngotto : 0 | DSPA : 3 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA & Ngotto
[8 empty] | Estimated number of community members reached through campaigns | [5 empty] | DSPA (2025): 1000 Ngotto (2025) : 0 | DSPA : 3000 Ngotto : 0 | DSPA : 4000 Ngotto : 500 | DSPA : 4000 Ngotto : 1000 | DSPA : 4000 Ngotto : 1500 | DSPA : 4000 Ngotto : 2000 | DSPA & Ngotto
[6 empty] | 3.1.1.6 | By June 2026, a comprehensive GBV action plan is developed and implemented in all target communities | Number of target communities with GBV action plans developed | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 |  | DSPA : 1 Ngotto : 1 |  | DSPA : 2 Ngotto : 1 | DSPA & Ngotto
[8 empty] | Number of GBV prevention and response activities implemented under the action plans developed | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 |  | DSPA : 1 Ngotto : 1 |  | DSPA : 2 Ngotto : 1 | DSPA & Ngotto
[6 empty] | 3.1.2 | By 2030, at least XX% of targeted IP&LCs in WWF CAR-supported landscapes have a positive perception towards conservation projects/ideas.
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.2.1 | By December 2026, at least 10 conservation awareness and education campaigns are conducted annually in IP&LC communities | Number of conservation awareness campaigns conducted per year | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 0 | DSPA : 3 Ngotto : 0 | DSPA : 3 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA & Ngotto
[8 empty] | Estimated number of IPLC community members reached through campaigns | [5 empty] | DSPA (2025): 1000 Ngotto (2025) : 0 | DSPA : 3000 Ngotto : 0 | DSPA : 4000 Ngotto : 500 | DSPA : 4000 Ngotto : 1000 | DSPA : 4000 Ngotto : 1500 | DSPA : 4000 Ngotto : 2000 | DSPA & Ngotto
[6 empty] | 3.1.2.2 | By December 2027, participatory decision-making frameworks are established and operational in at least 10 conservation sites | Number of operational participatory decision-making frameworks established | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto
[8 empty] | Number of sites with operational participatory decision-making frameworks | [5 empty] | DSPA (2025): 2 Ngotto (2025) : 0 | DSPA : 2 Ngotto : 1 | DSPA : 2 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 4 Ngotto : 3 | DSPA : 5 Ngotto : 5 | DSPA & Ngotto
[6 empty] | 3.1.2.3 | By March 2026, at least 10 culturally appropriate communication tools (e.g., visual aids, local language materials, storytelling formats) are developed and used in all target IP&LC communities | Number of culturally appropriate communication tools developed | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 0 | DSPA : 2 Ngotto : 0 | DSPA : 3 Ngotto : 0 | DSPA : 4 Ngotto : 1 | DSPA : 5 Ngotto : 2 | DSPA : 6 Ngotto : 4 | DSPA & Ngotto
[8 empty] | Number of IPLC communities using the tools in conservation education or engagement | [5 empty] | DSPA (2025) : 1000 Ngotto (2025) : 0 | DSPA : 3000 Ngotto : 0 | DSPA : 4000 Ngotto : 0 | DSPA : 4000 Ngotto : 1000 | DSPA : 4000 Ngotto : 2000 | DSPA : 4000 Ngotto : 3000 | DSPA & Ngotto
[6 empty] | 3.1.2.4 | By December 2026, co-management structures involving IPLC representatives are established in two protected areas | Number of protected areas with formal co-management structures involving IPLCs | [5 empty] | DSPA (2019) : 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 |  | DSPA : 1 Ngotto : 1 |  | DSPA : 1 Ngotto : 1 | DSPA & Ngotto
[8 empty] | Number of IPLC representatives participating in co-management bodies | [5 empty] | DSPA (2019) : 11 Ngotto (2025) : 0 | DSPA : 11 Ngotto : 0 | DSPA : 11 Ngotto : 0 | DSPA : 11 Ngotto : 18 | DSPA : 11 Ngotto : 18 | DSPA : 11 Ngotto : 18 | DSPA & Ngotto
[6 empty] | 3.1.2.5 | By June 2027, at least 5 livelihood improvement initiatives (e.g., eco-tourism, sustainable harvesting, agroforestry) targetting 1000 households are implemented in target communities | Number of livelihood initiatives implemented in target communities | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 2 Ngotto : 0 | DSPA : 2 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA & Ngotto
[8 empty] | Number of households implementing at least one livelihood improvement initiative in target communities | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 0 | DSPA : 220 Ngotto : 0 | DSPA : 320 Ngotto : 0 | DSPA : 500 Ngotto : 100 | DSPA : 600 Ngotto : 200 | DSPA : 700 Ngotto : 300 | DSPA & Ngotto
[6 empty] | 3.1.2.6 | By March 2026, functional and accessible feedback and grievance mechanisms are established in all target landscapes | Number of target landscapes with operational feedback and grievance mechanisms | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto
[6 empty] | 3.1.2.7 | By December 2026, traditional ecological knowledge from IP&LCs is documented and integrated into conservation strategies | Number of landscapes where traditional ecological knowledge has been documented | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto
[8 empty] | Number of conservation strategies incorporating traditional knowledge | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto
[6 empty] | 3.1.3 | By 2030, at least 50% of supported pupils/students complete primary education and at least 20% complete secondary education in their respective cohort
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.3.1 | By December 2027, at least one Memorandum of Understanding (MoU) will be signed and operationalized between WWF and key education stakeholders to secure sustainable school funding mechanisms | Number of MoUs signed with education stakeholders | [5 empty] | DSPA (2025) : 0 Ngotto : N/A |  |  | DSPA : 1 Ngotto : N/A |  | DSPA : 1 Ngotto : N/A | DSPA
[8 empty] | Amount of funding secured/mobilised based on the MoUs | [5 empty] | DSPA (2025) : 0 Ngotto : N/A |  |  | DSPA : XAF 50000000 Ngotto : N/A | DSPA : XAF 55000000 Ngotto : N/A | DSPA : XAF 60000000 Ngotto : N/A | DSPA
[6 empty] | 3.1.3.2 | By June 2026, at least 10 qualified teachers will be recruited and deployed to target schools in WWF priority landscapes | Number of qualified teachers recruited and deployed to target schools | [5 empty] | DSPA (2024) : 0 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 3 Ngotto : N/A | DSPA : 6 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA
[6 empty] | 3.1.3.3 | By the end of each school cycle, school fees and essential learning-related costs will be fully covered for at least 50 Ba’Aka and other vulnerable children in WWF-supported landscapes | Number of Ba’Aka and other vulnerable children receiving full education support | [5 empty] | DSPA (2024) : 1603 Ngotto : N/A | DSPA : 1693 Ngotto : N/A | DSPA : 1750 Ngotto : N/A | DSPA : 1800 Ngotto : N/A | DSPA : 1900 Ngotto : N/A | DSPA : 2000 Ngotto : N/A | DSPA
[6 empty] | 3.1.3.4 | By December 2029, at least 10 target schools in WWF priority areas will receive comprehensive teaching and learning materials, including textbooks, stationery, and classroom supplies. | Number of schools receiving comprehensive set of teaching and learning materials | [5 empty] | DSPA (2025) : 20 Ngotto : N/A | DSPA : 25 Ngotto : N/A | DSPA : 25 Ngotto : N/A | DSPA : 25 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA
[6 empty] | 3.1.3.5 | By December 2030, five annual awareness campaigns will have been conducted in Ba’Aka communities to promote school enrollment | Number of school enrollment awareness campaigns conducted annually | [5 empty] | DSPA (2025) : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA : 3 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA
[8 empty] | Number of Ba’Aka community members reached through campaigns | [5 empty] | DSPA (2025) : 2400 Ngotto : N/A | DSPA : 2500 Ngotto : N/A | DSPA : 2800 Ngotto : N/A | DSPA : 3000 Ngotto : N/A | DSPA : 3500 Ngotto : N/A | DSPA : 4000 Ngotto : N/A | DSPA
[6 empty] | 3.1.3.6 | By June 2028, environmental education modules will have been developed and progressively integrated into the school curriculum in Yobé-Sangha, Nola and Salo areas | Number of environmental education modules developed and approved | [5 empty] | DSPA (2025) : 0 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA
Status of curriculum integration evidenced by the modules approved and used
[6 empty] | 3.1.3.7 | By December 2026, at least two exchange visits will have been organized for APDS community representatives to share best practices in education and conservation engagement across WWF-supported regions | Number of exchange visits conducted for APDS community representatives | [5 empty] | DSPA (2025) : 1 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA
[8 empty] | Number of APDS representatives participating in exchange visits | [5 empty] | DSPA (2025) : 2 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA
[6 empty] | 3.1.3.8 | By June 2028, at least 5 Nature Clubs will have been established and actively running in target schools or communities | Number of Nature Clubs established in target schools or communities | [5 empty] | DSPA (2025) : 3 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA : 25 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA
[8 empty] | Number of environmental activities conducted by Nature Clubs annually | [5 empty] | DSPA (2025) : 4 Ngotto : N/A | DSPA : 4 Ngotto : N/A | DSPA : 4 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA
[6 empty] | 3.1.4 | By 2030, targeted IPLC gain at least a 10% increase in household income from WWF-supported activities compared to the 2025 baseline
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.4.1 | By June 2026, a comprehensive baseline assessment of existing income-generating initiatives will be completed in all target communities within target areas | Number of target communities with completed baseline assessments | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto
[6 empty] | 3.1.4.2 | By December 2026, a community-based digital monitoring system will have been established and fully operational to track progress and impact of income-generating initiatives in at least 10 target communities. | Community based digital monitoring system available as evidenced by data outputs | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto
[8 empty] | Number of target communities using the digital monitoring system | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 2 Ngotto : 4 | DSPA : 8 Ngotto : 6 | DSPA : 10 Ngotto : 10 | DSPA & Ngotto
[6 empty] | 3.1.4.3 | By December 2025, at least 300 vulnerable households and 20 functional community groups will have been identified and validated for support within the target communities | # of beneficiary households identified for support | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 220 Ngotto : 0 | DSPA : 320 Ngotto : 100 | DSPA : 400 Ngotto : 200 | DSPA : 450 Ngotto : 250 | DSPA : 500 Ngotto : 300 | DSPA & Ngotto
[8 empty] | # of functional community groups identified for support | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 11 Ngotto : 0 | DSPA : 15 Ngotto : 5 | DSPA : 20 Ngotto : 10 | DSPA : 22 Ngotto : 12 | DSPA : 25 Ngotto : 15 | DSPA & Ngotto
[6 empty] | 3.1.4.4 | By June 2030, all identified households and community groups will have received essential inputs, technical training, and veterinary supplies | # of identified beneficiary households supported | [5 empty] | DSPA (2025) : 1000 Ngotto (2025) : 0 | DSPA : 2000 Ngotto : 0 | DSPA : 3000 Ngotto : 0 | DSPA : 3000 Ngotto : 1000 | DSPA : 3000 Ngotto : 2000 | DSPA : 4000 Ngotto : 3000 | DSPA & Ngotto
[6 empty] | 3.1.4.5 | By December 2030, at least 200 individuals (50% women and youth) are trained in vocational skills such as tailoring, carpentry, soap-making, mototaxi mechanics, hospitality, and electrical work | # of IPLC women trained in vocational skills | [5 empty] | DSPA (2024) : 10 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA : 40 Ngotto : N/A | DSPA : 50 Ngotto : N/A | DSPA
[8 empty] | # of IPLC men trained in vocational skills | [5 empty] | DSPA (2024) : 10 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA : 40 Ngotto : N/A | DSPA : 60 Ngotto : N/A | DSPA : 80 Ngotto : N/A | DSPA : 100 Ngotto : N/A | DSPA
[8 empty] | # of IPLC youth trained in vocational skills | [5 empty] | DSPA (2024) : 10 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA : 40 Ngotto : N/A | DSPA : 50 Ngotto : N/A | DSPA
[6 empty] | 3.1.4.6 | By March 2026, a market assessment report is completed analyzing demand, pricing, and value chains for non-timber forest products (NTFPs) and bushmeat in local and regional markets | Evidence of a market assessment report | [5 empty] | DSPA (2024) : 0 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 1 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto
[6 empty] | 3.1.4.7 | By December 2026, key components of the ZCC (Zone Cynégétique à Usage Contrôlé) management plan are implemented, including community patrols, zoning, and sustainable hunting practices in collaboration with local authorities | Number of community patrols conducted per quarter in the ZCC | Tracks the frequency and consistency of community-led patrols within the ZCC. |  |  |  |  | DSPA : 48100 (2025) | DSAP: 48100 | DSPA : 48100 | DSPA : 48100 | DSPA : 48100 | DSPA : 48100 | DSPA
[8 empty] | Percentage of hunting activities in ZCC compliant with sustainable hunting guidelines | Proportion of recorded hunting activities that adhere to established quotas, seasons, and species restrictions. |  |  |  |  | DSPA : TBD | DSPA : 50% | DSPA : 55% | DSPA : 60% | DSPA : 70 | DSPA : 75% | DSPA
[6 empty] | 3.1.4.8 | By December 2027, an inclusive agricultural strategy promoting agroforestry, cocoa, and Gnetum cultivation among others will have been developed and piloted in at least five target communities | Number of inclusive agricultural strategy documents developed and validated | Measures the completion and formal approval of the strategy document that integrates agroforestry, cocoa, Gnetum, and other crops. |  |  |  |  | National (2025) : 0 | 0 | 1 | 0 | 0 | 2 | National
[8 empty] | Number of target communities piloting the inclusive agricultural strategy | Tracks the number of communities where the strategy has been implemented on a pilot basis. |  |  |  |  | DSPA (2024) : 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 2 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA & Ngotto
[6 empty] | 3.1.4.9 | By December 2026, small-scale livestock farming (goats, poultry, pigs) will have been introduced and supported in at least 150 households through training, starter kits, and veterinary follow-up | Number of households receiving livestock starter kits and training | Tracks how many households have been equipped with animals (goats, poultry, pigs), basic inputs, and training to begin small-scale livestock farming. |  |  |  |  | DSPA (2024) : 0 Ngotto (2025) : N/A | DSPA : 30 Ngotto : N/A | DSPA : 50 Ngotto : N/A | DSPA : 80 Ngotto : N/A | DSPA : 120 Ngotto : N/A | DSPA : 150 Ngotto : N/A | DSPA
[8 empty] | Percentage of supported households receiving at least one veterinary follow-up visit within six months | Assesses the extent of veterinary support provided to ensure animal health and sustainability of the initiative. |  |  |  |  | DSPA (2024) : 0 Ngotto (2025) : N/A | DSPA : 100% Ngotto : N/A | DSPA : 100% Ngotto : N/A | DSPA : 100% Ngotto : N/A | DSPA : 100% Ngotto : N/A | DSPA : 100% Ngotto : N/A | DSPA
[6 empty] | 3.1.5 | By 2030, the number of targeted IPLC communities in WWF-supported landscapes having access to materials of good life has increased by at least 50% relative to the 2025 baseline
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.5.1 | By December 2027, essential medical equipment and small supplies will have been procured, delivered to the secondary hospital and used | Number of essential medical equipment and supply items procured and delivered | Tracks the total quantity of distinct equipment and supply items successfully delivered to the hospital. |  |  |  |  | DSPA (2025) : 2 Ngotto (2025) : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA
[8 empty] | # of patients treated in different health entities (hospital, FOSA, mobile clinic, private entities) (ref: gender, age class, ethnicity) | [5 empty] | DSPA (2025) : 2207 Ngotto (2025) : N/A | DSPA : 2500 Ngotto : N/A | DSPA : 2750 Ngotto : N/A | DSPA : 3000 Ngotto : N/A | DSPA : 3000 Ngotto : N/A | DSPA : 3000 Ngotto : N/A | DSPA
[6 empty] | 3.1.5.2 | By December 2027, at least 30 COGES (Health Committee) members are trained on health governance, planning, and accountability to enhance community participation in health service management | # of COGES members trained on health governance, planning, and accountability | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : N/A | DSPA : 0 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 15 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA
[6 empty] | 3.1.5.3 | By December 2028, a monitoring system will have been established and operational for at least 10 satellite health facilities (FOSA) in DSPA | Number of FOSA with functional monitoring systems established | Counts the number of satellite health facilities where the monitoring system (tools, processes, and personnel) has been set up and is operational. |  |  |  |  | DSPA (2025) : 0 Ngotto (2025) : N/A | DSPA : 0 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 7 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA
[6 empty] | 3.1.5.4 | By December 2028, at least 90% of BaAka newborns delivered in supported health facilities will have received birth certificates through collaboration with municipal civil registration services | Percentage of BaAka newborns delivered in supported health facilities who receive birth certificates | Measures the proportion of BaAka newborns who are officially registered and issued birth certificates through collaboration with municipal civil registration services. |  |  |  |  | DSPA (2023) :123 Ngotto : N/A | DSPA : 150 Ngotto : N/A | DSPA : 200 Ngotto : N/A | DSPA : 200 Ngotto : N/A | DSPA : 250 Ngotto : N/A | DSPA : 800 Ngotto : N/A | DSPA
[6 empty] | 3.1.5.5 | By June 2026, at least one BaAka staff member will be recruited and integrated into each WWF-supported health facility to improve cultural sensitivity and trust in healthcare delivery | # of Ba'Aka staff recruited and trained in the health programme | [5 empty] | DSPA (2025) : 0 Ngotto : N/A |  |  | DSPA : 1 Ngotto : N/A |  | DSPA : 1 Ngotto : N/A | DSPA
[6 empty] | 3.1.5.6 | By December 2029, at least four outreach health campaigns and two rounds of national vaccination drives will have been supported and implemented in BaAka communities | Number of outreach health campaigns conducted in BaAka communities | Number of outreach health campaigns conducted in BaAka communities |  |  |  |  | DSPA (2024) : 0 Ngotto : N/A | DSPA : 3 Ngotto : N/A | DSPA : 6 Ngotto : N/A | DSPA : 9 Ngotto : N/A | DSPA : 12 Ngotto : N/A | DSPA : 15 Ngotto : N/A | DSPA
[8 empty] | Number of national vaccination drive rounds supported and implemented in BaAka communities | Tracks the number of vaccination rounds that were successfully carried out with support in BaAka areas. |  |  |  |  | DSPA (2024) : 0 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 3 Ngotto : N/A
[6 empty] | 3.1.5.7 | By December 2028, medical consultation fees and mobile clinic services will have been covered for at least 1,000 BaAka individuals across all WWF-supported areas | Number of BaAka individuals who received free medical consultations or mobile clinic services | Counts the unique individuals who accessed services without paying fees, either at fixed health facilities or through mobile clinics. |  |  |  |  | DSPA (2025) : 403 Ngotto : N/A | DSPA : 500 Ngotto : N/A | DSPA : 600 Ngotto : N/A | DSPA : 750 Ngotto : N/A | DSPA : 850 Ngotto : N/A | DSPA : 1000 Ngotto : N/A | DSPA
[8 empty] | Number of mobile clinic visits conducted in WWF-supported areas | Tracks the number of mobile clinic deployments to BaAka communities within the supported zones. |  |  |  |  | DSPA (2025) : 6 Ngotto : N/A | DSPA : 6 Ngotto : N/A | DSPA : 7 Ngotto : N/A | DSPA : 7 Ngotto : N/A | DSPA : 8 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA
[6 empty] | 3.1.6 | By 2030, the annual revenues generated by ecotourism activities contribute at least 10% of the DSPA operating budget and 10% to support socio-economic development of IPLCs
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.6.1 | By December 2027, foundational infrastructure and governance frameworks for sustainable tourism will have been established in the target areas | Number of sustainable tourism governance frameworks developed and endorsed | Tracks the creation and formal approval of policies, guidelines, or institutional arrangements that support sustainable tourism. |  |  |  |  | DSPA (2024) : 0 Ngotto: N/A |  | DSPA : 1 Ngotto : N/A |  |  | DSPA : 1 Ngotto : N/A | Ngotto
[6 empty] | 3.1.6.2 | By December 2028, Doli Lodge’s profitability will be increased by at least 20% through improved financial management, staff training, and enhanced guest services | Percentage increase in net profit margin of Doli Lodge | Measures the change in profitability by comparing net profit margins before and after interventions. | [10 empty] | DSPA
[6 empty] | 3.1.6.3 | By December 2026, a digital marketing and reservation platform will have been launched and operational to improve online visibility and bookings for tourism services in the target area | Evidence of a digital platform launched and fully operational | Confirms the platform (website or app) is live, functional, and accessible to users, with core features such as service listings, booking functionality, and contact information. |  |  |  |  | DSPA (2024) : 0 Ngotto: N/A |  |  | DSPA : 1 Ngotto : N/A |  | DSPA : 1 Ngotto : N/A | Ngotto
[6 empty] | 3.1.6.4 | By December 2028, at least five community-based tourism initiatives are established and supported, with local communities trained and actively participating in guiding, hospitality, and cultural experiences. | Number of community-based tourism initiatives established and supported | Counts the total number of distinct tourism initiatives (e.g., eco-guiding, homestays, cultural performances) that have been formally launched with community involvement. |  |  |  |  | DSPA (2024) : 0 Ngotto: N/A | DSPA : 1 Ngotto: N/A | DSPA : 2 Ngotto: N/A | DSPA : 3 Ngotto: N/A | DSPA : 4 Ngotto: N/A | DSPA : 5 Ngotto: N/A | DSPA
[8 empty] | Number of community members trained and actively participating in tourism services | Tracks individuals from local communities who have received training and are engaged in guiding, hospitality, or cultural experience delivery. |  |  |  |  | DSPA (2024) : 0 Ngotto: N/A | DSPA : 50 Ngotto: N/A | DSPA : 100 Ngotto: N/A | DSPA : 150 Ngotto: N/A | DSPA : 200 Ngotto: N/A | DSPA : 300 Ngotto: N/A | DSPA
[6 empty] | 3.1.7 | By 2030, at least one new or revised policies or decisions promoting the rights and interests of IPLC enacted with with WWF support
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.7.1 | By December 2028, at least three CSO networks or coordination platforms are revitalized and actively functioning in WWF intervention landscapes in CAR | # of CSO networks revitalized | [5 empty] | National (2024) : 1 | National : 1 | National : 2 | National : 2 | National : 3 | National : 3 | National
[8 empty] | # of MoU with CSO network | [5 empty] | National (2024) : 0 | National : 0 | National : 1 | National : 2 | National : 3 | National : 3 | National
[6 empty] | 3.1.7.2 | By December 2029, at least 50 CSO representatives are trained in advocacy, organizational management, and lobbying | Number of CSO representatives trained in advocacy, organizational management, and lobbying | [5 empty] | National (2024) : 0 | National : 0 | National : 0 | National : 25 | National : 25 | National : 50 | National
[8 empty] | Number of training sessions conducted on advocacy, organizational management, and lobbying | [5 empty] | National (2024) : 0 | National : 0 | National : 0 | National : 1 | National : 1 | National : 2 | National
[6 empty] | 3.1.7.3 | By June 2030, at least 10 functional women’s associations will have received technical and financial support to implement or scale up local initiatives in conservation, livelihoods, or community development | Number of women’s associations receiving technical and financial support | [5 empty] | National (2025) : 0 | National : 0 | National : 0 | National : 5 | National : 5 | National : 10 | National
[8 empty] | Number of local initiatives implemented or scaled up by supported women’s associations | [5 empty] | National (2025) : 0 | National : 0 | National : 0 | National : 5 | National : 5 | National : 10 | National
[6 empty] | 3.1.7.4 | By December 2029, CSOs from WWF-supported landscapes participates in at least five local or national policy or planning forums related to environmental governance and community rights | # of CSOs participating in local and national initiatives with WWF support | [5 empty] | National (2025) : 0 | 2 | 4 | 6 | 8 | 10 | National
[6 empty] | 3.1.7.5 | By December 2030, at least five collaborative initiatives with Civil Society Organizations (CSOs) will have been developed and implemented in priority regions to promote the sustainable management and protection of natural resources | Number of collaborative initiatives with CSOs developed and implemented | Counts the total number of joint projects or programs launched with CSOs that focus on sustainable natural resource management and protection. |  |  |  |  | National (2025) : 0 | 1 | 2 | 3 | 4 | 5 | National
[8 empty] | # of projects implemented jointly with CSOs | [5 empty] | National (2025) : 0 | 0 | 0 | 1 | 1 | 1 | National
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Laurent Some it is important to have the risk assessment completed and a risk register done . I am available to support

## Programme Implementation Plan
| Output number | Output Statement | FY26 Cost | FY27 Cost | FY28 Cost | FY29 Cost | FY30 Cost | Total Output Cost + Management fee | Current Project (CPM Project #) | Target Funding Source
READ Me First |  | Please list all the outputs identified under the Factors & Outcome tab as well as the M&E plan. During the annual planning and budgeting process, the Programme will have opportunities to further refine and detail the activities and costs. The initial costing of the programme outputs can be estimated, which will be used to estimate the cost of total OSP implementation and the development of the financial plan. Please make sure to include activities related to M&E, ESSF and other risk mitigation, etc. "Please indicate the type of activities: - Programmatic - Innovation (ideation & prototyping & scale up) - M&E and Research - Risk mitigation/management (including ESSF) | [6 empty] | If the activity is already funded, please indicate the relevant CPM number(s). | If there is a funding gap and have prospective funding sources, please indicate the source.
| 1.1.1.1 | By December 2026, an HEC management framework is operational in priority PAs in DSPA and Ngotto | 0 | 67910.9292 | 70039.3385 | 65597.6894 | 68887.4823 | 306489.8693
| 1.1.1.2 | By 2030, dialogue and trust-building platforms between communities and conservation authorities are strenghtened | 29397.5818 | 20373.2788 | 21011.611 | 19678.7352 | 20666.7211 | 125018.9188
| 1.1.1.3 | by 2030, awareness among local communities on elephant behavior, ecological importance, and non-lethal conflict resolution is increased | 19599.6582 | 13582.1858 | 14008.0583 | 13120.1095 | 13777.4965 | 83348.4468
| 1.1.1.4 | By 2030, rapid response teams for managing human-elephant conflicts are trained and operational | 39197.4109 | 40746.5575 | 42023.222 | 39358.4231 | 41332.4894 | 227990.3658
| 1.1.2.1 | By December 2028, at least three community outreach and education programs on human-elephant coexistence are conducted annually in all target areas | 97994.48 | 101867.3466 | 105057.1023 | 98396.5341 | 103330.7471 | 569976.9862
| 1.1.2.2 | By December 2026, community members are actively engaged in at least three elephant conservation and HEC mitigation initiatives per target area, through structured participation mechanisms | 48997.24 | 67910.9292 | 70039.3385 | 65597.6894 | 68887.4823 | 361611.7643
| 1.1.2.3 | By December 2026, surveys and participatory assessments are conducted annually in all target communities to monitor perceptions and inform adaptive communication strategies on human-elephant coexistence | 19599.6582 | 20373.2788 | 21011.611 | 19678.7352 | 20666.7211 | 113996.2547
| 1.1.2.4 | By December 2027, support is provided to at least three alternative livelihood initiatives per target community that align with elephant conservation priorities, such as eco-tourism and beekeeping | 195988.0073 | 271643.7169 | 280154.4959 | 262390.7575 | 275549.9291 | 1446442.77
| 1.1.2.5 | By December 2028, recognition and incentive schemes are established and implemented in all target communities to reward adoption of effective human-elephant coexistence practices | 0 | 0 | 0 | 0 | 0
| 1.1.3 .1 | By December 2027, ethical law enforcement capacity is enhanced through training and deployment of rangers, and compliance with protected area regulations is monitored monthly using patrol data and incident reports | 1050377.6181 | 850257.6004 | 862781.298 | 830396.8929 | 896441.4149 | 5051536.6773
| 1.1.3 .2 | By December 2028, formal collaboration mechanisms are established and operational with law enforcement agencies, judicial institutions, and TNS partners to support coordinated responses to wildlife crime and human-elephant conflict | 72870.866 | 65037.4814 | 68098.6179 | 64779.2903 | 69120.9023 | 382395.5526
| 1.1.3 .3 | By December 2026, structured community engagement programs are implemented in all target areas to support active participation in wildlife and natural resource protection activities | 222014.8137 | 222507.3776 | 230271.2126 | 216442.2685 | 228141.8506 | 1259299.7134
| 1.1.3 .4 | By December 2027, advanced tools and technologies—such as drones, camera traps, and real-time monitoring systems—are deployed and operational in all priority areas to enhance anti-poaching efforts | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.3 .5 | By December 2028, ethical law enforcement staff in all target areas receive training on human rights standards | 58797.0691 | 33956.4173 | 28015.1638 | 26239.2663 | 27554.9929 | 196383.2731
| 1.1.4.1 | By December 2029, a shared vision and governance framework for landscape management is developed and endorsed by key stakeholders, with operational cross-border cooperation mechanisms established and functioning across the transboundary landscape | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.4.2 | By December 2027, evaluations of protected area management effectiveness are conducted annually using the IMET tool, with results documented and action plans developed and shared with relevant stakeholders | 14699.7436 | 0 | 10505.8055 | 0 | 10333.3605 | 39981.2734
| 1.1.4.3 | By December 2028, education programs and materials promoting sustainable development are implemented in all target communities | 0 | 0 | 0 | 13120.1095 | 20666.7211 | 38010.1844
| 1.1.4.4 | By December 2027, operational biological and socio-economic monitoring systems are established in all target areas, with data collected and reported annually to inform adaptive management | 97994.48 | 67910.9292 | 70039.3385 | 65597.6894 | 413324.8937 | 804225.7471
| 1.1.4.5 | By 2027, Gorilla groups and mangabeys group daily monitored and available for tourists and researchers to see, generating income for continuity and progress towards financial autonomy. | 299841.8057 | 216106.9059 | 232170.0129 | 300746.9037 | 482770.6785 | 1723090.8449
| 1.1.4.6 | By December 2029, sustainable financing mechanisms are established and functioning in all target protected areas, providing consistent financial support for long-term management and conservation activities | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.5.1 | By December 2027, local health and veterinary personnel in all target areas are trained and equipped to implement early detection and response protocols for zoonotic diseases | 29397.5818 | 27164.3717 | 28015.1638 | 26239.2663 | 27554.9929 | 155667.7985
| 1.1.5.2 | By December 2027, targeted training and awareness campaigns on biosecurity practices are conducted for communities, hunters, and bushmeat handlers in all high-risk areas | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.5.3 | By December 2026, community awareness and education campaigns on zoonotic disease risks and prevention measures are implemented in all target areas | 19599.6582 | 13582.1858 | 14008.0583 | 13120.1095 | 13777.4965 | 83348.4468
| 1.1.5.4 | By December 2028, intersectoral One Health coordination mechanisms are established and operational in all target regions, | 9799.8291 | 6791.0929 | 7003.5528 | 6559.5784 | 6889.2246 | 41673.6875
| 1.1.5.5 | By December 2027, improved waste management and sanitation systems are established and operational in all key wildlife-human interface areas | 29397.5818 | 33956.4173 | 49026.7748 | 45918.0015 | 48220.7612 | 232334.4787
| 3.1.1.1 | By December 2026, Local Development Plans are implemented in 20 IPLC communities with at least 70% community participation in planning and monitoring processes | 16852.9241 | 12146.4147 | 83067.0328 | 78288.1155 | 82747.8667 | 307240.1479
| 3.1.1.2 | By June 2026, community-based conflict management and resolution mechanisms are operational in 15 target communities | 16852.9241 | 32519.6934 | 34040.258 | 32369.1613 | 34527.1054 | 169097.785
| 3.1.1.3 | By December2026, a functional grievance and escalation system for human rights and GBV is established in all intervention areas | 16852.9241 | 25729.5532 | 27035.7525 | 25810.5357 | 27637.8808 | 138449.9771
| 3.1.1.4 | By December 2025, standardized data monitoring systems are established and operational iin 10 partner institutions | 16852.9241 | 12146.4147 | 13027.6942 | 12690.4262 | 13860.3844 | 77150.0739
| 3.1.1.5 | By December 2026, at least 10 human rights awareness campaigns are conducted across intervention areas | 26652.7532 | 18937.5076 | 20032.1997 | 19250.0046 | 20748.6562 | 118823.7614
| 3.1.1.6 | By June 2026, a comprehensive GBV action plan is developed and implemented in all target communities | 46251.4586 | 32519.6934 | 34040.258 | 32369.1613 | 27637.8808 | 194420.7587
Total Annual Cost + Management Fee |  |  | 2807866.1156 | 2560138.0642 | 2738838.3431 | 2692974.8857 | 3448188.1491 | 14248005.5578

## Result Chain
| Conservation Focus of the Programme | Priority Threats / Other Factors | Result ID | Program Outcomes | Relevant Geographic Scope | Relevant Thematic Scope | Annual Result - Year 1 | Output (Annual Result) - Year 2 | Output (Annual Result) - Year 3 | Output (Annual Result) - Year 4 | Output (Annual Result) - Year 5 | Key Assumptions & Risks | Sustainability & Exit Plan
READ Me First | Please copy the list of Conservation Focus from the previous tab. | For each Conservation Focus please list the priority threat (or other factors). Please use one line for each threat/factor. If a single threats affect more than one Conservation Focus, please list all the relevant conservation focus/focal interest under the column B. CMP Direct Threat Classification is available here - https://docs.google.com/spreadsheets/d/1rJSNz1LG_KOqoudVFglodx47HZ9LR-M6iVlRYMvn9Wk/edit#gid=310830663 Please ensure that priority threats/other factors are subset of those selected under the OSP. You may define further in detail. |  | Please Describe the desired reduction of threats (or changes to the identified factors). Please make sure the statement is SMART. | Please indicate the relevant Geographic Scope for each Outcome statement. Ensure to use one of the Geographic scope identified in the Scope tab of OSP Design Template. | Please indicate the relevant Thematic Scope for each Goal statement. Ensure to use one of the Thematic scope identified in the Scope tab of OSP Design Template. | Please define measurable Programme Annual Results which are milestones in achieving Programme outcomes. Therefore Programme Outcome must be embedded in the Programme Outputs. Outputs must represent tangible deliverables, within our area of control, that are critical to achieving the Programme Outcomes, in line with the Theory of Change. If there are areas of innovation and/or research, please make sure to include those outputs and activities as well. See the guidance on the approach to the Programme and Project Planning |  |  |  |  | Please identify the key assumptions that underpin the logical sequences linking Outputs, and Outcomes, and to one or more Goals Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment. WWF policies do not require risk assessment at program level but at Office level and at Project level. However each Program team is encouraged to perform Program Risk assessment. Use the Office risk register template in such case. | Please describe how your program aims to ensure the sustainability of the program outcome and an eventual exit by WWF. See Guidance by PPMS Step - Element 2.3
Example | Coral Reef Marine priority species | Overfishing / unsustainable fisheries |  | By 2030, fisheries management plans are in place (implemented & monitored) in 80% of coastal fisheries in ABC coastal communities. | Beta seascape | Ocean | Awareness of unsustainable fisheries increased in ABC coastal communities by 50% | Technical capacity of 10 fisheries communities built on fisheries management plan | 5 fisheries communities developed fisheries management plan | 4 fisheries communities developed fisheries management plan |  | Local communities can improve (or at least maintain) the economic state after the fisheries management plan. | Creation of alternative sustainable income to ensure that the sustainable implementation of the fisheries management plan. Also, inclusion of CSO (and their capacity building) in the project implementation to enable the eventual exit of WWF and transition of responsibility to the local CSO.
[5 empty] | Beta seascape | Ocean | Baseline assessment of current fisheries practices conducted for 10 fisheries in ABC coastal community |  |  | 50% of coastal fisheries are implementing and monitoring fisheries management plan | 80% of coastal fisheries are implementing and monitoring fisheries management plan
Note on I1: @hwilliams@wwfint.org, also here we should be align the language _Assigned to hwilliams@wwfint.org_ -Philip Kahuho

## Learning Questions
Learning Questions
READ Me First | Please articulate specific learning questions that your program will regularly reflect on for the learning priority. Max 100 words.
Example | - To what extent are the program's activities effective in achieving the planned results? - What worked and what didn’t? - Were there any unintended consequences? (positive or negative/ internal or external) - Were there any emergent results? (more than the planned results)