## Programme Profile
Read Me First
Programme Name | Please enter the Name of the Programme (Max 20 words) See the guidance on the approach to the Programme and Project Planning | Forests and other habitats
Program Lead | Please enter the Name of the Program Lead | Pierre Kafando
Program Team Member | Please list the name of Program Staff. This will be the list of staff who will have access to the Program information in the new PMEL system. | Laurent Somé Bruce Deguene Yoann Galeran Njunkeng Fualefac Ghislain Bellha Stef de Bethune Amandine Toumbou Antoine Edé Frédéric Singa Alphonsine Colombe Claude Bengono
Program Duration | Please indicate the duration of Program. Minimum Duration of the Program is 5 years. | FROM: | FY2026
|  | TO: | FY2030
Programme Description | Please enter a short description of the Programme (Max 200 words) | The Country Programme for CAR integrates species and habitat conservation across the Dzanga-Sangha Protected Areas (DSPA) and Ngotto landscapes, aiming to secure biodiversity and improve the well-being of Indigenous Peoples and Local Communities (IPLCs) by 2035. This integrated approach targets the protection of High Conservation Value (HCV) forests, forest elephants, great apes, and other threatened species through inclusive governance, sustainable livelihoods, and ecological resilience. The programme seeks to maintain 100% forest cover in Protected Areas and 95% in non-Protected Areas, while restoring degraded habitats and reducing forest conversion. Species conservation goals include stabilizing or increasing elephant and great ape populations, reducing poaching signs by 25%, and improving community attitudes toward wildlife. Key strategies include strengthening law enforcement, promoting sustainable land use and agroforestry, and expanding ecotourism and alternative livelihoods to reduce pressure on natural resources. In the biodiverse Ngotto landscape—including Mbaéré-Bodingué National Park (MBNP) and surrounding concessions—conservation success requires landscape-scale management due to ecological connectivity and growing human pressures. The programme emphasizes IPLC empowerment, secure land tenure, and education support, alongside policy advocacy for biodiversity protection and rights-based conservation. Together, these efforts aim to foster resilient ecosystems and empowered communities across CAR.
Program Focus / Focal Area | Please select one or more Conservation and/or Human well being Focus areas that your program will be focusing on. Please make sure this is a subset of what's selected in the OSP. | Forest Elephant Great Apes Dense forest High Conservation Value forests Adaptation to climate change Policy and advocacy Human well-being
Geographic Scope (Landscape) | Please list all the operational land/seascapes that are within the scope of the Program. For each land/seascape, provide short description of why the scape is critical in the context of this Program (max 200 words per land/seascape). Example: Name of the land/seascape: Description max 200 words. All land/seascapes must must apply ESSF. Guidance on landscape definition is here | Name of land/seascape | Description (Max 200 words)
|  | Dzanga-Sangha Protected Areas (DSPA) | The Dzanga-Sangha Protected Areas Complex (DSPA) in the Central African Republic spans 4,381 km² and plays a vital role in biodiversity conservation and supporting local communities through sustainable practices and ecotourism. Established in 1990, it includes the Dzanga-Ndoki National Park and the Dzanga-Sangha Special Dense Forest Reserve, hosting endangered species like forest elephants, gorillas, and chimpanzees. The DSPA's diverse habitats, including tropical forests and mineral-rich clearings, are critical for ecosystem connectivity, with the Sangha River being central to local fisheries. The region's population is ethnically diverse, with the BaAka indigenous people making up 21% and the Bilo migrant population 79%. Local governance involves both formal authorities and traditional land chiefs. The economy is driven by subsistence agriculture, fishing, artisanal mining, and hunting, though illegal activities like poaching and mining threaten conservation efforts. Despite improvements in infrastructure, health and education access remains limited, with common health issues including infectious diseases and malnutrition. Conservation faces challenges from resource extraction and climate change. Ecotourism offers economic opportunities, though its financial benefits remain modest. Balancing development and conservation is essential to ensure the region's sustainability.
|  | Ngotto Forest | The Ngotto Forest Complex in southwestern Central African Republic spans approximately 780,000 hectares, comprising the Mbaéré-Bodingué National Park (MBNP) and three surrounding logging concessions, with the broader landscape potentially extending to over one million hectares when including Dzanga-Sangha National Park (DSNP). The area forms a vital transition zone between savannah and tropical forest and supports rich biodiversity, including forest elephants, great apes, endemic species, and RAMSAR-listed wetlands. A 2024 survey recorded 27 mammal species, over 900 great apes, and 323 woody plant species, though small primates have declined sharply. Around 31,000 people—among them indigenous Bofi and 18 ethnic groups—depend on the landscape for subsistence agriculture, logging, mining, and bushmeat. However, the park alone is too small to ensure ecological integrity, making a conservation focus solely on MBNP impractical. Effective conservation must include the surrounding concessions, though this significantly increases the budgetary and logistical requirements. Key threats include illegal logging, poaching, deforestation, mining, climate change, and population pressure. Despite a history of political instability and underfunded conservation, recent ecological data and a landscape-scale approach offer renewed opportunities for integrated biodiversity protection and sustainable land management.
Thematic Scope (Practices) | Please list all the thematic that are relevant to the scope of the OSP. (Choice: Finance & Administration, Fundraising, Communications, P&C, Partnership, PMEL, etc.). For each theme, provide short description of why the theme is critical in the context of the OSP (max 200 words per theme). Example: Name of the theme: Description max 200 words. See Guidance by PPMS Step - Element 1.2 | Name of Thematic Scope | Description (Max 200 words)
|  | Forest and Other Habitats Programme | The Forest and Other Habitat Conservation Programme in CAR focuses on the DSPA and Ngotto landscapes. It aims to secure High Conservation Value (HCV) forests and vital habitats by 2035 while enhancing the well-being of Indigenous Peoples and Local Communities (IPLCs). Guided by a theory of change that emphasizes inclusive governance, sustainable development, and community stewardship, the programme targets maintaining 100% of forest cover in Protected Areas and at least 95% in non-Protected Areas. Core strategies include enforcing forest protection laws, promoting sustainable forest and land-use practices, and restoring degraded habitats—especially ecological corridors and riparian zones—by 25% over 2025 levels. WWF and partners will empower IPLCs through secure land tenure, participatory forest governance, and alternative livelihoods such as agroforestry, sustainable agriculture, and ecotourism. These efforts aim to improve community well-being by 10%, household incomes by at least 10%, and access to essential services by 50%. Policy advocacy will drive institutional reform, with an objective to enact at least two biodiversity policies and one IPLC rights law. By 2030, 75% of logging firms should have approved management plans, and ecotourism will contribute 10% of DSPA’s operational budget. The programme envisions resilient forests and empowered communities, advancing conservation through equity, sustainability, and adaptive management.

## Situation Analysis
Read Me First
Political | Please enter the concise analysis (narrative) of context and trends (political, social, economic, climate & environmental, and institutional) in country that has effects on the scope of the Programme. Depending on the nature of the program, some context may be more relevant than the others. (See Guidance by PPMS Step - Element 1.3, and IUCN-CMP Unified classification of Threat 2.0s) | • Government Stability and Capacity: CAR has experienced prolonged political instability, conflict, and weak governance. These factors undermine effective conservation enforcement, coordination, and long-term planning. • Security Risks: Armed groups, cross-border poaching networks, and illegal logging are facilitated by insecurity in and around DSPAs and Ngotto, threatening both wildlife and staff safety. • International Partnerships: Conservation programmes in DSPAs (co-managed with WWF) benefit from political support via international conservation agreements (e.g. CITES, CBD), but local political will remains inconsistent. • Decentralization and Local Governance: Ongoing efforts to devolve natural resource management to local authorities and communities can enhance ownership but also face capacity and corruption challenges.
Social |  | • Community Engagement and Customary Rights: Indigenous groups (e.g. BaAka) and rural communities have deep ties to forest resources. Exclusion or top-down conservation approaches have led to marginalization and conflict. • Education and Awareness: Low literacy and environmental awareness hinder local participation in conservation programmes, though community-based education initiatives in DSPAs are improving. • Cultural Practices: Traditional hunting practices can conflict with species protection, but also offer opportunities for culturally grounded conservation models when communities are empowered. • Demographic Pressure: Population growth, migration, and returnees (post-conflict) increase pressure on forest resources around Ngotto and the DSPAs.
Economic |  | • Poverty and Livelihood Dependency: High poverty levels in CAR push local communities to depend on forest resources (e.g. hunting, logging) for survival, creating tension with conservation goals. • Donor Dependence: Conservation in DSPAs and Ngotto is heavily reliant on external funding (e.g. EU, GEF), which makes programmes vulnerable to shifting donor priorities and financial sustainability risks. • Ecotourism Potential: DSPAs, especially the Dzanga Bai, have high ecotourism value (e.g. lowland gorillas, forest elephants), but fragile security and poor infrastructure limit economic benefits. • Informal Economy and Illicit Trade: Illegal logging, bushmeat trade, and trafficking of ivory or endangered species generate informal revenues that undermine conservation and divert economic gains from legal conservation-linked ventures.
Climate & Environmental |  | • Community Engagement and Customary Rights: Indigenous groups (e.g. BaAka) and rural communities have deep ties to forest resources. Exclusion or top-down conservation approaches have led to marginalization and conflict. • Education and Awareness: Low literacy and environmental awareness hinder local participation in conservation programmes, though community-based education initiatives in DSPAs are improving. • Cultural Practices: Traditional hunting practices can conflict with species protection, but also offer opportunities for culturally grounded conservation models when communities are empowered. • Demographic Pressure: Population growth, migration, and returnees (post-conflict) increase pressure on forest resources around Ngotto and the DSPAs.
Institutional |  | • Governance & Institutional Framework: Co-management model in DSPAs (WWF + government), but weak government presence and institutional structures in Ngotto. • Capacity Issues: Limited staffing, skills gaps, and underfunded conservation institutions, particularly in remote areas like Ngotto. • Coordination Challenges: Weak inter-ministerial and local governance coordination; transboundary cooperation exists in DSPAs but is often fragmented. • Funding & Sustainability: High reliance on external donors for DSPAs; Ngotto lacks stable funding and national resource allocation. • Legal & Enforcement Gaps: Weak judicial systems, limited law enforcement capacity (e.g., eco-guards), and corruption hinder effective conservation law enforcement. • Community Engagement: Stronger community-based conservation initiatives in DSPAs; Ngotto has less community organization and institutional support from NGOs.

## Stakeholder Analysis
| Stakeholder Name | Stakeholder Description | Stakeholder Type | Engagement Stage (planning, Implementation, MEL) | Engagement methods & strategies | Due Diligence (Y/N)
READ Me First | Please list key groups of stakeholders (people and organizations) who will be influenced by, have an impact on, or will help implement conservation to engage during the Programme planning, implementation, monitoring, and learning. Max 20 words. See Guidance by PPMS Step - Element 1.4 | Please briefly explain the significance of engaging with the stakeholder, and what you expect from the effective engagement. max 200 words | Please indicate the type of stakeholders (individual or organization): - Indigenous People & Local Communities - Civil Society Organization - Government's / Public Sector Organization - Companies / Private Sector - Universities / Research Organization - Other | Please indicate what stage each stakeholder group will be engaged - Programme planning, implementation, M&E, and Learning, etc. | Please describe how each stakeholder group will be engaged. Make sure that stakeholders will have regular access to the Programme information and, as appropriate, are aware of complaints procedures and feedback mechanisms. | For corporate & philanthropic partners (major donors, trusts, and foundations), please indicate if the due diligence is already conducted or not. For Other stakeholders, put NA. Corporate Partnership Rules & Guidelines Philanthropy Due Diligence
| MEFCP | National authority of co-management | Government's / Public Sector Organization |  | Responsible, within the framework of the general policy defined by the Government, for drawing up and implementing national policy in the fields of Water, Forests, Hunting and Fishing.
| MACT | National authority of management | Government's / Public Sector Organization
| MEDD | National authority of management | Government's / Public Sector Organization |  | Responsible, within the framework of the general policy defined by the Government, for drawing up and implementing national policy in the fields of Environment and Sustainable Development,
FTNS
UE
MEFP
| Ndima Kali |  | Indigenous People & Local Communities
Radio Njokou
| GDRNE |  | Civil Society Organization

## Focus & Goals
| Conservation Focus | Relevant OSP Goals | Key Assumptions
READ Me First | Please list each conservation focus / focal interest. Biodiversity Focal Interests can be focal species or habitats/ ecological systems. Human Wellbeing Focal Interests can be those component of human wellbeing affected by the status of biodiversity focal interests (material and non-material benefits obtained by ecosystem. Please ensure that focus / focal interest is a subset of those selected under the OSP. You may define further detail. | Based on the focus / focal interest selected, Please select the OSP Goal that your program is aiming to deliver. Please list the OSP Goal statement. | Please identify the key assumptions that underpin the logical sequences linking strategies to one or more focal interests. Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment.
Example | Coral Reef in Beta seascape. | Live coral reef covers at least 25% of the reef within the priority coastal seascapes in country Y. | WWF or its partner organization can monitor the live coral reef coverage in the coastal Beta seascape with proper funding.
| High conservation Value forest | By 2035, at least 90% of targeted HCV forests in priority landscapes are conserved to retain their key ecological functions relative to baseline (DSPA: 2020 & Ngotto: 2024) | 1. No sudden environmental disturbances that could lead to additional clearance of HCV forest surface HCV forests are covered by legal designations or agreements that are actively enforced by competent and committed authorities. HCV forests are resilient to climate shocks (e.g. fires, drought) through adaptation strategies and early warning systems.
| Dense forest | By 2035, the number of ha of dense forests in the targeted landscapes is maintained 100% intact in the targeted PAs and at least 95% in the non-PAs compared to 2020 | Government agencies and local management bodies have the resources, skills, and authority to implement forest protection and respond to threats effectively. Land-use plans in non-protected areas prioritize forest conservation through buffer zones, agroforestry, and community forest management schemes.
| Human Wellbeing | By 2035, the well-being and resilience of targeted communities is improved by at least 10% relative to 2025 baseline

## Narrative TOC
Read Me First
Narrative Theory of Change | Please articulate the Theory of Change in Narrative. A Theory of Change (ToC) should be underpinned by evidence of the logic. Articulate the causal pathway that leads from the current to the desired situation, describing how the Programme activities will deliver the envisioned Programme Outputs and Outcomes, and ultimately the Programme/OSP Goals. Key risks associated with the key assumptions along the Theory of Change to achieve its Programme Outcomes and Goals must be articulated. A risk is potential future event that may impact achievement of goals. Assumptions are explicit statements of what the CO assumes is true. The logical sequences must link activities to one or more focal interests as reflected in a theory of change. Assumptions may also express how external variables may influence the achievement of results. Max. 500 words See Guidance by PPMS Step - Element 2.1 | This theory of change aims to ensure the long-term conservation of High Conservation Value (HCV) forests and habitats in the DSPA and Ngotto landscapes, while enhancing the wellbeing of Indigenous Peoples and Local Communities (IPLCs) by 2035. It recognizes that effective conservation depends on strong governance, community stewardship, and inclusive economic development. By 2035, the goal is to keep at least 90% of targeted HCV forests intact, with 100% preserved in Protected Areas and at least 95% in non-Protected Areas, using 2020 as the baseline. Simultaneously, targeted communities are expected to experience at least a 10% improvement in wellbeing compared to 2025. These outcomes are based on key assumptions: that no major environmental or political disruptions (such as deforestation surges, conflict, or climate disasters) occur; that legal frameworks are enforced by capable authorities; and that stakeholders—including indigenous people and local communities, government, and the private sector—remain engaged and supportive. To achieve this, WWF and partners will promote legality and sustainable forest management, empower community forest governance, and expand sustainable agriculture and agroforestry. These efforts will halt forest conversion, restore degraded areas, and enhance livelihoods. By 2030, no HCV forests in targeted areas will be converted to other uses; at least 80% of supported farmers will apply best practices; and 75% of community forests will be sustainably managed. Habitat restoration will increase by 25% compared to 2025, assuming continued support from communities and private sector actors. Strengthened governance and policy frameworks are critical enablers. WWF will support policy advocacy and institutional reform to improve environmental protection and IPLC rights. By 2030, at least two national biodiversity-related policies and one IPLC rights policy or law will be enacted or revised. Simultaneously, at least 75% of logging companies will have approved management plans, driven by legal incentives, certification standards, and market demands. IPLC inclusion and empowerment are central to the change process. Rights-based conservation, fair grievance redress mechanisms, and sustainable income-generating activities will build trust and shared ownership. By 2030, conservation-related complaints will decrease by 90%, and IPLCs will increasingly view conservation efforts positively, thanks to tangible social and economic benefits. Household incomes will grow by at least 10%, and access to essential goods and services will improve by 50% compared to the 2025 baseline. Education support will result in at least 50% of pupils completing primary education and 20% completing secondary education, assuming stable community support and minimal disruption to schooling. Sustainable tourism will also contribute to conservation financing and community benefits. By 2030, ecotourism is expected to generate 10% of the DSPA’s operating budget and support IPLC socio-economic development by an equivalent amount, assuming favorable policies, consistent visitor interest, and stable operations. This integrated approach—linking forest conservation, inclusive governance, and sustainable development—is designed to foster resilient ecosystems, empowered communities, and long-term conservation success, underpinned by ongoing collaboration, capacity building, and adaptive management.
Opportunities for Innovation | Please articulate priority areas of innovation and research where needed. Innovation and Research activities must be included in the Programme Implementation Plan, Max. 500 words | We will engage with the government for conversion of logging concession into a conservation concession in the Dzanga Sangha Protected Areas landscape. This initiative aims to create a training and knowledge-transfer center that is truly rooted in the region, serving the empowerment of local populations and the preservation of natural and cultural heritage, while developing a center of excellence for inclusive socio-economic development, with national, regional and international reach in terms of training, applied research, territorial innovation and capacity-building.

## Program M&E Plan
RESULT LEVEL | PROGRAMMES | Relevant Geographic Scope | PROG_ID | FOCUS | Priority Threats / Other Factors | RESULT_ID | Statement | Indicator | Description | Means of Verification (Source of data) | Data Collection & Analysis Methodology | Frequency of Measurement | Assumptions & Risks | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Location | Responsible |  | Notes Meenu
GOAL | Forests & Other Habitats Conservation |  | 2 | High conservation Value forest |  | 2.1 | By 2035, at least 90% of targeted HCV forests in priority landscapes are conserved to retain their key ecological functions relative to baseline (DSPA: 2020 & Ngotto: 2024) | % of HCV forest that is kept intact | Forest intactness refers to the state of a forest that is largely free from significant human disturbance and fragmentation, retaining its natural structure and function. | Clearing and other FHCVs monitoring database | Data collection through camera traps and permanent presence of biomonitoring teams: Records on the size of the sites, the species present, the number of individuals visiting per species, the period of visit of species, etc. | Annually | 1. No sudden environmental disturbances that could lead to additional clearance of HCV forest surface HCV forests are covered by legal designations or agreements that are actively enforced by competent and committed authorities. HCV forests are resilient to climate shocks (e.g. fires, drought) through adaptation strategies and early warning systems. | DSPA (2024) : 88 % Ngotto (2024) : 85 % | DSPA : 88 % Ngotto : 85 % | DSPA : 89 % Ngotto : 86 % | DSPA : 89 % Ngotto : 87 % | DSPA : 90 % Ngotto : 88 % | DSPA : 90 % Ngotto : 90 %
GOAL | [7 empty] | Rate of use of HCV forest clearings of wildlife | Relates to the viability of the forest (Targeted forest include Saltflats, forest clearings, baïs) | Clearing and other FHCVs monitoring database | Data collection through camera traps and permanent presence of biomonitoring teams: Records on the size of the sites, the species present, the number of individuals visiting per species, the period of visit of species, etc. Rate of use: Average number of visits per species / day over one year | Annually |  | Propose to remove this indicator
GOAL | Forests & Other Habitats Conservation |  | 2 | Dense forest |  | 2.2 | By 2035, the number of ha of dense forests in the targeted landscapes is maintained 100% intact in the targeted PAs and at least 95% in the non-PAs compared to 2020 | Area (ha) of targeted forests maintained intact in Non-PAs | The number of hectares of dense forests measured in the targeted areas | Landcover monitoring data (with linked database) | Remote sensing | Midline (Twice) | Government agencies and local management bodies have the resources, skills, and authority to implement forest protection and respond to threats effectively. Land-use plans in non-protected areas prioritize forest conservation through buffer zones, agroforestry, and community forest management schemes. | Ngotto : 651000 ha DSPA: 311860 ha |  |  | Ngotto: 643188 ha DSPA: 311860 ha |  | Ngotto: 637980 ha DSPA: 311860 ha
GOAL | [7 empty] | Area (ha) of targeted forests maintained intact in PAs | The number of hectares of dense forests measured in the targeted areas | Landcover monitoring data (with linked database) | Remote sensing | Midline (Twice) |  | PNMB: 80000 ha DSPA: 126000 ha |  |  | PNMB: 80000 ha DSPA : 126000 ha |  | Ngotto: 80000 ha DSPA : 126000 ha
[8 empty] | Number of tonnes of the above ground carbon dioxide (CO2) stocked | Carbon stock in above ground biomass in the targeted PAs and non-PAs. | Carbon stock study database and report | Field-based study combined with remote sensing data through modelling process (Data could be used from current available data platforms like Global Forest Watch) | Annually |  | Ngotto: 112 547 026 tones (2025) DSPA: 67314720 tones (2025) | Ngotto: 112 547 026 tones DSPA: 67314720 tones | Ngotto: 112 547 026 tones DSPA: 67314720 tones | Ngotto: 112 547 026 tones DSPA: 67314720 tones | Ngotto: 112 547 026 tones DSPA: 67314720 tones | Ngotto: 112 547 026 tones DSPA: 67314720 tones | DSPA & Ngotto
GOAL | Wellbeing |  | 1,2 | Human Wellbeing |  | 3.1 | By 2035, the well-being and resilience of targeted communities is improved by at least 10% relative to 2025 baseline | Wellbeing score | Wellbeing includes materials for good life, social cohesion, rights, access to natural resources/5 categories of wellbeing Targeted communities - IPLCs targeted in the APDS and the Ngotto Forest | Wellbeing survey data (with linked database) | Socioeconomic survey related to supported wellbeing aspects | Endline |  | Ngotto (2024) : 39 % DSPA (2025): 64% |  |  |  |  | Ngotto (2024) : 49 % DSPA (2025): 74% | DSPA & Ngotto
OUTCOME | Forests & Other Habitats Conservation | DSPA landscape; Ngotto landscape | 2 | HCV forests | Logging (illegal and unsustainable); Mining (illegal or irresponsible) | 2.2.1 | By 2030, zero Ha of HCV forests converted to other land uses in targeted landscapes | Number of Ha of HCV forests converted to other land uses |  | Landcover monitoring data (with linked database) and field verification | Remote sensing and field verification | Endline (only measured half way and at the end) | 1. Weak regulations or poor enforcement could allow illegal or legal-but-unsustainable conversions. 2. Conflicting interests in conservation versus development intrests | MBNP (2020): 520 ha DSPA (2025) : 530 ha |  |  |  |  | Ngotto : 520 ha DSPA : 530 ha | DSPA & Ngotto
OUTCOME | Forests & Other Habitats Conservation |  | 2 |  | Weak natural resource management | 2.2.2 | By 2030, at least 80% of targeted farmers supported in priority landscapes use best agricultural practices. | % of farmers who adopt and implement best agricultural practices | Best Agricultural Practises follow Deforestation and Carbon Free -DCF program and nature positve practices. Implementation describes the effective operationalising as how it was intended. | Farm survey database (With validated analyses and report) | Farm survey | Anually | 1. The farmers will apply best management practices in managing their agricultural lands, even after the end of the support | MBNP (2020): 0% (0/500 farmers) DSPA (2025) : 18% (185/ 1000 farmers) | MBNP : 16% DSPA : 34% | MBNP : 32 % DSPA : 50 % | MBNP : 48% DSPA : 66% | MBNP : 64% DSPA : 82 % | Ngotto : 80% DSPA : 98% | DSPA & Ngotto
OUTCOME | [7 empty] | Number of hectares of agricultural land under Best Agricultural Practices | CAR targets at least 3000 ha of targetted land in APDS and Ngotto. Best Agricultural Practises follow Deforestation and Carbon Free -DCF program and nature positve practices. Implementation describes the effective operationalising as how it was intended. | Farm survey database (With validated analyses and report) | Farm survey | Annually |  | MBNP (2020): 0 (0/1000 ha) DSPA (2025) : 185 (185/ 2000 ha) | MBNP: 200 ha DSPA : 400 ha) | MBNP: 400 ha DSPA : 800 ha) | MBNP: 600 ha DSPA : 1200 ha) | MBNP: 800 ha DSPA :1600 ha) | Ngotto: 1000 ha DSPA :2000 ha) | DSPA & Ngotto |  | Updated
OUTCOME | Forests & Other Habitats Conservation | DSPA & Ngotto | 2 |  | Weak natural resource management | 2.2.3 | By 2030, at least 75% of supported community forest are managed using best practices, relative to 2025 baseline | % of community forest areas that are managed according to approved best practices | CAR targets at least 2 Community Forests of at least 10,000ha. Best practices include (PSG, in compliance with national legal procedures). Numerator: Hacteres of community forest managed according to approved best practices Divided by: Denominator: Hacteres of community forest | Community forest database (With validated analyses and report) | Forest area implementation survey | Anually | 1. IPLC apply best management practices in managing their community forest, even after the end of the support | MBNP (2020): 0 (0/2) DSPA (2025) : 50% (1/ 2) | MBNP : 0 (0/2) DSPA : 50% (1/ 2) | MBNP : 0 DSPA : 50% | MBNP : 50% (1/2) DSPA : 50% (2/2) | MBNP : 50% DSPA : 100% | Ngotto : 100% (2/2) DSPA : 100% (2/2) | DSPA & Ngotto
OUTCOME | Forests & Other Habitats Conservation | DSPA & Ngotto | 2 |  | Logging (illegal and unsustainable); habitat destruction | 2.2.4 | By 2030, the area of targeted habitat restored is increased by at least 25% compared to the 2025 baseline. | Area (in hectares) of habitat restored | CAR targets at least 2000 ha of new degraded areas in the Community Forests and the agricultural series of the targeted forest concessions for restoration. Restored zones are in community forests and fallow lands | Restoration database (With validated analyses and report) | Monitoring of restoration activities: recording of restored area size | Annually | 1. The private sector is willing to carry out restoration in their concessions, with the government/ law enforcement effectively monitoring | DSPA (2025): 220 ha Ngotto (2025): 0ha | DSPA : 250 ha Ngotto : 0ha | DSPA : 300 ha Ngotto : 100ha | DSPA : 400 ha Ngotto : 300ha | DSPA : 600 ha Ngotto : 600ha | DSPA : 1200 ha Ngotto : 1000ha | DSPA & Ngotto
OUTCOME | Forests & Other Habitats Conservation | DSPA & Ngotto | 2 |  | Logging (illegal and unsustainable); | 2.2.5 | By 2030, at least 75% of logging companies operating in target areas have approved management plans. | % of logging companies in operation that have an approved management plans | Targeted areas are areas located on the periphery of the DSPA and MBNP Numerator: No of logging companies with approved management plans Divided by: Denominator: All logging companies in the target areas | Approved management plan documents | Document review | Midline; endline | Operators recognize the long-term value of approved plans (e.g., legal access, market recognition) and are motivated to prepare and submit them. International buyers and certification schemes (e.g. FSC) increasingly demand proof of sustainable forest management, influencing company behavior. | DSPA (2025): 50% (1/2) Ngotto (2025): 66% (2/3) |  |  | DSPA : 50% Ngotto : 66% |  | DSPA 100% Ngotto: 100% | DSPA & Ngotto
|  | DSPA & Ngotto |  |  | Human rights abuse | 3.1.1 | By 2030, the percentage of conservation related complaints related to WWF's supported conservation activities in target landscapes is reduced to 75% compared to the 2024 baseline | % of conservation related complaints related to CARCO conservation activities | This will be mesured on national level not on program level. Numerator: Number of conservation related complaints related to CCO conservation activities Divided by: Denominator: Number of conservation related complaints | Grievance mechanism database | Grievance mechanism system | Annually | The GRM in place is well-managed, used and not abused | DSPA: 100% (4/4) (2024) Ngotto: 0 (2025) | DSPA: 75% (3/4) Ngotto: 0 | DSPA: 75% (3/4) Ngotto: 0 | DSPA: 50% (2/4) Ngotto: 0 | DSPA: 25% (1/4) Ngotto: 0 | DSPA: 25% (1/4) Ngotto: 0 |  |  |  | Outcome statement updates- 95% to 75%. Trargets Updated
Outcome statement updates- 95% to 75%
|  | DSPA & Ngotto |  |  | Limited support to conservation efforts | 3.1.2 | By 2030, at least 80% of targeted IP&LCs in WWF CAR-supported landscapes have a positive perception towards conservation projects/ideas. | % of IPLCs expressing positive perception towards conervation project/ideass | Landcapes - IP & LCs living around APDS and Ngotto | Survey data | Perception Survey | Annually | Conservation efforts produce tangible social or economic benefits for IPLCs (e.g., jobs, ecosystem services, access rights) | DSPA (2021) : 70% IPLC Ngotto: 60% | DSPA : 72% Ngotto: 64 | DSPA : 74% Ngotto: 68% | DSPA : 76% Ngotto: 72 % | DSPA : 78 % Ngotto: 76 % | DSPA : 80% Ngotto: 80 % | DSPA & Ngotto
|  | DSPA & Ngotto |  |  | Poverty; | 3.1.3 | By 2030, at least 90% of supported pupils/students complete primary education and at least 50% complete secondary education in their respective cohort | % supported primary school pupils that have completed their primary education |  | School records | School records | Annually | Parents/guardians and communities value and support education—especially for girls and IPs No major disruptions (e.g., political instability, natural disasters, pandemics) impact schooling | DSPA (2024) : 50% (768/1537) Ngotto : N/A | DSPA : 58% Ngotto : N/A | DSPA : 66% Ngotto : N/A | DSPA : 74% Ngotto : N/A | DSPA : 82% Ngotto : N/A | DSPA : 90% Ngotto : N/A | DSPA & Ngotto |  | Updated
[8 empty] | % supported secondary school students that have completed their secondary education |  | School records | School records | Annually |  | DSPA (2024) : 20 % (4/18) Ngotto : N/A | DSPA : 30% (5/18) Ngotto : N/A | DSPA : 35% (6/18) Ngotto : N/A | DSPA : 40% (7/18) Ngotto : N/A | DSPA : 45% (8/18) Ngotto : N/A | DSPA : 50 % (9/18) Ngotto : N/A | DSPA & Ngotto |  | Updated
[5 empty] | Poverty; Unemployment | 3.1.4 | By 2030, targeted IPLC gain at least a 10% increase in household income from WWF-supported activities compared to the 2025 baseline | Average household income of targeted IPLC | Household income could be derived from IGA value chains, tourism, etc | Household survey data (with linked database) | Household survey on WWF-supported activities | Annually | Markets remain stable or grow for the products/services linked to WWF-supported activities Climate and environmental conditions do not severely disrupt production (e.g., droughts, disease, flooding) | DSPA : 420 000 XAF Ngotto : 300 000 XAF | DSPA : 4 28400 XAF Ngotto : 306 000 XAF | DSPA : 436800 XAF Ngotto : 312 000 XAF | DSPA : 445200 XAF Ngotto : 318 000 XAF | DSPA : 453600 XAF Ngotto : 324 000 XAF | DSPA : 462 000 XAF Ngotto : 330 000 XAF | DSPA & Ngotto
[8 empty] | Average total annual income gained by IPLC through direct employment in conservation related activities | The income that is paid to IPLC directly from conservation activities | HR salary data (with linked database) | HR salary checks | Annually |  | DSPA (2022): 1080000XAF Ngotto (2025) : 960000 | DSPA: 1101600 XAF Ngotto : 984000 XAF | DSPA: 1123200 XAF Ngotto : 1008000 XAF | DSPA: 1144800 XAF Ngotto : 1032000 XAF | DSPA: 1166400 XAF Ngotto : 1032000 XAF | DSPA: 1188000 XAF Ngotto : 1056000 XAF | DSPA & Ngotto
|  | DSPA & Ngotto |  |  | Poverty | 3.1.5 | By 2030, the number of targeted IPLC communities in WWF-supported landscapes having access to materials of good life has increased by at least 30% relative to the 2025 baseline | % of targeted IPLC communities in the WWF-supported landscapes that have access to materials of good life | Access means the ability for the targeted group to make use of the materials. Materials of good life include portable water, health care, natural resources, food, education. Communities refers to a group of people living in one village. Numerator: Number of targeted communities with access to the materials of a good life Divided by: Denominator: Number of targeted communities | Community survey as well as program data (with linked database) | Community surveys and program progress reports | Annually | Communities are not subjected to conflict, displacement, or governance instability that disrupt access to basic needs or services. | DSPA : 42 % (8226/19586) Ngotto : 30 % (9329/31097) | DSPA : 52 % (10184/19586) Ngotto : 40 % (12438/31097) | DSPA : 62 % (12142/19586) Ngotto : 50 % (15547/31097) | DSPA : 72 % (14100/19586) Ngotto : 60 % (18656/31097) | DSPA : 72 % (14100/19586) Ngotto : 60 % (18656/31097) | DSPA : 72 % (14100/19586) Ngotto : 60 % (18656/31097) | DSPA & Ngotto |  | Updated | Targets Updated
[5 empty] | Poverty | 3.1.6 | By 2030, the annual revenues generated by ecotourism activities contribute at least 10% of the DSPA operating budget and 10% to support socio-economic development of IPLCs | % of annual ecotourism revenue allocated to support APDS operating budget |  | Ecotourism allocation data | Ecotourism allocation data | Annually | 1. National and local policies remain supportive of ecotourism development and revenue-sharing with conservation areas and IPLCs. 2. Domestic, regional, and international tourists maintain or increase interest in visiting the DSPA due to its unique natural and cultural offerings. 3. Major external disruptions (e.g. pandemics, conflicts, climate disasters) do not severely impact travel or DSPA operations for extended periods. | DSPA (2024) : 9 % (37567656/417418400) Ngotto : N/A | DSPA : 9 % (37567656/417418400) Ngotto : N/A | DSPA : 9.5 % (39654748/417418400) Ngotto : N/A | DSPA : 9.5 % (39654748/417418400) Ngotto : N/A | DSPA : 10 % (41741840/417418400) Ngotto : N/A | DSPA : 10 % (41741840/417418400) Ngotto : N/A | DSPA |  | Updated
[8 empty] | % of annual ecotourism revenue allocated to support IPLC projects |  | Ecotourism allocation data | Ecotourism allocation data | Annually |  | DSPA (2024) : 7 % (29219288/417418400) Ngotto : N/A | DSPA : 7 % (29219288/417418400) Ngotto : N/A | DSPA : 8 % (33393472/417418400) Ngotto : N/A | DSPA : 9 % (37567656/417418400) Ngotto : N/A | DSPA : 9 % (37567656/417418400) Ngotto : N/A | DSPA : 10 % (41741840/417418400) Ngotto : N/A | DSPA |  | Updated
[5 empty] | Weak governance | 3.1.7 | By 2030, at least one new or revised policies or decisions promoting the rights and interests of IPLC enacted with with WWF support | Number of new or revised policy or decisions promoting the rights and intrests of IPLC enacted with with WWF support | Policies include decrees or other circular decisions | Policy and advocacy database (With validated analyses and report) | Policy and advocacy activities | Annually | The government is willing to engage WWF and partners in the propositions, enacting and reviewing process | 0 | 0 | 0 | 1 | 0 | 1 | National
OUTCOME |  |  |  | This will be included under OM and mesured at national lebel. Please do not conside it under programs | Weak governance | 3.1.8 | By 2030, at least two national policies/ strategies or decrees of applications on biodiversity and environmental management are enacted or reviewed with support of WWF | Number of decrees enacted or reviewed with support of WWF | enacted and review is about getting a decree that supports the operationalisation of the law. | Policy and advocacy database (With validated analyses and report) | Policy and advocacy activities | Annually | The government is willing to engage WWF and partners in the propositions, enacting and reviewing process | 0 | 0 | 1 | 1 | 0 | 2 | National
[8 empty] | Number of national policies, strategies enacted or reviewed with support of WWF | This also includes international conventions (COPs) and national laws/decrees (NBSAP, NDC, CBD30x30). | Policy and advocacy database (With validated analyses and report) | Policy and advocacy activities | Annually |  | 0 | 0 | 1 | 1 | 1 | 3 | National
[6 empty] | 2.2.1 | By 2030, zero Ha of HCV forests converted to other land uses in targeted landscapes
| Forests & Other Habitats Conservation |  |  |  | Please write your output here >>>> Add more rows if needed | 2.2.1.1 | By December 2028, at least 500 hectares of cocoa, coffee and food crops are cultivated by smallholder farmers in designated non-HCV areas | Total hectares of cocoa, coffee, and food crops cultivated by smallholder farmers in non-HCV areas | Measures the cumulative land area under cultivation for the specified crops by smallholders in approved zones. | GIS maps, annual report |  |  |  | DSPA: 220 (2024) Ngotto : 400 (2024) | DSPA: 260 Ngotto : 400 | DSPA: 360 Ngotto : 450 | DSPA: 440 Ngotto : 550 | DSPA: 540 Ngotto : 650 | DSPA: 640 Ngotto : 750 | DSPA & Ngotto |  | Updated | Targets updated
[6 empty] | 2.2.1.2 | By june 2027, a strategy for planting coffee, cocoa and food crops outside High Conservation Values is developed. | Number of agricultural strategy available |  | Strategy document, final report |  |  |  | 0 | 0 | 1 | 1 | 1 | 1 | National |  | Updated | Targets updated
[6 empty] | 2.2.1.3 | By June 2028, at least 500 smallholder farmers have completed a certified training program on sustainable agriculture practices | Number of farmers issued certificates of completion |  | Attendance sheets, training reports, pre/post training assessments |  |  |  | DSPA : 0 (2025) Ngotto : 0 (2025) | DSPA : 0 Ngotto : 0 | DSPA : 50 Ngotto : 50 | DSPA : 50 Ngotto : 100 | DSPA : 50 Ngotto : 100 | DSPA : 50 Ngotto : 50 | DSPA & Ngotto |  | Updated | Targets updated
[6 empty] | 2.2.1.4 | By December 2027, 300 households in the target communities have adopted vegetable farming, evidenced by the establishment of home gardens or small plots | Number of households with established home gardens or small vegetable plots | Counts the households that have visibly set up and are actively maintaining vegetable gardens, either at home or on nearby plots. | Quaterly & annuals reports, periodic survey report |  |  |  | DSPA 0 (2025) Ngotto : 0 (2025) | DSPA : 0 Ngotto : 0 | DSPA : 30 Ngotto : 20 | DSPA : 50 Ngotto : 50 | DSPA : 50 Ngotto: 50 | DSPA : 20 Ngotto : 30 | DSPA & Ngotto |  | Updated | Targets updated
[6 empty] | 2.2.2 | By 2030, at least 80% of targeted farmers supported in priority landscapes use best agricultural practices.
| Species Conservation |  |  |  | Please write your output here >>>> Add more rows if needed | 2.2.2.1 | By December 2026, at least 300 farmers in the target communities are trained and equipped with deforestation-free agricultural best practices, with 80% receiving starter kits (e.g., agroforestry seedlings, composting tools), and demonstration plots established in each community to support adoption. | Number of farmers receiving and using starter kits | This indicator measures the number of trained farmers who have received and are actively using starter kits provided to support the adoption of deforestation-free agricultural practices. | Annuals reports, GIS maps |  |  |  | DSPA 0 (2025) Ngotto : 0 (2025) | DSPA : 0 Ngotto : 0 | DSPA : 30 Ngotto : 20 | DSPA : 50 Ngotto : 50 | DSPA : 50 Ngotto: 50 | DSPA : 20 Ngotto : 30 | DSPA & Ngotto |  | Updated | Target Updated. PI statement- Number of farmers actively applying starter kit inputs in their fields ( Should this be updated?)
[8 empty] | Number of demonstration plots established | This indicator tracks the number of demonstration plots set up in target communities to showcase deforestation-free agricultural practices |  |  |  |  | DSPA : 0 (2025) Ngotto : 0 (2025) | DSPA : 0 Ngotto : 0 | DSPA : 3 Ngotto : 0 | DSPA : 3 Ngotto : 2 | DSPA : 5 Ngotto : 5 | DSPA : 5 Ngotto : 5 | DSPA & Ngotto |  | Updated | Targets updated. Number of agricultural demonstration plots established
[6 empty] | 2.2.2.2 | By June 2027, three agricultural partnership models (e.g., contract farming, cooperative marketing, public-private partnerships) are piloted with at least 300 farmers, and one model scaled to an additional 300 farmers | Number of agricultural partnership models piloted |  | Contracts documents, attendance sheets, quaterly & yearly reports |  |  |  | DSPA : 0 (2025) Ngotto : 0 (2025) | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | 3 | DSPA & Ngotto |  | Updated | Targets updated barring endline. Please clarify if 3 applies to boyth landscapes
[8 empty] | Number of farmers participating in each partnership model | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 50 Ngotto : 50 | DSPA : 100 Ngotto : 100 | DSPA : 150 Ngotto : 150 | DSPA & Ngotto |  | Updated | Targets updated. New indicator created for Ngotto
[6 empty] | 2.2.2.3 | By September 2027, value chain support interventions (e.g., infrastructure, market access, processing facilities) are implemented in at least 5 areas | Number of value chain facilities (e.g., storage, processing) established |  | Reports documents, value chain document, |  |  |  | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA & Ngotto |  | Updated | Targets updated. New indicator created for Ngotto
[6 empty] | 2.2.3 | By 2030, at least 75% of supported community forest are managed using best practices, relative to 2025 baseline
[6 empty] | 2.2.3 .1 | By 2029, at least three community forests / OECMs are created and the management plans developed and implemented | # of management plans developed | [5 empty] | DSPA : 1 (2024) Ngotto : 0 (2025) | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 2 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | PI indicator- Number of simplified forest management plans developed and validated for community forests ( Should it be updated?) Blue font output updated in PI
[8 empty] | # of community forests / OECMs duly registered | [5 empty] | DSPA : 1 (2024) Ngotto : 0 (2025) | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 2 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | Didn't find indicator
[6 empty] | 2.2.3.2_1 | By December 2027, a comprehensive set of context-specific forest management best practices is developed, validated with stakeholders, and distributed to all supported community forests. | Number of community forests that have received and adopted the forest management best practice guidelines. | [5 empty] | DSPA : 1 (2024) Ngotto : 0 (2025) | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 2 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | Didn't find indicator
[6 empty] | 2.2.3.2_2 | By December 2026, community forest managers and governance bodies receive targeted training and ongoing technical support on implementing best practices in forest management. | Number of community forest managers and governance members trained on forest management best practices. | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA (2025): 10 Ngotto (2025) : 10 | DSPA (2025): 20 Ngotto (2025) : 20 | DSPA (2025): 20 Ngotto (2025) : 30 | DSPA & Ngotto |  | Updated | Didn't find indicator
| Species Conservation |  |  |  | Please write your output here >>>> Add more rows if needed | 2.2.3.3 | By December 2026, at least two non-timber forest product (NTFP) value chain are developed in partnership with Indigenous Peoples and Local Communities (IPLC) | Number of NTFP value chains co-developed with IPLCs |  | Value chain document, attendance sheets, annual report |  |  |  | DSPA : 0 (2025) Ngotto : 0 (2025) | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated | Targets Updated
[6 empty] | 2.2.3.3 |  | Number of IPLC members engaged in value chain development activities | [5 empty] | DSPA : 0 (2025) Ngotto : 0 (2025) | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 30 Ngotto : 0 | DSPA : 50 Ngotto : 50 | DSPA : 50 Ngotto : 50 | DSPA & Ngotto |  | Updated | Targets Updated
[6 empty] | 2.2.3.4 | By December 2028, at least 50 NTFP-based enterprises in IPLC areas are supported and strengthened through capacity building, access to markets, and financial services | Number of NTFP enterprises receiving capacity-building support |  | Annuals reports, contract doc withs locales company |  |  |  | DSPA : 0 (2025) Ngotto : 0 (2025) | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | PI outpout says 2026 and 10 NTFP (Needs updating?) Ngotto needs adding but first clarity on output name
[8 empty] | Number of NTFP enterprises accessing new markets or financial services | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | PI outpout says 2026 and 10 NTFP (Needs updating?) DSPA needs adding but first clarity on output name
[6 empty] | 2.2.3.5 | By June 2027, sustainable production systems for Gnetum africanum are established and promoted in at least 5 IPLC communities | Number of sustainable Gnetum africanum production systems established |  | Training report, attendance sheet |  |  |  | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 1 | DSPA : 0 Ngotto : 1 | DSPA : 0 Ngotto : 1 | DSPA & Ngotto |  | Updated | target Updated
[8 empty] | Number of IPLC communities with established and operational Gnetum africanum production systems | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 1 | DSPA : 1 Ngotto : 2 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | target Updated
[8 empty] | Number of IPLC farmers trained and applying sustainable Gnetum africanum cultivation practices | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 20 | DSPA : 10 Ngotto : 20 | DSPA : 20 Ngotto : 30 | DSPA & Ngotto |  | Updated | target Updated
[6 empty] | 2.2.3.6 | By December 2026, the beekeeping value chain is promoted and strengthened in at least 10 IPLC communities through training, provision of equipment, and market linkages | Number of IPLC communities supported with beekeeping training and equipment Number of beekeepers linked to markets or buyers | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 2 | DSPA : 1 Ngotto : 3 | DSPA : 3 Ngotto : 7 | DSPA & Ngotto |  | Updated | PI outpiut- By September 2026, at least 300 beekeepers are trained and equipped with modern hives and processing- (which is correct?). Ngotto needs updating
[6 empty] | 2.2.4 | By 2030, the area of targeted habitat restored is increased by at least 25% compared to the 2025 baseline.
| Forests & Other Habitats Conservation |  |  |  | Please write your output here >>>> Add more rows if needed | 2.2.4.1 | By December 2030, forest and landscape restoration pilots are implemented in 5 degraded sites, covering at least 2,000 hectares, with scaling strategies developed and documented. | # of hectares under active restoration through pilot interventions |  | GIS maps, annual report, partenersh agreement with IPLC, FLR management plan |  |  |  | DSPA (2025): 220 Ngotto (2025) : 0 | DSPA : 260 Ngotto : 0 | DSPA : 360 Ngotto : 100 | DSPA :400 Ngotto : 300 | DSPA : 600 Ngotto : 500 | DSPA : 800 Ngotto : 1200 | DSPA & Ngotto |  | Updated | Targets updated, Ngotto added
[8 empty] | Number of forest and landscape restoration pilot sites implemented | [5 empty] | DSPA (2025): 3 Ngotto (2025) : 0 | DSPA : 3 Ngotto : 0 | DSPA : 3 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA & Ngotto |  | Updated | Targets updated, Ngotto added
[6 empty] | 2.2.4.2 | By June 2030, 10 community forest management groups are supported with restoration plans, tools, and training, and at least 1000 hectares will be under active restoration. | Number of community forest management groups supported with restoration plans, tools and training |  | Community forest FLAR management plan, GIS maps |  |  |  | DSPA (2025): 3 Ngotto (2025) : 0 | DSPA : 3 Ngotto : 0 | DSPA : 3 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 4 Ngotto : 3 | DSPA : 5 Ngotto : 5 | DSPA & Ngotto |  | Updated | Targets updated, Ngotto added
[8 empty] | Number of hectares under active restoration by supported groups | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 40 Ngotto : 0 | DSPA : 100 Ngotto : 100 | DSPA : 200 Ngotto : 200 | DSPA : 300 Ngotto : 350 | DSPA : 500 Ngotto : 500 | DSPA & Ngotto |  | Updated | Targets updated, Ngotto added
[6 empty] | 2.2.4.3 | By June 2030, 100,000 seedlings of caterpillar-host tree species are raised and planted across 20 community-managed sites | Number of seedlings planted and geo-tagged |  | Anual report, community record, beneficiary survey |  |  |  | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 10000 Ngotto : 0 | DSPA : 25000 Ngotto : 25000 | DSPA : 50000 Ngotto : 50000 | DSPA : 50000 Ngotto : 50000 | DSPA : 50000 Ngotto : 50000 | DSPA & Ngotto |  | Updated | Targets updated, but output says Auguest in PI
[8 empty] | Number of community managed sites participating | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 3 Ngotto : 0 | DSPA : 3 Ngotto : 3 | DSPA : 6 Ngotto : 8 | DSPA : 10 Ngotto : 10 | DSPA : 10 Ngotto : 10 | DSPA & Ngotto |  | Updated | Targets updated, but output says Auguest in PI
[6 empty] | 2.2.5 | By 2030, at least 75% of logging companies operating in target areas have approved management plans.
| Forests & Other Habitats Conservation |  |  |  | Please write your output here >>>> Add more rows if needed | 2.2.5.1 | By December 2028, at least 5 forestry companies receive training and technical support on sustainable logging practices | Number of forestry companies completing training |  | Training report, attendance sheet |  |  |  | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto :3 | DSPA : 2 Ngotto : 3 | DSPA : 2 Ngotto : 3 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | PI indicator- Number of forestry companies completing training on sustainable logging practice.
[6 empty] | 2.2.5.2 | By December 2029, simplified forest management plans are developed and validated for 5 community forests, with local committees trained on implementation. | Number of simplified forest management plans developed and validated for community forests |  | Document of forest management plan, annual report |  |  |  | DSPA (2025): 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 2 | DSPA : 2 Ngotto : 2 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | Target updated
[8 empty] | Number of local forest management committee members trained on implementation of forest management plans | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 2 | DSPA : 2 Ngotto : 2 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | Ngotto pending - couldn't find output
[6 empty] | 2.2.5.3 | By March 2030, ecosystem service valuation tools are applied in 5 districts, and results integrated into local development plans and livelihood strategies. | Number of districts where ecosystem service valuation tools have been applied |  | Document of Local Development Plan, periodics report, reviews reports |  |  |  | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 2 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | Targets updated
[8 empty] | Number of local development plans and livelihood strategies integrating ecosystem service valuation results | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 2 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | Targets updated
[6 empty] | 2.2.5.4 | By June 2030, monitoring protocols and By June 2030, monitoring protocols and patrol systems are established in 5 logging concessions to protect intact forest landscapes are established in 5 logging concessions to protect intact forest landscapes | Number of logging concessions with operational monitoring protocols and patrol systems |  | Doc of partnership agreement, patrols reports, quaterly and yearly reports |  |  |  | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 2 | DSPA : 2 Ngotto : 3 | DSPA & Ngotto |  | Updated | Targets updated
[6 empty] | 2.2.5.5 | By December 2027, at least 50 government staff are trained on forest law enforcement, monitoring, and reporting systems | Number of government staff trained on forest law enforcement, monitoring, and reporting systems |  | Training report, attendance sheet |  |  |  | National (2025): 0 | National: 0 | National: 0 | National: 20 | National: 30 | National: 50 | National |  | Updated | Clarify Landscape
[6 empty] | 2.2.5.6 | By December 2028, 10 civil society organizations are trained and equipped for independent forest monitoring | Number of civil society organizations trained and equipped for independent forest monitoring |  | Training report, attendance sheet |  |  |  | National (2025): 0 | National: 0 | National: 0 | National: 10 | National: 10 | National: 10 | National |  | Updated | Clarify Landscape
[6 empty] | 3.1.1 | By 2030, the percentage of conservation related complaints related to WWF's supported conservation activities in target landscapes is reduced by at least 90% compared to the 2024 baseline
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.1.1 | By December 2026, Local Development Plans are implemented in 20 IPLC communities with at least 70% community participation in planning and monitoring processes | Number of IPLC communities with Local Development Plans implemented |  | Community survey report, annual report |  |  |  | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 3 Ngotto : 3 | DSPA : 5 Ngotto : 8 | DSPA : 8 Ngotto : 12 | DSPA & Ngotto |  | Updated | Targets updated
[8 empty] | Percentage of community members participating in planning and monitoring activities | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 1 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 30 Ngotto : 20 | DSPA : 50 Ngotto : 50 | DSPA : 70 Ngotto : 70 | DSPA & Ngotto |  | Updated | Clarify numerator and denominator
[6 empty] | 3.1.1.2 | By June 2026, community-based conflict management and resolution mechanisms are operational in 15 target communities | Number of communities with operational conflict resolution committees or structures |  | Training report, attendance sheet, activities report |  |  |  | DSPA (2025): 1 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 2 Ngotto : 3 | DSPA : 3 Ngotto : 5 | DSPA : 4 Ngotto : 7 | DSPA : 6 Ngotto : 9 | DSPA & Ngotto |  | Updated | Targets updated
[8 empty] | Number of community members trained in conflict resolution and mediation | [5 empty] | DSPA (2025): 7 Ngotto (2025) : 7 | DSPA : 7 Ngotto : 7 | DSPA : 14 Ngotto : 21 | DSPA : 21 Ngotto : 35 | DSPA : 28 Ngotto : 49 | DSPA : 42 Ngotto : 63 | DSPA & Ngotto |  | Updated | Targets updated
[6 empty] | 3.1.1.3 | By December2026, a functional grievance and escalation system for human rights and GBV is established in all intervention areas | Number of intervention areas with functional grievance and escalation mechanisms | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated | Targets updated
[8 empty] | Number of grievances received through the system | [5 empty] | DSPA (2025): 4 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 3 Ngotto : 1 | DSPA : 2 Ngotto : 1 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA & Ngotto |  | Updated | PI Indicator- % of grievances received through the system that are addressed 9 Clarify N/D)
[8 empty] | Number of grievances addressed through the system | [5 empty] | DSPA (2025): 4 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 3 Ngotto : 1 | DSPA : 2 Ngotto : 1 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA & Ngotto |  | Updated | Indicator not found
[6 empty] | 3.1.1.4 | By December 2025, standardized data monitoring systems are established and operational in 10 partner institutions | Number of partner institutions using standardized data monitoring tools | [5 empty] | National (2025) : 0 | 0 | 2 | 5 | 8 | 10 |  |  | Updated | Clarify Landscape
[8 empty] | Number of staff from partner institutions trained in data collection and reporting protocols | [5 empty] | National (2025) : 0 | 0 | 6 | 15 | 24 | 30 |  |  | Updated | Clarify Landscape
[6 empty] | 3.1.1.5 | By December 2028, at least 10 human rights awareness campaigns are conducted across intervention areas | Number of human rights awareness campaigns conducted | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 0 | DSPA : 3 Ngotto : 0 | DSPA : 3 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 |  |  | Updated
[8 empty] | Estimated number of community members reached through campaigns | [5 empty] | DSPA (2025): 1000 Ngotto (2025) : 0 | DSPA : 3000 Ngotto : 0 | DSPA : 4000 Ngotto : 500 | DSPA : 4000 Ngotto : 1000 | DSPA : 4000 Ngotto : 1500 | DSPA : 4000 Ngotto : 2000 |  |  | Updated | Is this PI indicator correct- Number of Ba’Aka community members reached through campaigns?
[6 empty] | 3.1.1.6 | By June 2028, a comprehensive GBV action plan is developed and implemented in all target communities | Number of target communities with GBV action plans developed | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 |  | DSPA : 1 Ngotto : 1 |  | DSPA : 2 Ngotto : 1 |  |  | Updated | Complete targets?
[8 empty] | Number of GBV prevention and response activities implemented under the action plans developed | [5 empty] | DSPA (2025): 0 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 |  | DSPA : 1 Ngotto : 1 |  | DSPA : 2 Ngotto : 1 |  |  | Updated | Complete targets?
[6 empty] | 3.1.2 | By 2030, at least XX% of targeted IP&LCs in WWF CAR-supported landscapes have a positive perception towards conservation projects/ideas.
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.2.1 | By December 2026, at least 10 conservation awareness and education campaigns are conducted annually in IP&LC communities | Number of conservation awareness campaigns conducted per year | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 0 | DSPA : 3 Ngotto : 0 | DSPA : 3 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA & Ngotto |  | Updated | Targets updated
[8 empty] | Estimated number of IPLC community members reached through campaigns | [5 empty] | DSPA (2025): 1000 Ngotto (2025) : 0 | DSPA : 3000 Ngotto : 0 | DSPA : 4000 Ngotto : 500 | DSPA : 4000 Ngotto : 1000 | DSPA : 4000 Ngotto : 1500 | DSPA : 4000 Ngotto : 2000 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.2.2 | By December 2027, participatory decision-making frameworks are established and operational in at least 10 conservation sites | Number of operational participatory decision-making frameworks established | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated
[8 empty] | Number of sites with operational participatory decision-making frameworks | [5 empty] | DSPA (2025): 2 Ngotto (2025) : 0 | DSPA : 2 Ngotto : 1 | DSPA : 2 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 4 Ngotto : 3 | DSPA : 5 Ngotto : 5 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.2.3 | By March 2026, at least 10 culturally appropriate communication tools (e.g., visual aids, local language materials, storytelling formats) are developed and used in all target IP&LC communities | Number of culturally appropriate communication tools developed | [5 empty] | DSPA (2025): 1 Ngotto (2025) : 0 | DSPA : 2 Ngotto : 0 | DSPA : 3 Ngotto : 0 | DSPA : 4 Ngotto : 1 | DSPA : 5 Ngotto : 2 | DSPA : 6 Ngotto : 4 | DSPA & Ngotto |  | Updated
[8 empty] | Number of IPLC members using the tools in conservation education or engagement | [5 empty] | DSPA (2025) : 1000 Ngotto (2025) : 0 | DSPA : 3000 Ngotto : 0 | DSPA : 4000 Ngotto : 0 | DSPA : 4000 Ngotto : 1000 | DSPA : 4000 Ngotto : 2000 | DSPA : 4000 Ngotto : 3000 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.2.4 | By December 2026, co-management structures involving community representatives are established in two protected areas | Number of protected areas with formal co-management structures involving IPLCs | [5 empty] | DSPA (2019) : 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 |  | DSPA : 1 Ngotto : 1 |  | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated
[8 empty] | Number of IPLC representatives participating in co-management bodies | [5 empty] | DSPA (2019) : 11 Ngotto (2025) : 0 | DSPA : 11 Ngotto : 0 | DSPA : 11 Ngotto : 0 | DSPA : 11 Ngotto : 18 | DSPA : 11 Ngotto : 18 | DSPA : 11 Ngotto : 18 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.2.5 | By June 2027, at least 5 livelihood improvement initiatives (e.g., eco-tourism, sustainable harvesting, agroforestry) targetting 1000 households are implemented in target communities | Number of livelihood initiatives implemented in target communities | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 2 Ngotto : 0 | DSPA : 2 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA & Ngotto |  | Updated
[8 empty] | Number of households implementing at least one livelihood improvement initiative in target communities | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 0 | DSPA : 220 Ngotto : 0 | DSPA : 320 Ngotto : 0 | DSPA : 500 Ngotto : 100 | DSPA : 600 Ngotto : 200 | DSPA : 700 Ngotto : 300 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.2.6 | By March 2026, functional and accessible feedback and grievance mechanisms are established in all target landscapes | Number of target landscapes with operational feedback and grievance mechanisms | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.2.7 | By December 2026, traditional ecological knowledge from IP&LCs is documented and integrated into conservation strategies | Number of landscapes where traditional ecological knowledge has been documented | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated
[8 empty] | Number of conservation strategies incorporating traditional knowledge | [5 empty] | DSPA (2025) : 1 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.3 | By 2030, at least 50% of supported pupils/students complete primary education and at least 20% complete secondary education in their respective cohort
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.3.1 | By December 2027, at least one Memorandum of Understanding (MoU) will be signed and operationalized between WWF and key education stakeholders to secure sustainable school funding mechanisms | Number of MoUs signed with education stakeholders | [5 empty] | DSPA (2025) : 0 Ngotto : N/A |  |  | DSPA : 1 Ngotto : N/A |  | DSPA : 1 Ngotto : N/A | DSPA |  | Updated
[8 empty] | Amount of funding secured/mobilised based on the MoUs | [5 empty] | DSPA (2025) : 0 Ngotto : N/A |  |  | DSPA : XAF 50000000 Ngotto : N/A | DSPA : XAF 55000000 Ngotto : N/A | DSPA : XAF 60000000 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.3.2 | By June 2026, at least 10 qualified teachers will be recruited and deployed to target schools in WWF priority landscapes | Number of qualified teachers recruited and deployed to target schools | [5 empty] | DSPA (2024) : 0 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 3 Ngotto : N/A | DSPA : 6 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.3.3 | By the end of each school cycle, school fees and essential learning-related costs will be fully covered for at least 50 Ba’Aka and other vulnerable children in WWF-supported landscapes | Number of Ba’Aka and other vulnerable children receiving full education support | [5 empty] | DSPA (2024) : 1603 Ngotto : N/A | DSPA : 1693 Ngotto : N/A | DSPA : 1750 Ngotto : N/A | DSPA : 1800 Ngotto : N/A | DSPA : 1900 Ngotto : N/A | DSPA : 2000 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.3.4 | By December 2029, at least 10 target schools in WWF priority areas will receive comprehensive teaching and learning materials, including textbooks, stationery, and classroom supplies. | Number of schools receiving comprehensive sets of teaching and learning materials | [5 empty] | DSPA (2025) : 20 Ngotto : N/A | DSPA : 25 Ngotto : N/A | DSPA : 25 Ngotto : N/A | DSPA : 25 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.3.5 | By December 2030, five annual awareness campaigns will have been conducted in Ba’Aka communities to promote school enrollment | Number of school enrollment awareness campaigns conducted annually | [5 empty] | DSPA (2025) : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA : 3 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA |  | Updated
[8 empty] | Number of Ba’Aka community members reached through campaigns | [5 empty] | DSPA (2025) : 2400 Ngotto : N/A | DSPA : 2500 Ngotto : N/A | DSPA : 2800 Ngotto : N/A | DSPA : 3000 Ngotto : N/A | DSPA : 3500 Ngotto : N/A | DSPA : 4000 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.3.6 | By June 2028, environmental education modules will have been developed and officially integrated into the school curriculum in Yobé-Sangha, Nola, and Salo areas | Number of environmental education modules developed and approved | [5 empty] | DSPA (2025) : 0 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA |  | Updated
Status of curriculum integration evidenced by the modules approved and used
[6 empty] | 3.1.3.7 | By December 2026, at least two exchange visits will have been organized for APDS community representatives to share best practices in education and conservation engagement across WWF-supported regions | Number of exchange visits conducted for APDS community representatives | [5 empty] | DSPA (2025) : 1 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA |  | Updated
[8 empty] | Number of APDS representatives participating in exchange visits | [5 empty] | DSPA (2025) : 2 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.3.8 | By June 2028, at least 30 Nature Clubs will have been established and actively running in target schools or communities | Number of Nature Clubs established in target schools or communities | [5 empty] | DSPA (2025) : 3 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA : 25 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA |  | Updated
[8 empty] | Number of environmental activities conducted by Nature Clubs annually | [5 empty] | DSPA (2025) : 4 Ngotto : N/A | DSPA : 4 Ngotto : N/A | DSPA : 4 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.4 | By 2030, targeted IPLC gain at least a 10% increase in household income from WWF-supported activities compared to the 2025 baseline
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.4.1 | By June2026, a comprehensive baseline assessment of existing income-generating initiatives will be completed in all target communities within target areas | Number of target communities with completed baseline assessments | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.4.2 | By December 2026, a digital and community-based monitoring system will have been established and fully operational to track progress and impact of income-generating initiatives in at least 10 target communities. | Community based digital monitoring system available as evidenced by data outputs | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated
[8 empty] | Number of target communities using the digital monitoring system | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 2 Ngotto : 4 | DSPA : 8 Ngotto : 6 | DSPA : 10 Ngotto : 10 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.4.3 | By December 2026, at least 300 vulnerable households and 20 functional community groups will have been identified and validated for support within the target communities | # of beneficiary households identified for support | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 220 Ngotto : 0 | DSPA : 320 Ngotto : 100 | DSPA : 400 Ngotto : 200 | DSPA : 450 Ngotto : 250 | DSPA : 500 Ngotto : 300 | DSPA & Ngotto |  | Updated
[8 empty] | # of functional community groups identified for support | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : 0 | DSPA : 11 Ngotto : 0 | DSPA : 15 Ngotto : 5 | DSPA : 20 Ngotto : 10 | DSPA : 22 Ngotto : 12 | DSPA : 25 Ngotto : 15 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.4.4 | By June 2030, all identified households and community groups will have received essential inputs, technical training, and veterinary supplies | # of household benefiting | [5 empty] | DSPA (2025) : 1000 Ngotto (2025) : 0 | DSPA : 2000 Ngotto : 0 | DSPA : 3000 Ngotto : 0 | DSPA : 3000 Ngotto : 1000 | DSPA : 3000 Ngotto : 2000 | DSPA : 4000 Ngotto : 3000 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.4.5 | By December 2030, at least 200 individuals (50% women and youth) will have been trained in vocational skills such as tailoring, carpentry, soap-making, mototaxi mechanics, hospitality, and electrical work | # of IPLC women trained in vocational skills | [5 empty] | DSPA (2024) : 10 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA : 40 Ngotto : N/A | DSPA : 50 Ngotto : N/A | DSPA |  | Updated
[8 empty] | # of IPLC men trained in vocational skills | [5 empty] | DSPA (2024) : 10 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA : 40 Ngotto : N/A | DSPA : 60 Ngotto : N/A | DSPA : 80 Ngotto : N/A | DSPA : 100 Ngotto : N/A | DSPA |  | Updated
[8 empty] | # of IPLC youth trained in vocational skills | [5 empty] | DSPA (2024) : 10 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA : 30 Ngotto : N/A | DSPA : 40 Ngotto : N/A | DSPA : 50 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.4.6 | By March 2026, a market assessment report will be completed analyzing demand, pricing, and value chains for non-timber forest products (NTFPs) and bushmeat in local and regional markets | Evidence of a market assessment report | [5 empty] | DSPA (2024) : 0 Ngotto (2025) : 0 | DSPA : 1 Ngotto : 0 | DSPA : 0 Ngotto : 0 | DSPA : 0 Ngotto : 1 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 1 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.4.7 | By December 2026, key components of the ZCC (Zone Cynégétique à Usage Contrôlé) management plan will be implemented, including community patrols, zoning, and sustainable hunting practices in collaboration with local authorities | Number of community patrols conducted per quarter in the ZCC | Tracks the frequency and consistency of community-led patrols within the ZCC. |  |  |  |  | DSPA : 48100 (2025) | DSAP: 48100 | DSPA : 48100 | DSPA : 48100 | DSPA : 48100 | DSPA : 48100 | DSPA |  | Updated
[8 empty] | Percentage of hunting activities in ZCC compliant with sustainable hunting guidelines | Proportion of recorded hunting activities that adhere to established quotas, seasons, and species restrictions. |  |  |  |  | DSPA : TBD | DSPA : 50% | DSPA : 55% | DSPA : 60% | DSPA : 70 | DSPA : 75% | DSPA |  | Updated
[6 empty] | 3.1.4.8 | By December 2027, an inclusive agricultural strategy promoting agroforestry, cocoa, and Gnetum cultivation among others will have been developed and piloted in at least five target communities | Number of inclusive agricultural strategy documents developed and validated | Measures the completion and formal approval of the strategy document that integrates agroforestry, cocoa, Gnetum, and other crops. |  |  |  |  | National (2025) : 0 | 0 | 1 | 0 | 0 | 2 | National |  | Updated
[8 empty] | Number of target communities piloting the inclusive agricultural strategy | Tracks the number of communities where the strategy has been implemented on a pilot basis. |  |  |  |  | DSPA (2024) : 0 Ngotto (2025) : 0 | DSPA : 0 Ngotto : 0 | DSPA : 1 Ngotto : 0 | DSPA : 2 Ngotto : 1 | DSPA : 3 Ngotto : 2 | DSPA : 3 Ngotto : 2 | DSPA & Ngotto |  | Updated
[6 empty] | 3.1.4.9 | By December 2026, small-scale livestock farming (goats, poultry, pigs) will have been introduced and supported in at least 150 households through training, starter kits, and veterinary follow-up | Number of households receiving livestock starter kits and training | Tracks how many households have been equipped with animals (goats, poultry, pigs), basic inputs, and training to begin small-scale livestock farming. |  |  |  |  | DSPA (2024) : 0 Ngotto (2025) : N/A | DSPA : 30 Ngotto : N/A | DSPA : 50 Ngotto : N/A | DSPA : 80 Ngotto : N/A | DSPA : 120 Ngotto : N/A | DSPA : 150 Ngotto : N/A | DSPA |  | Updated
[8 empty] | Percentage of supported households receiving at least one veterinary follow-up visit within six months | Assesses the extent of veterinary support provided to ensure animal health and sustainability of the initiative. |  |  |  |  | DSPA (2024) : 0 Ngotto (2025) : N/A | DSPA : 100% Ngotto : N/A | DSPA : 100% Ngotto : N/A | DSPA : 100% Ngotto : N/A | DSPA : 100% Ngotto : N/A | DSPA : 100% Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.5 | By 2030, the number of targeted IPLC communities in WWF-supported landscapes having access to materials of good life has increased by at least 50% relative to the 2025 baseline
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.5.1 | By December 2027, essential medical equipment and small supplies will have been procured and delivered to the secondary hospital | Number of essential medical equipment and supply items procured and delivered | Tracks the total quantity of distinct equipment and supply items successfully delivered to the hospital. |  |  |  |  | DSPA (2025) : 2 Ngotto (2025) : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA |  | Updated | Baseline is more than targets
[8 empty] | # of patients treated in different health entities (hospital, FOSA, mobile clinic, private entities) (ref: gender, age class, ethnicity) | [5 empty] | DSPA (2025) : 2207 Ngotto (2025) : N/A | DSPA : 2500 Ngotto : N/A | DSPA : 2750 Ngotto : N/A | DSPA : 3000 Ngotto : N/A | DSPA : 3000 Ngotto : N/A | DSPA : 3000 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.5.2 | By December 2027, at least 30 COGES (Helath Committee) members will be trained in health governance, planning, and accountability to enhance community participation in health service management | # of COGES members trained on health governance, planning, and accountability | [5 empty] | DSPA (2025) : 0 Ngotto (2025) : N/A | DSPA : 0 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA : 15 Ngotto : N/A | DSPA : 20 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.5.3 | By December 2028, a monitoring system will have been established and operational for at least 10 satellite health facilities (FOSA) in DSPA | Number of FOSA with functional monitoring systems established | Counts the number of satellite health facilities where the monitoring system (tools, processes, and personnel) has been set up and is operational. |  |  |  |  | DSPA (2025) : 0 Ngotto (2025) : N/A | DSPA : 0 Ngotto : N/A | DSPA : 2 Ngotto : N/A | DSPA : 5 Ngotto : N/A | DSPA : 7 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.5.4 | By December 2028, at least 90% of BaAka newborns delivered in supported health facilities will have received birth certificates through collaboration with municipal civil registration services | Percentage of BaAka newborns delivered in supported health facilities who receive birth certificates | Measures the proportion of BaAka newborns who are officially registered and issued birth certificates through collaboration with municipal civil registration services. |  |  |  |  | DSPA (2023) :123 Ngotto : N/A | DSPA : 150 Ngotto : N/A | DSPA : 200 Ngotto : N/A | DSPA : 200 Ngotto : N/A | DSPA : 250 Ngotto : N/A | DSPA : 800 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.5.5 | By June 2026, at least one BaAka staff member will be recruited and integrated into each WWF-supported health facility to improve cultural sensitivity and trust in healthcare delivery | *# of Ba'aka staff recruited and trained in the health programme | [5 empty] | DSPA (2025) : 0 Ngotto : N/A |  |  | DSPA : 1 Ngotto : N/A |  | DSPA : 1 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.5.6 | By December 2029, at least four outreach health campaigns and two rounds of national vaccination drives will have been supported and implemented in BaAka communities | Number of outreach health campaigns conducted in BaAka communities | Number of outreach health campaigns conducted in BaAka communities |  |  |  |  | DSPA (2024) : 0 Ngotto : N/A | DSPA : 3 Ngotto : N/A | DSPA : 6 Ngotto : N/A | DSPA : 9 Ngotto : N/A | DSPA : 12 Ngotto : N/A | DSPA : 15 Ngotto : N/A | DSPA |  | Updated
[8 empty] | Number of national vaccination drive rounds supported and implemented in BaAka communities | Tracks the number of vaccination rounds that were successfully carried out with support in BaAka areas. |  |  |  |  | DSPA (2024) : 0 Ngotto : N/A | DSPA : 0 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 1 Ngotto : N/A | DSPA : 3 Ngotto : N/A |  |  | Updated
[6 empty] | 3.1.5.7 | By December 2028, medical consultation fees and mobile clinic services will have been covered for at least 1,000 BaAka individuals across all WWF-supported areas | Number of BaAka individuals who received free medical consultations or mobile clinic services | Counts the unique individuals who accessed services without paying fees, either at fixed health facilities or through mobile clinics. |  |  |  |  | DSPA (2025) : 403 Ngotto : N/A | DSPA : 500 Ngotto : N/A | DSPA : 600 Ngotto : N/A | DSPA : 750 Ngotto : N/A | DSPA : 850 Ngotto : N/A | DSPA : 1000 Ngotto : N/A | DSPA |  | Updated
[8 empty] | Number of mobile clinic visits conducted in WWF-supported areas | Tracks the number of mobile clinic deployments to BaAka communities within the supported zones. |  |  |  |  | DSPA (2025) : 6 Ngotto : N/A | DSPA : 6 Ngotto : N/A | DSPA : 7 Ngotto : N/A | DSPA : 7 Ngotto : N/A | DSPA : 8 Ngotto : N/A | DSPA : 10 Ngotto : N/A | DSPA |  | Updated
[6 empty] | 3.1.6 | By 2030, the annual revenues generated by ecotourism activities contribute at least 10% of the DSPA operating budget and 10% to support socio-economic development of IPLCs
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.6.1 | By December 2027, foundational infrastructure and governance frameworks for sustainable tourism will have been established in the target areas | Number of sustainable tourism governance frameworks developed and endorsed | Tracks the creation and formal approval of policies, guidelines, or institutional arrangements that support sustainable tourism. |  |  |  |  | DSPA (2024) : 0 Ngotto: N/A |  | DSPA : 1 Ngotto : N/A |  |  | DSPA : 1 Ngotto : N/A | Ngotto |  | Updated
[6 empty] | 3.1.6.2 | By December 2028, Doli Lodge’s profitability will be increased by at least 20% through improved financial management, staff training, and enhanced guest services | Percentage increase in net profit margin of Doli Lodge | Measures the change in profitability by comparing net profit margins before and after interventions. | [10 empty] | DSPA |  | Updated
[6 empty] | 3.1.6.3 | By December 2026, a digital marketing and reservation platform will have been launched and operational to improve online visibility and bookings for tourism services in the target area | Evidence of a digital platform launched and fully operational | Confirms the platform (website or app) is live, functional, and accessible to users, with core features such as service listings, booking functionality, and contact information. |  |  |  |  | DSPA (2024) : 0 Ngotto: N/A |  |  | DSPA : 1 Ngotto : N/A |  | DSPA : 1 Ngotto : N/A | Ngotto |  | Updated
[6 empty] | 3.1.6.4 | By December 2028, at least five community-based tourism initiatives will have been established and supported, with local communities trained and actively participating in guiding, hospitality, and cultural experiences. | Number of community-based tourism initiatives established and supported | Counts the total number of distinct tourism initiatives (e.g., eco-guiding, homestays, cultural performances) that have been formally launched with community involvement. |  |  |  |  | DSPA (2024) : 0 Ngotto: N/A | DSPA : 1 Ngotto: N/A | DSPA : 2 Ngotto: N/A | DSPA : 3 Ngotto: N/A | DSPA : 4 Ngotto: N/A | DSPA : 5 Ngotto: N/A | DSPA |  | Updated
[8 empty] | Number of community members trained and actively participating in tourism services | Tracks individuals from local communities who have received training and are engaged in guiding, hospitality, or cultural experience delivery. |  |  |  |  | DSPA (2024) : 0 Ngotto: N/A | DSPA : 50 Ngotto: N/A | DSPA : 100 Ngotto: N/A | DSPA : 150 Ngotto: N/A | DSPA : 200 Ngotto: N/A | DSPA : 300 Ngotto: N/A | DSPA |  | Updated
[6 empty] | 3.1.7 | By 2030, at least one new or revised policies or decisions promoting the rights and interests of IPLC enacted with with WWF support
| Human Well Being |  |  |  | Please write your output here >>>> Add more rows if needed | 3.1.7.1 | By December 2028, at least three CSO networks or coordination platforms will have been revitalized and actively functioning in WWF intervention landscapes in CAR | # of CSO networks revitalized |  |  |  | -2024 |  | National (2024) : 1 | National : 1 | National : 2 | National : 2 | National : 3 | National : 3 | National |  | Updated
[8 empty] | # of MoU with CSO network | [5 empty] | National (2024) : 0 | National : 0 | National : 1 | National : 2 | National : 3 | National : 3 | National |  | Updated
[6 empty] | 3.1.7.2 | By December 2029, at least 50 CSO representatives are trained in advocacy, organizational management, and lobbying | Number of CSO representatives trained in advocacy, organizational management, and lobbying | [5 empty] | National (2024) : 0 | National : 0 | National : 0 | National : 25 | National : 25 | National : 50 | National |  | Updated
[8 empty] | Number of training sessions conducted on advocacy, organizational management, and lobbying | [5 empty] | National (2024) : 0 | National : 0 | National : 0 | National : 1 | National : 1 | National : 2 | National |  | Updated
[6 empty] | 3.1.7.3 | By June 2030, at least 10 functional women’s associations will have received technical and financial support to implement or scale up local initiatives in conservation, livelihoods, or community development | Number of women’s associations receiving technical and financial support | [5 empty] | National (2025) : 0 | National : 0 | National : 0 | National : 5 | National : 5 | National : 10 | National |  | Updated
[8 empty] | Number of local initiatives implemented or scaled up by supported women’s associations | [5 empty] | National (2025) : 0 | National : 0 | National : 0 | National : 5 | National : 5 | National : 10 | National |  | Updated
[6 empty] | 3.1.7.4 | By December 2029, CSOs from WWF-supported landscapes will participate in at least five local or national policy or planning forums related to environmental governance and community rights | # of CSOs participating in local and national initiatives with WWF support | [5 empty] | National (2025) : 0 | 2 | 4 | 6 | 8 | 10 | National |  | Updated
[6 empty] | 3.1.7.5 | By December 2030, at least five collaborative initiatives with Civil Society Organizations (CSOs) will have been developed and implemented in priority regions to promote the sustainable management and protection of natural resources | Number of collaborative initiatives with CSOs developed and implemented | Counts the total number of joint projects or programs launched with CSOs that focus on sustainable natural resource management and protection. |  |  |  |  | National (2025) : 0 | 1 | 2 | 3 | 4 | 5 | National |  | Updated
[8 empty] | # of projects implemented jointly with CSOs | [5 empty] | National (2025) : 0 | 0 | 0 | 1 | 1 | 1 | National |  | Updated
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Pierre Kafando we need to complete the risk assessment and the risk register. I am available to support
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduce to 75%
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Pierre Kafando , @Bruce DEGUENE most of the Output indicators still do not have baseline and targets. For the few that have, they are not well formatted to know which is which. I would suggest you put it as in the outcome which is excellently done.

## Programme Implementation Plan
| Output number | Output Statement | FY26 Cost | FY27 Cost | FY28 Cost | FY29 Cost | FY30 Cost | Total Output Cost + Management fee | Current Project (CPM Project #) | Target Funding Source
READ Me First |  | Please list all the outputs identified under the Factors & Outcome tab as well as the M&E plan. During the annual planning and budgeting process, the Programme will have opportunities to further refine and detail the activities and costs. The initial costing of the programme outputs can be estimated, which will be used to estimate the cost of total OSP implementation and the development of the financial plan. Please make sure to include activities related to M&E, ESSF and other risk mitigation, etc. "Please indicate the type of activities: - Programmatic - Innovation (ideation & prototyping & scale up) - M&E and Research - Risk mitigation/management (including ESSF) | [6 empty] | If the activity is already funded, please indicate the relevant CPM number(s). | If there is a funding gap and have prospective funding sources, please indicate the source.
| 2.2.1.1 | By December 2028, at least 500 hectares of cocoa, coffee and food crops are cultivated by smallholder farmers in designated non-HCV areas | 66145.5118 | 0 | 0 | 29519.5319 | 0 | 107623.1741
| 2.2.1.2 | By june 2027, a strategy for planting coffee, cocoa and food crops outside High Conservation Values is developed. | 165365.2087 | 0 | 0 | 0 | 0 | 186035.8597
| 2.2.1.3 | By June 2028, at least 500 smallholder farmers have completed a certified training program on sustainable agriculture practices | 0 | 152799.5907 | 157586.1299 | 147594.8011 | 154996.5969 | 689599.2584
| 2.2.1.4 | By December 2027, 300 households in the target communities have adopted vegetable farming, evidenced by the establishment of home gardens or small plots | 0 | 458398.7722 | 472760.295 | 442784.4032 | 464990.7436 | 2068800.9908
| 2.2.2.1 | By December 2026, at least 300 farmers in the target communities are trained and equipped with deforestation-free agricultural best practices, with 80% receiving starter kits (e.g., agroforestry seedlings, composting tools), and demonstration plots established in each community to support adoption. | 66145.5118 | 114599.693 | 118190.5501 | 110696.339 | 116246.9713 | 591613.9485
| 2.2.2.2 | By June 2027, three agricultural partnership models (e.g., contract farming, cooperative marketing, public-private partnerships) are piloted with at least 300 farmers, and one model scaled to an additional 300 farmers | 66145.5118 | 229200.3388 | 236380.1475 | 221392.678 | 154996.5969 | 1021629.6822
| 2.2.2.3 | By September 2027, value chain support interventions (e.g., infrastructure, market access, processing facilities) are implemented in at least 5 areas | 66145.5118 | 229200.3388 | 236380.1475 | 147594.8011 | 154996.5969 | 938607.0707
| 2.2.3 .1 | By 2029, at least three community forests / OECMs are created and the simple management plans developed and implemented | 55121.4186 | 114599.693 | 118190.5501 | 110696.339 | 116246.9713 | 579211.8437
| 2.2.3 .2_1 | By December 2027, a comprehensive set of context-specific forest management best practices is developed, validated with stakeholders, and distributed to all supported community forests. | 33073.2323 | 45839.8772 | 47276.6011 | 44278.3451 | 46499.1696 | 244088.1285
| 2.2.3 .2_2 | By December 2026, community forest managers and governance bodies receive targeted training and ongoing technical support on implementing best practices in forest management. | 33073.2323 | 45839.8772 | 47276.6011 | 44278.3451 | 46499.1696 | 244088.1285
| 2.2.3.3 | By December 2026, at least two non-timber forest product (NTFP) value chain are developed in partnership with Indigenous Peoples and Local Communities (IPLC) | 66145.5118 | 152799.5907 | 157586.1299 | 147594.8011 | 154996.5969 | 764012.9592
| 2.2.3.4 | By December 2028, at least 10 NTFP-based enterprises in IPLC areas are supported and strengthened through capacity building, access to markets, and financial services | 0 | 0 | 0 | 0 | 0
| 2.2.3 .5 | By June 2027, sustainable production systems for Gnetum africanum are established and promoted in at least 5 IPLC communities | 0 | 305600.1342 | 315173.2124 | 295189.6022 | 309994.1466 | 1379201.7323
| 2.2.3.6 | By December 2026, the beekeeping value chain is promoted and strengthened in at least 10 IPLC communities through training, provision of equipment, and market linkages | 0 | 0 | 0 | 0 | 0
| 2.2.4.1 | By December 2030, forest and landscape restoration pilots are implemented in 5 degraded sites, covering at least 2,000 hectares, with scaling strategies developed and documented. | 330729.4646 | 381999.9296 | 393966.2774 | 368987.4791 | 387492.4451 | 2096072.5451
| 2.2.4.2 | By June 2030, 10 community forest management groups are supported with restoration plans, tools, and training, and at least 1000 hectares will be under active restoration. | 55121.4186 | 76399.7954 | 78793.0649 | 73796.9242 | 77498.2985 | 406810.6893
| 2.2.4.3 | By August 2030, 100,000 seedlings of caterpillar-host tree species are raised and planted across 20 community-managed sites | 55121.4186 | 152799.5907 | 157586.1299 | 147594.8011 | 154996.5969 | 751610.8544
| 2.2.5.1 | By December 2028, at least 5 forestry companies receive training and technical support on sustainable logging practices | 118747.8999 | 186084.3301 | 192025.5837 | 179959.1987 | 189103.5464 | 974160.6287
| 2.2.5.2 | By December 2029, simplified forest management plans are developed and validated for 5 community forests, with local committees trained on implementation. | 339234.5272 | 231924.2073 | 121111.6347 | 113542.1575 | 119354.7919 | 1040813.2335
| 2.2.5.3 | By March 2030, ecosystem service valuation tools are applied in 5 districts, and results integrated into local development plans and livelihood strategies. | 52601.4354 | 48564.6985 | 50197.6857 | 47123.2109 | 34106.9494 | 261668.2273
| 2.2.5.4 | By June 2030, monitoring protocols and patrol systems are established in 5 logging concessions to protect intact forest landscapes | 41577.3422 | 40923.7662 | 42318.5698 | 39744.2806 | 26357.4054 | 214786.5347
| 2.2.5.5 | By December 2027, at least 50 government staff are trained on forest law enforcement, monitoring, and reporting systems | 118747.8999 | 117324.5143 | 121111.6347 | 150439.6669 | 158104.4175 | 748944.15
| 2.2.5.6 | By December 2028, 10 civil society organizations are trained and equipped for independent forest monitoring | 1110936.2936 | 766723.7276 | 790855.5448 | 740819.8239 | 778092.7108 | 4710856.6133
| 3.1.1.1 | By December 2026, Local Development Plans are implemented in 20 IPLC communities with at least 70% community participation in planning and monitoring processes | 18959.4205 | 13664.121 | 93450.8882 | 88074.6063 | 93090.7545 | 345644.7644
| 3.1.1.2 | By June 2026, community-based conflict management and resolution mechanisms are operational in 15 target communities | 18959.4205 | 36585.0124 | 38295.1712 | 36416.3783 | 38842.0409 | 190235.2761
| 3.1.1.3 | By December2026, a functional grievance and escalation system for human rights and GBV is established in all intervention areas | 18959.4205 | 28945.0328 | 30416.0552 | 29036.4954 | 31092.4968 | 155755.6883
| 3.1.1.4 | By December 2025, standardized data monitoring systems are established and operational iin 10 partner institutions | 18959.4205 | 13664.121 | 14657.8233 | 14276.7294 | 15592.4561 | 86794.3691
| 3.1.1.5 | By December 2026, at least 10 human rights awareness campaigns are conducted across intervention areas | 29984.4664 | 21305.0533 | 22535.9865 | 21656.6124 | 23342.9528 | 133678.2054
| 3.1.1.6 | By June 2026, a comprehensive GBV action plan is developed and implemented in all target communities | 52032.6528 | 36585.0124 | 38295.1712 | 36416.3783 | 31092.4968 | 218724.4254
| 3.1.2.1 | By December 2026, at least 10 conservation awareness and education campaigns are conducted annually in IP&LC communities | 15974.5027 | 11329.921 | 11963.4896 | 11477.5949 | 12348.3944 | 70980.6404
| 3.1.2.2 | By December 2027, participatory decision-making frameworks are established and operational in at least 10 conservation sites | 31408.8048 | 22026.2735 | 22995.2047 | 21808.0972 | 23198.1371 | 136616.0819
| 3.1.2.3 | By March 2026, at least 10 culturally appropriate communication tools (e.g., visual aids, local language materials, storytelling formats) are developed and used in all target IP&LC communities | 15974.5027 | 11329.921 | 11963.4896 | 11477.5949 | 12348.3944 | 70980.6404
| 3.1.2.4 | By December 2026, co-management structures involving community representatives are established in two protected areas | 9359.6657 | 6746.3144 | 7236.9728 | 7049.284 | 7699.0491 | 42852.6967
| 3.1.2.5 | By June 2027, at least 5 livelihood improvement initiatives (e.g., eco-tourism, sustainable harvesting, agroforestry) targetting 1000 households are implemented in target communities | 64481.0843 | 44946.2121 | 46632.5525 | 43948.6988 | 46447.722 | 277263.3034
| 3.1.2.6 | By March 2026, functional and accessible feedback and grievance mechanisms are established in all target landscapes | 42432.8979 | 29666.253 | 30874.3206 | 29187.9802 | 30948.6339 | 183498.8463
| 3.1.2.7 | By December 2026, traditional ecological knowledge from IP&LCs is documented and integrated into conservation strategies | 9359.6657 | 6746.3144 | 7236.9728 | 7049.284 | 7699.0491 | 42852.6967
| 3.1.3.1 | By December 2026, at least one Memorandum of Understanding (MoU) will be signed and operationalized between WWF and key education stakeholders to secure sustainable school funding mechanisms | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.3.2 | By June 2026, at least 10 qualified teachers will be recruited and deployed to target schools in WWF priority landscapes | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.3.3 | By the end of each school cycle, school fees and essential learning-related costs will be fully covered for at least 50 Ba’Aka and other vulnerable children in WWF-supported landscapes | 20661.0046 | 14891.2433 | 15972.5972 | 15560.0631 | 16992.0233 | 94586.548
| 3.1.3.4 | By December 2029, at least 10 target schools in WWF priority areas will receive comprehensive teaching and learning materials, including textbooks, stationery, and classroom supplies. | 160639.6446 | 115778.2259 | 124182.2986 | 120959.1972 | 132108.0986 | 735375.8979
| 3.1.3.5 | By December 2030, five annual awareness campaigns will have been conducted in Ba’Aka communities to promote school enrollment | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.3.6 | By June 2028, environmental education modules will have been developed and officially integrated into the school curriculum in Yobé-Sangha, Nola, and Salo | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.3.7 | By December 2026, at least two exchange visits will have been organized for APDS community representatives to share best practices in education and conservation engagement across WWF-supported regions | 1417.6692 | 1022.2843 | 1094.6922 | 1067.0629 | 1166.1473 | 6488.8378
| 3.1.3.8 | By June 2028, at least 5 Nature Clubs will have been established and actively running in target schools or communities | 4094.8537 | 2950.6194 | 3165.9374 | 3083.0495 | 3368.8699 | 18746.2461
| 3.1.4.1 | By June2026, a comprehensive baseline assessment of existing income-generating initiatives will be completed in all target communities within target areas | 22048.1864 | 15279.9591 | 15758.2319 | 14758.8132 | 15499.0881 | 93762.3134
| 3.1.4.2 | By December 2026, a digital and community-based monitoring system will have been established and fully operational to track progress and impact of income-generating initiatives in at least 10 target communities. | 33073.2323 | 22919.9386 | 23638.3006 | 22138.6962 | 23249.5848 | 140647.2215
| 3.1.4.3 | By December 2025, at least 300 vulnerable households and 20 functional community groups will have been identified and validated for support within the target communities | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.4.4 | By June 2030, all identified households and community groups will have received essential inputs, technical training, and veterinary supplies | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.4.5 | By December 2030, at least 200 individuals (50% women and youth) will have been trained in vocational skills such as tailoring, carpentry, soap-making, mototaxi mechanics, hospitality, and electrical work | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.4.6 | By March 2026, a market assessment report will be completed analyzing demand, pricing, and value chains for non-timber forest products (NTFPs) and bushmeat in local and regional markets | 33073.2323 | 22919.9386 | 23638.3006 | 22138.6962 | 23249.5848 | 140647.2215
| 3.1.4.7 | By December 2026, key components of the ZCC (Zone Cynégétique à Usage Contrôlé) management plan will be implemented, including community patrols, zoning, and sustainable hunting practices in collaboration with local authorities | 94494.1327 | 21829.0574 | 23412.5024 | 27410.1772 | 24355.7098 | 215439.2771
| 3.1.4.8 | By December 2027, an inclusive agricultural strategy promoting agroforestry, cocoa, and Gnetum cultivation among others will have been developed and piloted in at least five target communities | 35833.3047 | 64048.5428 | 40962.8283 | 310724.8941 | 29571.9323 | 541284.1899
| 3.1.4.9 | By December 2026, small-scale livestock farming (goats, poultry, pigs) will have been introduced and supported in at least 150 households through training, starter kits, and veterinary follow-up | 5258.1428 | 3793.7896 | 4071.9881 | 3970.0455 | 4339.7065 | 24112.8815
| 3.1.5.1 | By December 2027, essential medical equipment and small supplies will have been procured and delivered to the secondary hospital | 3412.6957 | 2459.961 | 2638.1224 | 2569.5255 | 2806.7564 | 15622.9436
| 3.1.5.2 | By December 2027, at least 30 COGES (Helath Committee) members will be trained in health governance, planning, and accountability to enhance community participation in health service management | 341.079 | 245.8056 | 262.9548 | 256.2856 | 280.104 | 1559.5076
| 3.1.5.3 | By December 2028, a monitoring system will have been established and operational for at least 10 satellite health facilities (FOSA) | 341.079 | 245.8056 | 262.9548 | 256.2856 | 280.104 | 1559.5076
| 3.1.5.4 | By December 2028, at least 90% of BaAka newborns delivered in supported health facilities will have received birth certificates through collaboration with municipal civil registration services | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.5.5 | By June 2026, at least one BaAka staff member will be recruited and integrated into each WWF-supported health facility to improve cultural sensitivity and trust in healthcare delivery | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.5.6 | By December 2029, at least four outreach health campaigns and two rounds of national vaccination drives will have been supported and implemented in BaAka communities | 17063.4784 | 12298.8522 | 13191.5646 | 12849.5329 | 14032.8294 | 78115.7896
| 3.1.5.7 | By December 2028, medical consultation fees and mobile clinic services will have been covered for at least 1,000 BaAka individuals across all WWF-supported areas | 113757.4756 | 81989.4898 | 87941.2235 | 85659.4239 | 93552.8309 | 520762.9991
| 3.1.6.1 | By December 2027, foundational infrastructure and governance frameworks for sustainable tourism will have been established in the target areas | 22183.4747 | 16001.1792 | 17178.7593 | 16747.1705 | 18306.7972 | 101719.5536
| 3.1.6.2 | By December 2028, Doli Lodge’s profitability will be increased by at least 20% through improved financial management, staff training, and enhanced guest services | 20476.1741 | 0 | 0 | 0 | 0 | 23035.6959
| 3.1.6.3 | By December 2026, a digital marketing and reservation platform will have been launched and operational to improve online visibility and bookings for tourism services in the target area | 40379.7547 | 29127.9579 | 31269.7055 | 134831.9671 | 37548.2272 | 307302.3138
| 3.1.6.4 | By December 2028, at least five community-based tourism initiatives will have been established and supported, with local communities trained and actively participating in guiding, hospitality, and cultural experiences. | 0 | 0 | 0 | 0 | 0 | 0
| 3.1.7.1 | By December 2028, at least three CSO networks or coordination platforms will have been revitalized and actively functioning in WWF intervention landscapes in CAR | 53547.5009 | 7639.9795 | 7880.0687 | 7379.883 | 7750.4968 | 94722.67
| 3.1.7.2 | By December 2029, at least 50 CSO representatives are trained in advocacy, organizational management, and lobbying | 15749.6573 | 34271.7725 | 35813.2973 | 33998.3377 | 36201.0603 | 175538.3907
| 3.1.7.3 | By June 2030, at least 10 functional women’s associations will have received technical and financial support to implement or scale up local initiatives in conservation, livelihoods, or community development | 42523.4077 | 30341.7419 | 40107.2725 | 38477.1435 | 33652.495 | 208239.8182
| 3.1.7.4 | By December 2029, CSOs from WWF-supported landscapes will participate in at least five local or national policy or planning forums related to environmental governance and community rights | 29921.5859 | 20955.3997 | 21846.2066 | 20688.6339 | 21975.7785 | 129811.0552
| 3.1.7.5 | By December 2030, at least five collaborative initiatives with Civil Society Organizations (CSOs) will have been developed and implemented in priority regions to promote the sustainable management and protection of natural resources | 488221.2737 | 492452.3685 | 509284.3324 | 478361.4223 | 348848.573 | 2606813.9661
Total Annual Cost + Management Fee |  |  | 5001228.3552 | 5792204.1828 | 5934256.5688 | 6002313.2665 | 5522006.3599 | 28252008.7332

## Learning Questions
Learning Questions
READ Me First | Please articulate specific learning questions that your program will regularly reflect on for the learning priority. Max 100 words.
Example | - To what extent are the program's activities effective in achieving the planned results? - What worked and what didn’t? - Were there any unintended consequences? (positive or negative/ internal or external) - Were there any emergent results? (more than the planned results)

## Result Chain
| Conservation Focus of the Programme | Priority Threats / Other Factors | Result ID | Program Outcomes | Relevant Geographic Scope | Relevant Thematic Scope | Annual Result - Year 1 | Output (Annual Result) - Year 2 | Output (Annual Result) - Year 3 | Output (Annual Result) - Year 4 | Output (Annual Result) - Year 5 | Key Assumptions & Risks | Sustainability & Exit Plan
READ Me First | Please copy the list of Conservation Focus from the previous tab. | For each Conservation Focus please list the priority threat (or other factors). Please use one line for each threat/factor. If a single threats affect more than one Conservation Focus, please list all the relevant conservation focus/focal interest under the column B. CMP Direct Threat Classification is available here - https://docs.google.com/spreadsheets/d/1rJSNz1LG_KOqoudVFglodx47HZ9LR-M6iVlRYMvn9Wk/edit#gid=310830663 Please ensure that priority threats/other factors are subset of those selected under the OSP. You may define further in detail. |  | Please Describe the desired reduction of threats (or changes to the identified factors). Please make sure the statement is SMART. | Please indicate the relevant Geographic Scope for each Outcome statement. Ensure to use one of the Geographic scope identified in the Scope tab of OSP Design Template. | Please indicate the relevant Thematic Scope for each Goal statement. Ensure to use one of the Thematic scope identified in the Scope tab of OSP Design Template. | Please define measurable Programme Annual Results which are milestones in achieving Programme outcomes. Therefore Programme Outcome must be embedded in the Programme Outputs. Outputs must represent tangible deliverables, within our area of control, that are critical to achieving the Programme Outcomes, in line with the Theory of Change. If there are areas of innovation and/or research, please make sure to include those outputs and activities as well. See the guidance on the approach to the Programme and Project Planning |  |  |  |  | Please identify the key assumptions that underpin the logical sequences linking Outputs, and Outcomes, and to one or more Goals Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment. WWF policies do not require risk assessment at program level but at Office level and at Project level. However each Program team is encouraged to perform Program Risk assessment. Use the Office risk register template in such case. | Please describe how your program aims to ensure the sustainability of the program outcome and an eventual exit by WWF. See Guidance by PPMS Step - Element 2.3
Example | Coral Reef Marine priority species | Overfishing / unsustainable fisheries |  | By 2030, fisheries management plans are in place (implemented & monitored) in 80% of coastal fisheries in ABC coastal communities. | Beta seascape | Ocean | Awareness of unsustainable fisheries increased in ABC coastal communities by 50% | Technical capacity of 10 fisheries communities built on fisheries management plan | 5 fisheries communities developed fisheries management plan | 4 fisheries communities developed fisheries management plan |  | Local communities can improve (or at least maintain) the economic state after the fisheries management plan. | Creation of alternative sustainable income to ensure that the sustainable implementation of the fisheries management plan. Also, inclusion of CSO (and their capacity building) in the project implementation to enable the eventual exit of WWF and transition of responsibility to the local CSO.
[5 empty] | Beta seascape | Ocean | Baseline assessment of current fisheries practices conducted for 10 fisheries in ABC coastal community |  |  | 50% of coastal fisheries are implementing and monitoring fisheries management plan | 80% of coastal fisheries are implementing and monitoring fisheries management plan
Note on I1: @hwilliams@wwfint.org, also here we should be align the language _Assigned to hwilliams@wwfint.org_ -Philip Kahuho