## OM Results Chain
| OSP Goal Statment | Priorities Outcomes | Relevant Geographic Scope | Relevant Thematic Scope | Output (Annual Result) - Year 1 | Output (Annual Result) - Year 2 | Output (Annual Result) - Year 3 | Output (Annual Result) - Year 4 | Output (Annual Result) - Year 5 | Key Assumptions | Sustainability & Exit Plan
READ Me First | Copy the goal stament from the OSP template. | For each OSP goal, describe the specific, measurable outcomes you aim to achieve. Outcomes should focus on addressing gaps in organizational management identified through capacity assessments. Ensure these are SMART (Specific, Measurable, Achievable, Relevant, Time-bound). |  |  | For each year, define measurable annual outputs that serve as milestones in achieving the program outcomes. Outputs should be tangible, within the organization’s control, and directly linked to program outcomes. |  |  |  |  | Identify the assumptions that underpin the success of activities, outputs, and outcomes. These are external factors or conditions necessary for success that may be beyond the office’s direct control. | Outline how the outcomes will be sustained beyond the period of active intervention. Focus on building internal capacities, integrating new systems, and ensuring the office can independently manage its operations.
| By FY30, WWF CAR fosters a high-performing, inclusive, and values-driven organizational culture through effective recruitment, onboarding, and performance systems that enhance staff well-being, engagement, and long-term retention. | By 2030 WWF CARCO has a robust performance and talent management strategy that fosters a high-performance culture, enhances the capabilities of employees, including national staff, and supports career development and alignment with organizational goals. |  | People & Culture | 70% of training needs are identified and appropriate training programs are offered as a priority to national staff. Deploy a skills development framework and ensure alignment of development plans for staff in critical functions. | 80% of employees supervised by a mentor or manager to promote greater commitment and consolidate know-how | 95% of assessments carried out according to clear, standardized criteria | 85% of employees express a sense of belonging and well-being | 75% of employees have access to job upgrades or promotions | The organization has enhanced initiatives to maximize on staff satisfaction, staff development and provides attractive work conditions, and carrer opportunities. | WWF has an evolving, qualified and motivated national staff to guarantee the sustainability of its activities.
|  | By 2028, provide a working environment that fosters commitment and creativity |  | People & Culture | 90% of energy analyses completed and validated | 100% of offices equipped with solar systems and back-up batteries | 85% of equipment maintained and operational | 80% of financing secured through specialized partners | 90% of energy data collected and analyzed | Ensuring a gradual and measurable energy transition and improving working conditions | % of sites (Bangui, Bayanga & Ngotto sites) having access to green and sustainable energy
|  | By 2030, WWF CARCO ensure an efficient, connected work environment that fosters team satisfaction and performance |  | People & Culture | 90% of employees with stable Internet access | 85% of employees trained in digital tools and best practices | 90% of IT equipment available and operational | 85% of services digitized and integrated into a monitoring dashboard | 90% des retours d’enquête pris en compte et intégrés aux améliorations | To ensure an efficient and connected work environment that fosters team satisfaction and performance. | Improving communication and operational efficiency
| By FY30, WWF CAR achieves operational excellence and strategic focus by aligning its structure and systems with organizational priorities, strengthening logistical and digital capacity, and embedding accountability and adaptive management frameworks. | By 2030, WWF CARCO built a solid governance (complete at least 100%) to facilitate program coordination and development |  | Organisational managment | 80% of transferable best practices are identified with the aim of developing Ngotto under the DSPA model. | 85% of data collected and analyzed to provide a better understanding of local issues and reduce implementation risks | 75% of stakeholders involved in the project,Strengthening local collaboration and increasing community support | 75% of stakeholders involved in the project | 85% of the actions carried out are evaluated and recommendations are made for the following phases | aligned to the conservation strategy. | Expanding conservation areas and improving WWF ecological results
|  | Modernizing infrastructures and optimizing team performance |  | Organisational managment | 90% of positions and functions formalized in an organization chart and operational framework | 85% of regular follow-up and coordination meetings | 80% of decisions validated via consultative processes to reinforce stakeholder trust and involvement | 75% of Program activities are reported for better visibility via modern communication tools | 85% of programs integrated into a strategic dashboard | Ensure program coordination, facilitate reporting and capitalize on experience | Greater organizational fluidity and optimized decision-making
|  | By 2030, WWF CARCO has achieved at least 100% compliance with the required policies and procedures for quality deliverying the implementation of its 2026-2030 OSP |  | Organisational managment | 80% of offices equipped with modern, functional tools | 75% of offices equipped with high-performance digital systems | 85% of employees trained in new practices and technologies | 70% of teams involved in innovative initiatives | 80% of monitoring indicators defined and used regularly | Proactive adaptation of strategies and continuous improvement | Increased productivity and operational efficiency
|  | By 2030, strengthen ethical governance and the implementation of WWF values |  | Organisational managment | 85% of donor commitments established and monitored | 80% of donors integrated into a database and tracked regularly | 85% of financing requests processed with a structured plan | 80% of financing obtained from several partners and reduce dependence on a single lessor and secure projects | 90% of financing monitored by performance indicators | Increased funding and stronger partnerships | Increasing funding and stabilizing resources
| By FY30, WWF CAR has cultivated a dynamic leadership pipeline by embedding continuous leadership development through training, coaching, and strategic exposure that enhances strategic thinking and decision-making. | By 2030, WWF CARCO has achieved at least 100% compliance with the required policies and procedures for quality deliverying the implementation of its 2026-2030 OSP |  | Leadership | 100% of activities compliant with established standards | 100% of internal audits validated without non-conformity or fraud | 90% of employees trained in compliance and integrity rules | 100% of alerts effectively handled and followed up Quickly identify risks and improve prevention | 100% of audit recommendations implemented | Ensure full compliance and efficient management of WWF CARCO operations | Enhanced credibility and organizational effectiveness to ensure effective and compliant implementation of the 2026-2030 action plan

## OSP M&E Plan
OM M&E plan | # | Results Name | Results Statemet | Indicator | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Assumptions | Means of Verification | Data Collection Tool | Frequency of Measurement | Risks | Location | Responsible
OM Goals | 1 | High-performing, inclusive, and values-driven organizational culture | By FY30, WWF CAR fosters a high-performing, inclusive, and values-driven organizational culture through effective recruitment, onboarding, and performance systems that enhance staff well-being, engagement, and long-term retention. | % score staff satisfactry survey; FTE 36 | 36% | 45% | 55% | 65% | 75% | 90% | The organization has enhanced initiatives to maximize on staff satisfaction, staff development and provides attractive work conditions, and carrer opportunities. | • Feedback from performance reviews or staff appraisal systems. • Salary and benefits benchmarking report | • Structured staff satisfaction surveys, Exit interview forms, Focus group discussions with various departments • HR metrics dashboards (tracking promotions, attrition, participation in training) • Suggestion boxes or anonymous feedback platforms | Staff survey every 2 years | • Misalignment between staff needs and initiatives • Limited funding for development programs • High staff turnover due to external opportunities • Favoritism or unequal access to development programs |  | P&C Manager
|  |  |  | % score in staff PDJ (Staff performance); FTE 36 | 100% | 100% | 100% | 100% | 100% | 100% | The organization has enhanced initiatives to maximize on staff satisfaction, staff development and provides attractive work conditions, and carrer opportunities. | • HR policy documents outlining development initiatives and benefits. • Internal reports on staff training sessions, promotions, and satisfaction surveys. | Staff PDJ and 360 | Staff survey every 2 years | • Misalignment between staff needs and initiatives • Limited funding for development programs • High staff turnover due to external opportunities • Favoritism or unequal access to development programs |  | P&C Manager
|  |  |  | % in staff turnover rate. | 16% | 8% | 6% | 5% | 5% | 3% | The organization has enhanced initiatives to maximize on staff satisfaction, staff development and provides attractive work conditions, and carrer opportunities. | • Retention and turnover statistics over time. | HR database | Staff survey every 2 years | • Misalignment between staff needs and initiatives • Limited funding for development programs • High staff turnover due to external opportunities • Favoritism or unequal access to development programs |  | P&C Manager
| 2 | Operational excellence | By FY30, WWF CAR achieves operational excellence and strategic focus by aligning its structure and systems with organizational priorities, strengthening logistical and digital capacity, and embedding accountability and adaptive management frameworks. | *Number of non compliance act (Fraud and corruption complance breach of contract); | 1 100% | 0 100% | 0 100% | 0 100% | 0 100% | 0 100% | To ensure an efficient and connected work environment that fosters team satisfaction and performance. | • Annual governance audits and compliance reviews • Organizational capacity assessment reports • Board and committee meeting minutes showing active decision-making • WWF internal evaluations against governance benchmarks • Quarterly performance reports linked to OSP targets • Risk and accountability registers (updated regularly) | • Governance effectiveness survey tools (staff, leadership, partners) • Process mapping and compliance checklists • Structured interviews with management, field staff, and community stakeholders | Each year | Without robust monitoring, non-compliance or inefficiencies may go unnoticed. Frequent leadership changes can disrupt continuity and the maturity of governance systems. Deep-rooted habits or structures might slow down efforts to update or standardize governance processes. |  | Country Director/PC Manager
| 3 | Dynamic leadership | By FY30, WWF CAR has cultivated a dynamic leadership pipeline by embedding continuous leadership development through training, coaching, and strategic exposure that enhances strategic thinking and decision-making. | % of mid/senior staff rated “strategically competent” in annual performance reviews - (Voir avec Ghislain pou rle nombres de mid/Senior staff 2024) | 30% | 45% | 60% | 70% | 80% | 90% | Leadership training is consistently funded and integrated into HR processes; staff actively engage in coaching, mentoring, and retreats | Annual performance appraisal reports; HR leadership development dashboard; feedback from coaching/training evaluations | Standardized evaluation rubric for strategic competency; 360° feedback surveys; leadership training tracking sheets | Annualy | • Low uptake of programs due to workload or lack of clarity • Inconsistent evaluation standards across departments |  | Country Director:PC Manager:Projetcs Managers
OM Priorities Outcomes | 1.1 | Performance and talent management strategy developed | By 2030 WWF CARCO has a robust performance and talent management strategy that fosters a high-performance culture, enhances the capabilities of employees, including national staff, and supports career development and alignment with organizational goals. | % of staff achieving performance rating “Meets or Exceeds Expectations” | 30% | 45% | 55% | 65% | 80% | 90% | high-performance culture through regular appraisals and performance management systems and enhancing career development and inclusivity, especially for national staff | • Performance appraisal reports showing distribution of ratings over time • Talent review meeting summaries and feedback • Annual staff survey results measuring perception of support and career growth | • Structured performance review forms linked to KPIs • HRIS systems for capturing training, promotions, retention metrics • Focus group discussions with national staff and department leads | Each year | Inconsistent performance appraisal processes Limited career development for national staff High-performing staff attrition Resistance to adopting a performance culture Gaps in training follow-through | ------------------------- | Country Director/PC Manager/Projects Managers
|  |  |  | % of staff with individualized career development plans in use | 30% | 45% | 60% | 75% | 85% | 90% |  | • HR dashboards tracking career development plans, promotions, training sessions • Individual Development Plans (PDJs) for staff • Training completion reports and internal skills audits | • Staff development plan templates and tracking systems | Each year
| 1.2 | Working environment that fosters commitment and creativity | By 2028, provide a working environment that fosters commitment and creativity | % of staff with active Career Development Plans | 50% | 50% | 60% | 70% | 80% | 100% | performance by 2030, ensuring inclusivity and institutional growth. | • HRIS reports on PDJs and performance evaluations • Annual talent review summaries • Training and promotion statistics by department • Internal HR dashboards and analytics • Staff survey results on development opportunities and recognition | • Standardized performance appraisal forms • Career Development Plan templates • Staff feedback surveys (including national staff perspectives) • Focus group discussions and exit interviews | Each year | • Unequal access to development opportunities • Inconsistent performance review standards • Low staff engagement in career planning • Resistance to change |  | P&C Manager/Projects Manager
| 1.3 | Satisfaction and performance Improved | By 2030, WWF CARCO ensure an efficient, connected work environment that fosters team satisfaction and performance | % of staff reporting satisfaction with collaboration tools/systems | 35% | 60% | 70% | 85% | 90% | 95% | capture both the quality of the work environment and the results it enables. | • Annual staff satisfaction and workplace connectivity surveys • Internal performance review summaries • Minutes from cross-functional coordination meetings • Feedback from team retreats or integration workshops | • Feedback forms from organizational events or integration activities | Each year | • Low adoption of digital collaboration tools • Inconsistent cross-team communication • Technical infrastructure limitations • Staff burnout or disengagement from over-connectedness |  | Country Director/PC Manager/Manager
| 2.1 | Governance to facilitate program coordination and developmed | By 2030, WWF CARCO built a solid governance (complete at least 100%) to facilitate program coordination and development | % of programs with clearly defined governance roles | 60% | 70% | 90% | 90% | 100% | 100% | Stakeholders commit to defining governance frameworks | Annual Program Reports Governance Assessments |  |  | Political instability or conflic
| 2.2 | Modernized infrastructure | Modernizing infrastructures and optimizing team performance | Score of staff satisfaction | FTE 36 Equivalent to 100% |  | 55% |  | 70% | 70% | Increase cost recovery | Staff survey reports Annual Reports | Survey, Individual feedbacks | Every 2 years | Demotivation, leak of engagement | DSPA, Ngotto,National | Country Director/P&C/
| 2.3 | Compliance to policies and procedures improved | By 2030, WWF CARCO has achieved at least 100% compliance with the required policies and procedures for quality deliverying the implementation of its 2026-2030 OSP | % of complince with the required policies and policies | FTE 36 Equivalent to 100% |  |  |  |  | 100% | Need to recruit an internal controler staff Increase capacities of financial staff Promote SODA implementation | Audit Reports Finance Repports | Internal and International audit | Every year | Lost of Credibilty, Lost of donors confidence,lost of funds |  | Country Director/P&C/Finance Coordinator
| 3.1 | Implementation of ethical governance of WWF values stren | By 2030, strengthen ethical governance and the implementation of WWF values | % of staff trained annually on WWF Code of Ethics and Values | 100% | 100% | 100% | 100% | 100% | 100% | All staff are trained | Induction repports, training reports,annual reports | attendance sheet, End of contract interview form |  |  |  | Country Director/P&C/
OM Priorities Outputs | 1.1.1 |  | By 2030, achieve a 90% staff retention rate and ensure 100% of staff meet or exceed their annual performance (PDJ) targets through a standardized career development framework. | % Staff Retention and Performance Achievement | 70% (36 /36) | 75% | 80% | 85% | 90% | 90% |  |  | Canopy HRIS | Annual | -------------------------
| 1.1.2 |  | By 2030, establish a QA Secretariat that audits 100% of active projects annually, ensuring a minimum 85% compliance score with WWF’s effectiveness and impact standards. | % Project Compliance with Effectiveness Standards | 100% | 100% | 100% | 100% | 100% | 100% |  |  | Panda Impact System | Annual
| 1.1.3 |  | By 2030, implement a continuous feedback loop where 100% of staff receive quarterly ethics training and 95% of staff report a high "culture of integrity" in annual surveys. | % Staff with High Integrity Perception & Training. FTE 36 | 50% | 60% | 70% | 80% | 90% | 100% |  |  | Staff perceptions survey | Quarterly
| 1.2.1 |  | By 2030, transition 100% of WWF CAR field offices to reliable, modern, and renewable energy sources (Solar/Hybrid), reducing carbon footprint by 50%. | % Field Offices on Renewable Energy (Solar/Hybrid) | 100% | 100% | 100% | 100% | 100% | 100% |  |  | Datasheet | Bi-annual | -------------------------
| 1.2.2 |  | By 2030, ensure 100% of offices have stable internet (>10Mbps) and a Logistics Support System that resolves 90% of field requests within 48 hours. | % Offices with Stable Internet & Rapid Logistics | 50% | 80% | 90% | 100% | 100% | 100% |  |  | IT system logs | Monthly | -------------------------
| 1.3.1 |  | By 2030, deploy an Automated Document Management System (ADMS) that secures 100% of critical project and legal records with real-time cloud backup. | % Critical Records Secured in ADMS | 50% | 60% | 80% | 90% | 100% | 100% |  |  | Datasheet | Quarterly
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Bruce DEGUENE , could you check with P&C what is the staff turn over rate? CC @Pierre Kafando
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Musa Cheruiyot , No Outputs

## Implementation Plan
| Output number | Output Statement | FY26 Cost | FY27 Cost | FY28 Cost | FY29 Cost | FY30 Cost | Total | Current Project (CPM Project #) | Target Funding Source
READ Me First. OD Costs should include: A. Human Resources and Capacity Development B. Organisational Governance and Compliance C. Operational Efficiency and Process Improvement D. Technology and Systems E. Stakeholder Engagement and Communications |  | Please list all the outputs identified under the Factors & Outcome tab as well as the M&E plan. During the annual planning and budgeting process, the Programme will have opportunities to further refine and detail the activities and costs. The initial costing of the priority outputs can be estimated, which will be used to estimate the cost of total OSP implementation and the development of the financial plan. Please make sure to include outputs related to M&E, ESSF and other risk mitigation, etc. | [5 empty] | This column will be automatically sum up the total. | If the activity is already funded, please indicate the relevant CPM number(s). | If there is a funding gap and have prospective funding sources, please indicate the source.
| 1.1.1 | Improved staff retention and performance | 3000 | 3000 | 3000 | 3000 | 3000 | 15000
| 1.1.2 | Access to affordable, reliable, sustainable and modern energy for all field offices | 71428 | 71428 | 5000 | 5000 | 5000 | 157856
| 1.1.3 | Fast and stable internet access. Efficient and responsive logistics support | 40000 | 40000 | 40000 | 40000 | 40000 | 200000
| 1.1.4 | Automated document management system ensuring the secure storage ad backup of critical documents | 10000 | 1000 | 1000 | 1000 | 1000 | 14000
| 1.1.5 | Establishmeent of a rigorous quality assurance process to ensure projects and programs meet the highest standards of effectiveness, effeciency and impact; aligning with the OSP | 3000 | 3000 | 3000 | 3000 | 3000 | 15000
| 1.1.6 | Regular training and awareness raising activities and feedback mechanisms to ensure staff ar eengaged and promote a culture of integrity and accountability | 3000 | 3000 | 3000 | 3000 | 3000 | 15000
0
Total |  |  | 130428 | 121428 | 55000 | 55000 | 55000 | 416856