## OM Results Chain
| OSP Goal Statment | Priorities Outcomes | Relevant Geographic Scope | Relevant Thematic Scope | Output (Annual Result) - Year 1 | Output (Annual Result) - Year 2 | Output (Annual Result) - Year 3 | Output (Annual Result) - Year 4 | Output (Annual Result) - Year 5 | Key Assumptions | Sustainability & Exit Plan
READ Me First | Copy the goal stament from the OSP template. | For each OSP goal, describe the specific, measurable outcomes you aim to achieve. Outcomes should focus on addressing gaps in organizational management identified through capacity assessments. Ensure these are SMART (Specific, Measurable, Achievable, Relevant, Time-bound). |  |  | For each year, define measurable annual outputs that serve as milestones in achieving the program outcomes. Outputs should be tangible, within the organization’s control, and directly linked to program outcomes. |  |  |  |  | Identify the assumptions that underpin the success of activities, outputs, and outcomes. These are external factors or conditions necessary for success that may be beyond the office’s direct control. | Outline how the outcomes will be sustained beyond the period of active intervention. Focus on building internal capacities, integrating new systems, and ensuring the office can independently manage its operations.
| By 2030, level of CCO staff performance is maintained at at least 90% and competent and dedicated staff are retained at 95% relative to 2024 baseline. | By 2028, at least 90% of competent and accountable staff of WWF CCO scoring at least 75% in performance evaluation are retained relative to 2024 baseline |  | Operational Excellence | By 2025, local Infrastructure in Yaounde and field offices are upgraded to entreprise-based standard relative to 2023 baseline | By June 2026 CCO is 100% equipped with an efficient electronic filing system for easy retrieval of information | By 2027, green and sustainable energy is 100% installed in Yaounde and field sites offices to solve power outages | By 2028,all staff are at least 90% satisfied annually with information services (reliable internet connectivity, digital dexterity of the staff etc) and logistics support based on survey report
| By 2030, WWF CCO has achieved 100% compliance with the required policies and procedures for quality delivery in the implementation of its 2026-2030 OSP | By 2029, WWF CCO ensures full institutional compliance (100%) with all required internal and external policies, procedures, and quality standards related to the implementation of its 2026–2030 Office Strategic Plan (OSP), thereby enabling consistent, transparent, and high-quality delivery across all programmes and operations. |  | Governance & Leadership | Compliance Framework for OSP 2026–2030 developed, approved, and disseminated across WWF CCO with training provided to 10% of WWF CCO staff by December 2025 Annual compliance audits conducted with corrective actions implemented | Digital compliance tracking system (dashboard) designed, deployed, and updated quarterly | Quarterly management reviews and compliance oversight reports produced and acted upon | Compliance clauses and reporting mechanisms integrated into all partner agreements and monitored annually | Comprehensive documentation system for compliance maintained for all OSP-related projects annually | Adequate staff capacity and leadership commitment to enforce compliance External standards remain stable and achievable; external partners cooperate | Institutionalization of compliance culture, automation of tracking systems, integration into organizational performance reviews Compliance embedded in partner onboarding and contracts, regular refresher training
| By 2030, at least 90% of WWF CCO staff are satisfied at atleast 75% with the governance and leadership system as compared to 2026 baseline | By 2028,the level of implementation of WWF core values and policies by all staff is atleast 90% relative to 2025 baseline |  | Governance & Leadership | By 2028,the level of implementation of WWF core values and policies by all staff is atleast 90% relative to 2025 baseline | All staff trained (including refreshers) on WWF core values, ethics, and code of conduct by June 2026 and annual refreshers done | Quarterly staff compliance assessments integrated into performance reviews on quarterly base Staff recognition program established to reward compliance with WWF values and policies | Biannual internal audits on policy compliance and staff conduct conducted with 100% response rate annually | Leadership and line managers trained to model and reinforce WWF core values in their teams by December 2027 | Staff feel safe to express honest feedback; leadership engages meaningfully with feedback Core values and policies are well communicated and enforced | Institutionalize annual governance feedback loop and leadership response plans Integration into staff onboarding, appraisal system, and leadership KPIs
| By 2030, WWF CCO demonstrates operational excellence by achieving at least 75% of its strategic plan goals | By end 2028, CCO is a viable, trusted and strategic partner for donors, CSOs, IPLC, private sector, government and other conservation and development players to work in synergy in the delivering of its conservation vision relative to 2020 baseline |  | Partnerships for Conservation Delivery | The endorsement of the CCO private sector engagement plan by QAC facilitated | At least 4 new strategic partnership agreements signed with CCO | At least 2 conservation events/fora/discourse co-organise with strategic partners annually | At least one proposal, one position paper, one publication jointly developed and shared with the right audience annually. |  | Stakeholders see added value in partnering with CCO; Political environment remains conducive; Resources are available for engagement activities | Institutionalization of engagement frameworks; Capacity building of CCO staff; Integration of engagement efforts into core strategy and budget
|  | By FY'27, WWF CCO has developed and implemented an integrated science-based country strategy for the conservation of natural resources and the sustainable use of these resources by the local communities/indigenous people in the landscapes where WWF RoC Works |  | People, capacities, Organisational design, and wellbeing (landscapes) | 1. Organisational design completed (org chart, functions and roles) by December 2025 | 2. Key vacancies filled by December 2025 | 3. Improved Organisational culture and enabling environment at CCO for enhanced staff performance and retention by Dec 2026 | 4. Improved health and security conditions (program disaster plans) for CCO staff by June 2026 |  | Stakeholder engagement is effective; adequate scientific data and expertise are available; political environment remains supportive | Institutional capacity-building, stakeholder co-ownership, integration into national policy frameworks
|  | 25% income growth i.e increased to FCFA 7,500,000,000 that is US$ 13,000,000, achieved by CCO from a diversified fundraising base and surplus unrestricted income improved relative to the 2023 baseline |  | Resource Mobilization | 1. Funds through joint proposals with corporate entities increased by 10% by June 2026 and by 20% by Dec 2028 | 2. At least one joint proposal submitted to PSPs after every two years is approved for funding | 3. At least one proposal submitted to Foundations after every two years is approved for funding | 4. At least 4 new donors are committing 200000 US$ per year to CCO | 5. Funds mobilized through the Network have increased by at least 20% by 2025 6. By 2028, mobilize funds closed to 13,000,000 US$ | Fundraising strategy is effectively implemented; donor interest remains strong; CCO has capacity to manage funds | Develop diverse fundraising strategy, build endowment/reserve fund, maintain donor stewardship plan
|  | By 2028 WWF CCO has institutionalized management decision making and communication culture and systems to enable agility and effectiveness in conservation programme delivery relative to 2023 baseline |  | External and Internal Communications | 1. CCO staff awareness and use of the different channels and tools have increased by at least 75% by 2027 | 2. Staff knowledge on use of internal and external communications tools, and clearance procedure enhanced by at least 75% by 2027 | 3. CCO staff effectively receiving information and communication through the internal and external communications channels have increased by at least 75% by 2027 | 5. Staff perception of WWF external communications has improved by at least 75% by 2027 | 6. At least 75% of senior staff members are equipped with Crisis communications and media interview skills | Leadership is committed; systems are adopted organization-wide; training is effective | Embed systems in organizational SOPs, build leadership pipeline, implement feedback and learning loops
|  | By 2028, CCO has, an integrated information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline. |  | Enabling integrated information system | 1.Logistics department is 100% equipped with an interactive tool to facilitate operations by January 24 Internet Connectivity reliable in Yaounde’s Office Digital dexterity of the staff ensured | 2. CCO is 100% equipped with an efficient electronic filing system for easy retrieval of information by June 2026 Local Infrastructure in Yaounde and field offices are upgraded to entreprise-based standard | 3. Staff are at least 90% satisfied with information services based on survey report | 4. Staff are at least 90% satisfied with logistics support based on survey report | 5. Green and sustainable energy is 100% installed in Yaounde and field sites offices to solve power outages. | Digital literacy is sufficient across teams; systems are interoperable; staff are willing to share knowledge | Provide user training, ensure system relevance and usability, foster knowledge-sharing culture
|  | By 2028, CCO has, an integrated monitoring, evaluation, learning, information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline. |  | Monitoring and Evaluation of the OD Plan. | 1. Accountability, credibility, and transparency with both internal/staff, external donors and other accountability bodies/stakeholders enhanced. | 2. Ownership of the work by staff, partners, and stakeholders, and therefore sustainability of the work for the future strengthened. | 3. Improved staff efficiency to support the overall effort to professionalize and institutionalize WWF Cameroon Country processes and work contributing to streamlining processes, and promote social cohesion among staff. | 4. OD support is contributing effectively to achieving the CC0 strategic plan. |  | Sufficient capacity and tools; commitment to learning and adaptation; resources for implementation | Build MELIKM capacity, align with strategic planning cycle, institutionalize learning forums

## OSP M&E Plan original (hidden)
OM M&E plan | # |  | Description | Indicator | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Assumptions | Means of Verification | Data Collection Tool | Frequency of Measurement | Risks | Location | Responsible
OM Priorities Theory of Change
OM Goals | 1 | Operational Excellence Demonstrated | By 2030, WWF CCO demonstrates operational excellence by achieving at least 75% of its strategic plan goals | % of strategic plan objectives fully achieved or on track by 2030 (target: ≥75%) | 0 | Baseline Information on OSP implementation established | At least 25% of strategic plan objectives fully achieved or on track | At least 50% of strategic plan objectives fully achieved or on track | At least 70% of strategic plan objectives fully achieved or on track | At least 75% of strategic plan objectives fully achieved or on track | Strategic plan is well-designed and aligned with capacity and context; leadership and staff are committed to implementation; adequate funding is available | Mid-term and end-term strategic plan evaluations, annual progress reports, scorecards, board meeting minutes | Annual performance reviews, strategic plan tracking tools, KPI dashboards, internal audit reports | Annually | Inadequate resource mobilization, misalignment between operations and strategy, external shocks (e.g., political/economic instability) | National & Landscape levels | DC & PMEL team
| 2 | Satisfied and engaged Staff | By 2030, level of CCO staff performance is maintained at at least 90% and competent and dedicated staff are retained at 95% relative to 2024 baseline. | % score of competent and accountable staff retained | 0 | Baseline information established | At least 80% of competent and accountable staff retained | At least 80% of competent and accountable staff retained | At least 90% of competent and accountable staff retained | At least 95% of competent and accountable staff retained | • Sufficient financial resources are available for staff capacity-building, incentives, and retention programs • Leadership remains committed to staff development • External factors (e.g., political, economic) remain stable | • Annual HR reports • Performance appraisal results • Staff satisfaction surveys • Exit interview reports | • Staff performance evaluation forms • Annual staff satisfaction questionnaires • HR MIS system • Exit interview templates | Annually | • High staff turnover due to external opportunities • Burnout or poor morale due to workload or unmet expectations • Budget constraints reducing investment in staff welfare | National & Landscape levels | CLT
|  |  |  | % score in performance evaluation |  |  | At least 75% average staff score in performance evaluation | At least 80% average staff score in performance evaluation | At least 90% average staff score in performance evaluation | At least 95% average staff score in performance evaluation | [6 empty] | CLT & PMs/TLs
|  |  |  | Score (%) of landscape staff satisfaction on wellbeing conditions. |  |  | At least 75% of sites-based staff are satisfied with the wellbeing conditions | At least 80% of sites-based staff are satisfied with the wellbeing conditions | At least 90% of sites-based staff are satisfied with the wellbeing conditions | At least 95% of sites-based staff are satisfied with the wellbeing conditions | [6 empty] | CLT & PMs
| 3 | Full compliance with Policies achieved | By 2030, WWF CCO has achieved 100% compliance with the required policies and procedures for quality delivery in the implementation of its 2026-2030 OSP | % of compliance with procedures and policies | 95% Compliance with procedures and policies | 98% Compliance with procedures and policies | 100% Compliance with procedures and policies | 100% Compliance with procedures and policies | 100% Compliance with procedures and policies | 100% Compliance with procedures and policies | Adequate staff capacity and leadership commitment to enforce compliance | Annual compliance audit reports, M&E system outputs, external audit findings | Audit tools, compliance dashboard | Annually | Inadequate funding, staff turnover, resistance to accountability mechanisms | National & Landscape levels | CLT & PMs/TLs
|  |  |  | % Score of level of implementation and efficiency of the governance structure in place Structured system put in place Number of documents shared | 80% implementation and efficiency of the governance structure in place | 85% implementation and efficiency of the governance structure in place | 90% implementation and efficiency of the governance structure in place | 95% implementation and efficiency of the governance structure in place | 98% implementation and efficiency of the governance structure in place | 100% implementation and efficiency of the governance structure in place |  |  |  | Annually
| 4 |  | By 2030, at least 90% of WWF CCO staff are satisfied at atleast 50% with the governance and leadership system as compared to 2026 baseline | % of staff satisfied with the governance and leadership system | 0 | Baseline information collected | At least 75% of staff are satisfied with the governance and leadership system | At least 80% of staff are satisfied with the governance and leadership system | At least 85% of staff are satisfied with the governance and leadership system | At least 95% of staff are satisfied with the governance and leadership system | Staff feel safe to express honest feedback; leadership engages meaningfully with feedback Core values and policies are well communicated and enforced | Staff satisfaction reports; survey summaries; leadership action plans | Staff perception survey tool | Annually | Low participation rates; perception of survey ineffectiveness | National & Landscape levels | CLT & PMs/TLs
|  |  |  | % of the governance and leadership system that are marked satisfactory | 0 | Baseline information collected | At least 30% of the governance and leadership system that are marked satisfactory | At least 35% of the governance and leadership system that are marked satisfactory | At least 40% of the governance and leadership system that are marked satisfactory | At least 50% of the governance and leadership system that are marked satisfactory
| 4.1 |  | By 2028,the level of implementation of WWF core values and policies by all staff is atleast 90% relative to 2025 baseline | % adherence to core values based on compliance tracking and disciplinary records | 0 | Baseline information established | At least 75% of CCO staff adherence to core values based on compliance tracking and disciplinary records | At least 80% of CCO staff adherence to core values based on compliance tracking and disciplinary records | At least 90% of CCO staff adherence to core values based on compliance tracking and disciplinary records | At least 90% of CCO staff adherence to core values based on compliance tracking and disciplinary records | Core values and policies are well communicated and enforced | Ethics reports, incident tracking reports, HR disciplinary data | Internal audit checklists; non-compliance log | Annually | Inconsistent enforcement; fear of reporting violations | National & Landscape levels | CLT & PMs/TLs
| 2 |  | By 2029, WWF CCO ensures full institutional compliance (100%) with all required internal and external policies, procedures, and quality standards related to the implementation of its 2026–2030 Office Strategic Plan (OSP), thereby enabling consistent, transparent, and high-quality delivery across all programmes and operations. | % of organizational units meeting compliance requirements in annual reviews | 0 | Baseline information established | At least 90% of organizational units are meeting compliance requirements in annual reviews | At least 95% of organizational units are meeting compliance requirements in annual reviews | 100% of organizational units are meeting compliance requirements in annual reviews | 100% of organizational units are meeting compliance requirements in annual reviews | External standards remain stable and achievable; external partners cooperate | Internal quality assurance reports, partner evaluation reports, independent verification | Annual partner reviews, internal QA assessments | Annually | Regulatory changes, low partner compliance, operational disruptions | National & Landscape levels | CLT & PMs/TLs
OM Priorities outcomes | 3 | Fundraising | By end 2028, CCO is a viable, trusted and strategic partner for donors, CSOs, IPLC, private sector, government and other conservation and development players to work in synergy in delivering its conservation vision relative to 2020 baseline | Increase in number of partnerships, events co-hosted, joint publications, and endorsement of plans compared to 2020 baseline | 0 | Baseline information established | At least 1 new credible & functional partnership | At least 2 new credible & functional partnership | At least 3 new credible & functional partnership | At least 4 new credible & functional partnership | Stakeholders see added value in partnering with CCO; Political environment remains conducive; Resources are available for engagement activities | Partnership agreements, Event reports, Published materials, Endorsement letters | Stakeholder surveys, Partnership tracking matrix, Event reports, Document review | Annually | Political instability; Shifts in donor or partner priorities; Internal capacity constraints | National & Landscape levels | CLT & PMs/TLs
| 4 |  | By FY'27, WWF CCO has developed and implemented an integrated science-based country strategy for the conservation of natural resources and the sustainable use of these resources by the local communities/indigenous people in the landscapes where CCO works | Country Strategy developed, approved and operationalized in priority landscapes | WWF CCO OSP developed and validated | At least 25% of strategic plan objectives being implemented | At least 50% of strategic plan objectives being implemented | At least 60% of strategic plan objectives being implemented | At least 75% of strategic plan objectives being implemented | Strategic plan is well-designed and aligned with capacity and context; leadership and staff are committed to implementation; adequate funding is available | Stakeholder engagement is effective; adequate scientific data and expertise are available; political environment remains supportive | Approved strategy document, implementation plans, evidence of activities in landscapes | Strategy documents, implementation reports, landscape assessments, stakeholder feedback tools | Annually | Political interference, limited stakeholder buy-in, lack of resources | National & Landscape levels | CLT & PMs/TLs
| 5 | Fundraising | 50% income growth i.e increased to FCFA 10,000,000,000 (US$ 20,000,000) achieved by CCO from a diversified fundraising base and surplus unrestricted income improved relative to the 2023 baseline | Total annual income and proportion of unrestricted income from diversified sources (public, private, foundations, etc.) |  | Baseline information established |  |  |  |  | Fundraising strategy is effectively implemented; donor interest remains strong; CCO has capacity to manage funds | Audited financial statements, donor portfolio reports | Financial records, donor reports, fundraising dashboards |  | Economic downturns, changing donor priorities, over-reliance on few sources | National & Landscape levels | DN & CLT
| 1.1 |  | By 2028 WWF CCO has institutionalized management decision-making and communication culture and systems to enable agility and effectiveness in conservation programme delivery relative to 2023 baseline | Evidence of functional decision-making and internal communication systems; improved decision turnaround times | 0 | Baseline information established | At least 1 decision made to improve on internal and effectiveness in OSP delivery | At least 1 new decision made to improve on internal and effectiveness in OSP delivery | At least 1 new decision made to improve on internal and effectiveness in OSP delivery | At least 1 new decision made to improve on internal and effectiveness in OSP delivery | Leadership is committed; systems are adopted organization-wide; training is effective | Performance reviews, dashboards, survey results, decision logs | Internal audits, HR reports, staff surveys, management meeting minutes | Annually | Resistance to change, staff turnover, weak IT infrastructure | National & Landscape levels | DN & CLT
| 1.2 |  | By 2028, CCO has an integrated information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline | % of teams reporting improved access to and use of timely data/information; frequency of use of the knowledge system | 0 | Baseline information for IT satisfaction survey established | At least 75% staff satisfaction survey score on IT | At least 85% staff satisfaction survey score on IT | At least 90% staff satisfaction survey score on IT | At least 95% staff satisfaction survey score on IT | Digital literacy is sufficient across teams; systems are interoperable; staff are willing to share knowledge | Reports from KM system, case studies, increased documentation and learning products | KM system usage data, user feedback surveys, IT system reports | Annually | Low usage by staff, poor data quality, siloed departments | Annually | IT & PMs/TLs
| 1.3 |  | By 2028, CCO has an integrated monitoring, evaluation, learning, information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline | % of programmes using integrated MELIKM data for decision-making and reporting; quality of data collected and used | At least 60% of technical and operations delivery of CCO strategy achieved | At least 70% of technical and operations delivery of CCO strategy achieved | At least 75% of technical and operations delivery of CCO strategy achieved | At least 80% of technical and operations delivery of CCO strategy achieved | At least 85% of technical and operations delivery of CCO strategy achieved | 90% of technical and operations delivery of CCO strategy achieved | Sufficient capacity and tools; commitment to learning and adaptation; resources for implementation | Evaluation reports, adaptive management decisions, improved outcomes in program reports | MEL reports, learning sessions, data dashboards, system analytics | Annually | Inadequate data use, fragmented systems, MEL fatigue | Annually | PMEL & PMs/TLs
| 4.1 |  | By 2028,the level of implementation of WWF core values and policies by all staff is atleast 90% relative to 2025 baseline
OM Priorities Outputs | 1.1 |  | All staff trained (including refreshers) on WWF core values, ethics, and code of conduct by June 2026 and annual refreshers done | % of staff completing initial and refresher trainings annually | [6 empty] | Training resources and schedules are available; staff are motivated to attend | Training attendance records; post-training assessments | E-learning modules, attendance registers, feedback forms |  | Competing priorities; limited trainer availability
| 1.2 |  | Quarterly staff compliance assessments integrated into performance reviews on quarterly basis | % of performance reviews including compliance criteria | [6 empty] | HR systems are able to accommodate quarterly evaluations | Performance appraisal reports; staff scorecards | HRIS; appraisal templates |  | Staff fatigue from frequent reviews; inconsistent manager enforcement
| 1.3 |  | Staff recognition program established to reward compliance with WWF values and policies | # of staff recognized annually for exemplary value-based behavior | [6 empty] | Recognition is seen as meaningful; nominations are fairly evaluated | Award records; internal communication showcasing awardees | Nomination forms, recognition logs |  | Perceived favoritism; low participation
| 1.4 |  | Biannual internal audits on policy compliance and staff conduct conducted with 100% response rate annually | % of audit recommendations addressed and compliance gaps closed | [6 empty] | Audit teams have capacity and independence; findings are acted upon | Audit reports; management response matrices | Audit checklists, F&C tracking sheets |  | Audit fatigue; poor management follow-through
| 1.5 |  | Leadership and line managers trained to model and reinforce WWF core values in their teams by December 2027 | % of managers trained and applying values-based leadership practices | [6 empty] | Leadership is committed to role-modelling; training is tailored and practical | Training reports; 360° feedback; team climate assessments | Training rosters, pre/post assessments |  | Resistance to change; unclear expectations
| 2 |  | By 2029, WWF CCO ensures full institutional compliance (100%) with all required internal and external policies, procedures, and quality standards related to the implementation of its 2026–2030 Office Strategic Plan (OSP), thereby enabling consistent, transparent, and high-quality delivery across all programmes and operations.
| 2.1 |  | Compliance Framework for OSP 2026–2030 developed, approved, and disseminated across WWF CCO with training provided to 10% of WWF CCO staff by December 2025 | Approved framework available; % of staff trained | [6 empty] | Leadership support; availability of technical expertise | Approved compliance framework; training attendance records | Training reports; staff feedback forms |  | Delays in approval; limited participation in training
| 2.2 |  | Annual compliance audits conducted with corrective actions implemented | # of audits conducted annually; % of corrective actions implemented | [6 empty] | Audit team capacity; cooperation of departments | Audit reports; corrective action logs; follow-up review reports | Audit checklists; corrective action tracking sheets |  | Low compliance response; audit fatigue
| 2.3 |  | Digital compliance tracking system (dashboard) designed, deployed, and updated quarterly | System developed and used; # of updates per year | [6 empty] | IT infrastructure in place; staff use the system | System logs; usage data; compliance issue resolution reports | System analytics dashboard; user feedback tools |  | Technical glitches; low adoption
| 2.4 |  | Quarterly management reviews and compliance oversight reports produced and acted upon | # of reviews held; % of action items addressed | [6 empty] | Leadership commitment; effective data collection | Meeting minutes; follow-up action trackers; compliance reports | Review templates; action tracking matrices |  | Low participation or follow-through; competing priorities
| 2.5 |  | Compliance clauses and reporting mechanisms integrated into all partner agreements and monitored annually | % of agreements with compliance clauses; # of partner compliance reports submitted | [6 empty] | Procurement/legal teams follow policy; partners accept terms | Signed contracts; partner monitoring reports | Compliance checklist for contracts; partner reporting templates |  | Partner resistance; poor follow-up from WWF teams
| 2.6 |  | Comprehensive documentation system for compliance maintained for all OSP-related projects annually | % of projects with complete and updated compliance documentation | [6 empty] | Staff understand documentation protocols; archiving systems exist | Document repository; M&E reports; project audit files | Documentation templates; file review logs |  | Poor recordkeeping; lack of standardization
| 3 |  | By end 2028, CCO is a viable, trusted and strategic partner for donors, CSOs, IPLC, private sector, government and other conservation and development players to work in synergy in delivering its conservation vision relative to 2020 baseline
| 3.1 |  | The endorsement of the CCO private sector engagement plan by QAC facilitated | Engagement plan endorsed and officially documented by QAC | [6 empty] | QAC is supportive of CCO’s direction and open to collaboration | Official QAC documentation of endorsement | Meeting minutes, correspondence, signed endorsement letter |  | Resistance from QAC; Changes in QAC leadership
| 3.2 |  | At least 4 new strategic partnership agreements signed with CCO | Number of signed partnership MOUs/agreements | [6 empty] | Clear value proposition presented by CCO; Willing partners exist | Signed MOUs; Communications from partners | Partnership tracking database; Document review |  | Competition for partners; Misalignment of interests
| 3.3 |  | At least 2 conservation events/fora/discourse co-organized with strategic partners annually | Number of co-organized events per year | [6 empty] | Partners are willing and able to co-host; Sufficient budget and staff time | Event agendas, Participant lists, Reports | Event calendars, Reports, Invitations |  | Logistical challenges; Lack of interest or capacity from partners
| 3.4 |  | At least one proposal, one position paper, one publication jointly developed and shared with the right audience annually | Number of joint documents developed and disseminated | [6 empty] | Partners have technical capacity and willingness to co-develop content | Published materials, Media coverage, Website analytics | Document repository, Communication records |  | Limited partner capacity or time; Disagreements on content
| 4 |  | By FY'27, WWF CCO has developed and implemented an integrated science-based country strategy for the conservation of natural resources and the sustainable use of these resources by the local communities/indigenous people in the landscapes where WWF CCO works
| 4.1 |  | 1. Organisational design completed (org chart, functions and roles) by December 2025 | Approved organizational structure, finalized organogram, and updated job descriptions in use | [6 empty] | Leadership and staff support change; external consultant (if used) delivers quality input; resources allocated for the process | Final org chart, HR records, Board or SMT approval minutes | HR files, org design documentation, staff feedback survey |  | Resistance to change; delays in approval; scope creep
| 4.2 |  | 2. Key vacancies filled by December 2025 | % of critical positions filled (target: 100%) | [6 empty] | Qualified candidates are available and willing to join; recruitment process is timely and well-resourced | HR recruitment records; Contracts signed; Onboarding reports | Vacancy tracker, interview records, recruitment reports |  | Talent scarcity; competition from other organizations; lengthy recruitment process
| 4.3 |  | 3. Improved organizational culture and enabling environment at CCO for enhanced staff performance and retention by Dec 2026 | Results of staff satisfaction survey (target: ≥75% positive); turnover rate reduced by 30% | [6 empty] | Leadership commitment to culture change; feedback mechanisms in place; HR systems support performance and growth | Staff surveys, retention reports, exit interviews | Employee satisfaction survey, HR MIS reports, performance appraisals |  | Resistance to culture change; weak leadership modelling; insufficient HR capacity
| 4.4 |  | 4. Improved health and security conditions (program disaster plans) for CCO staff by June 2026 | Disaster preparedness plans developed, tested, and implemented; % of staff trained in safety protocols | [6 empty] | Sufficient budget and expertise; collaboration with safety/security experts; staff participation in drills | Disaster response plan document, training reports, audit results | Risk management plans, security incident reports, training attendance sheets |  | Unpredictable crises; low staff engagement in training; inadequate infrastructure
| 5 |  | 50% income growth i.e increased to FCFA 10,000,000,000 (US$ 20,000,000) achieved by CCO from a diversified fundraising base and surplus unrestricted income improved relative to the 2023 baseline
| 5.1 |  | 1. Funds through joint proposals with corporate entities increased by 10% by June 2026 and by 20% by Dec 2028 | % increase in funds from joint proposals with corporate entities | [6 empty] | Assumptions | Means of Verification | Data Collection Tool
| 5.2 |  | 2. At least one joint proposal submitted to PSPs after every two years is approved for funding | Number of approved proposals submitted to Public Sector Partners every two years (target: ≥1) | [6 empty] | Strong partnerships with corporate sector; proposals aligned with shared goals (CSR/sustainability); economic stability | Financial statements, grant agreements | Fundraising database, proposal tracker
| 5.3 |  | 3. At least one proposal submitted to Foundations after every two years is approved for funding | Number of approved foundation proposals every two years (target: ≥1) | [6 empty] | PSPs maintain strong interest in conservation; quality of proposals is high; compliance with donor guidelines | Donor approval letters, contracts, progress reports | Proposal submission and outcome tracker
| 5.4 |  | 4. At least 4 new donors are committing 200,000 US$ per year to CCO | Number of new donors annually committing ≥$200,000 | [6 empty] | Foundations have funding calls aligned with CCO strategy; quality and relevance of proposals are strong | Grant award letters, donor agreements | Foundation proposal tracker, donor database
| 5.5 |  | 5. Funds mobilized through the Network have increased by at least 20% by 2025 | % increase in income from WWF Network sources by 2025 (baseline 2023) | [6 empty] | Effective donor cultivation and stewardship; clear value proposition and trust in CCO’s delivery | Signed donor agreements, financial records | Donor pipeline tracker, income reports
| 5.6 |  | 6. By 2028, mobilize funds close to 20,000,000 US$ | Total cumulative funds raised by 2028 (target: US$ 20M) | [6 empty] | Continued prioritization of CCO by Network offices; CCO delivers on program quality | Network financial reports, joint funding agreements | Network fundraising dashboard, income analysis tool
| 6 |  | By 2028 WWF CCO has institutionalized management decision-making and communication culture and systems to enable agility and effectiveness in conservation programme delivery relative to 2023 baseline
| 6.1 |  | 1. CCO staff awareness and use of the different channels and tools have increased by at least 75% by 2027 | % of staff reporting increased awareness and use of communications tools (email, intranet, newsletter, Teams, etc.) | [6 empty] | Tools are accessible and user-friendly; communications team provides training; leadership encourages use | Staff surveys, internal communication reports | Staff feedback forms, system usage analytics |  | Low digital literacy; tool fatigue; inconsistent rollout
| 6.2 |  | 2. Staff knowledge on use of internal and external communications tools, and clearance procedure enhanced by at least 75% by 2027 | % of staff demonstrating correct use of tools and procedures in practice and feedback | [6 empty] | Communication protocols are well documented; staff are trained and supported | Post-training evaluations, content review logs | Training attendance sheets, knowledge assessments |  | Lack of follow-up support; unclear procedures; staff turnover
| 6.3 |  | 3. CCO staff effectively receiving information and communication through the internal and external communications channels have increased by at least 75% by 2027 | % of staff who feel well-informed through internal channels (newsletters, intranet, email, meetings, etc.) | [6 empty] | Messages are relevant, timely, and accessible; channels are functioning well | Annual staff surveys, feedback sessions | Survey data, internal communications metrics |  | Communication overload; inconsistent messaging
| 6.4 |  | 4. CCO staff are writing and publishing quality reports, articles, position papers, etc. | Number and quality of staff-authored publications produced and shared annually | [6 empty] | Staff have writing skills, time, and institutional support; editorial process is in place | Publication records, editorial reviews, online analytics | Publication repository, web stats, citation tracking |  | Poor writing capacity; lack of editorial support; unclear guidance
| 6.5 |  | 5. Staff perception of WWF external communications has improved by at least 75% by 2027 | % of staff expressing positive perception of WWF’s public messaging and visibility | [6 empty] | External communication aligns with brand values; internal communications promote it effectively | Staff perception surveys, communications audit | Annual perception survey, social media engagement review |  | Disconnection between internal and external messages; external missteps
| 6.6 |  | 6. At least 75% of senior staff members are equipped with crisis communications and media interview skills | % of senior staff trained and confident in crisis response and media engagement | [6 empty] | Senior staff availability and willingness to participate; practical, scenario-based training delivered | Training records, post-training evaluations | Media training sessions, simulation exercises |  | Lack of senior staff buy-in; insufficient follow-up practice
| 7 |  | By 2028, CCO has an integrated information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline
| 7.1 |  | 1. Logistics department is 100% equipped with an interactive tool to facilitate operations by January 2024 | Operational logistics tool fully deployed and used by staff (target: 100%) | [6 empty] | Tool is user-friendly; staff are trained; procurement and IT support available | Tool implementation reports, usage analytics | Deployment checklist, user feedback surveys |  | Resistance to change, technical issues
| 7.2 |  | 2. CCO is 100% equipped with an efficient electronic filing system for easy retrieval of information by June 2026 | All departments using standardized electronic filing system; retrieval time reduced | [6 empty] | Adequate IT infrastructure; staff follow protocols; system maintained | Internal audits, user satisfaction reports | File system audit logs, document access logs |  | Inconsistent use; technical breakdown; poor archiving discipline
| 7.3 |  | 3. Staff are at least 90% satisfied with information services based on survey report | ≥90% of staff report satisfaction in annual survey | [6 empty] | Information needs are well understood; services are responsive; feedback loop in place | Staff satisfaction survey report | Online/physical surveys, focus group discussions |  | Lack of responsiveness from info services; survey bias
| 7.4 |  | 4. Staff are at least 90% satisfied with logistics support based on survey report | ≥90% of staff satisfied with travel, procurement, fleet, and event support services | [6 empty] | Logistics services are timely, responsive, and adequately resourced | Survey reports, service usage records | Annual satisfaction survey, suggestion boxes |  | Delays in procurement; poor communication
| 7.5 |  | 5. Green and sustainable energy is 100% installed in Yaoundé and field offices to solve power outages | % of offices fully powered by solar/renewable systems (target: 100%) | [6 empty] | Technical assessments support feasibility; budget available; local suppliers engaged | Technical installation reports, energy audit | Energy bills, backup power use reports, system maintenance logs |  | Installation delays; poor maintenance; high upfront costs
| 7.6 |  | 6. Internet Connectivity reliable in Yaoundé Office | ≥95% uptime of internet connection measured monthly | [6 empty] | Reliable service provider; backup options available | Network performance logs, IT reports | Internet uptime monitoring software |  | Provider outages; equipment failure
| 7.7 |  | 7. Local Infrastructure in Yaoundé and field offices are upgraded to enterprise-based standard | % of sites meeting infrastructure checklist aligned with enterprise standard (target: 100%) | [6 empty] | Clear standard defined; budget available; renovations implemented in phases | Infrastructure audit report | Facilities checklist, procurement and renovation reports |  | Funding gaps; supply chain delays; remote site challenges
| 7.8 |  | 8. Digital dexterity of the staff ensured | % of staff proficient in using core digital tools and platforms (target: ≥90%) | [6 empty] | Training is prioritized; tools are relevant to job functions; staff willing to learn | Pre/post-training evaluations, IT support tickets | Digital literacy assessment, LMS reports, user support stats |  | Training fatigue; varying skill levels; lack of follow-up
| 8 |  | By 2028, CCO has an integrated monitoring, evaluation, learning, information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline
| 8.1 |  | 1. Accountability, credibility, and transparency with both internal staff, external donors, and other accountability bodies/stakeholders enhanced | Number of internal audits completed, donor compliance reports submitted on time, % of staff and partners reporting increased trust | [6 empty] | Leadership commitment to transparency; adequate systems for reporting and feedback | Internal audit reports, donor reports, stakeholder feedback reports | Annual surveys, audit tools, partner/stakeholder consultations |  | Misalignment between reporting tools and donor/stakeholder expectations; weak internal controls
| 8.2 |  | 2. Ownership of the work by staff, partners, and stakeholders, and therefore sustainability of the work for the future strengthened | % of projects with active partner/stakeholder engagement in design and implementation phases | [6 empty] | Stakeholders are genuinely involved and empowered; staff understand value of co-creation | Project documentation, partnership agreements, feedback forms | Engagement logs, co-creation workshop reports |  | Tokenistic participation; time constraints; weak communication
| 8.3 |  | 3. Improved staff efficiency to support the overall effort to professionalize and institutionalize WWF Cameroon Country Office processes and work, contributing to streamlining processes and promoting social cohesion among staff | % improvement in staff satisfaction, reduced turnaround time for core processes, improved internal communication scores | [6 empty] | Clear roles and responsibilities; process mapping and documentation in place; leadership supports culture of efficiency | Process audit reports, satisfaction surveys, performance reviews | HR data, workflow assessments, internal comms surveys |  | Process fatigue; resistance to change; unclear process owners
| 8.4 |  | 4. OD support is contributing effectively to achieving the CCO strategic plan | % of strategic plan goals positively impacted by OD interventions (target: ≥75%) | [6 empty] | OD initiatives aligned with strategic goals; leadership provides resources and support | Strategic plan progress reports, OD activity reports | Monitoring matrix, strategic KPIs, staff feedback |  | Fragmented OD efforts; weak linkage with strategy implementation
| 8.5 |  | 5. Lessons learned are used to inform decision-making, facilitate improved performance, to track changes, risks, and assumptions, and for adaptive management | % of projects/programs applying learning in subsequent planning and reporting cycles; number of documented learning products | [6 empty] | A learning culture is promoted; systems exist to capture and use lessons | After-action reviews, learning reports, adaptive action plans | Knowledge management tools, MEL reports, learning workshop outputs |  | Lessons not documented or revisited; low staff engagement in learning

## OSP M&E Plan revision1 (hidden)
OM M&E plan | # |  | Description | Indicator | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Assumptions | Means of Verification | Data Collection Tool | Frequency of Measurement | Risks | Location | Responsible
OM Priorities Theory of Change
OM Goals | 1 | Operational Excellence Demonstrated | By 2030, WWF CCO demonstrates operational excellence by achieving at least 75% of its strategic plan goals | % of strategic plan objectives fully achieved or on track by 2030 (target: ≥75%) | 0 | Baseline Information on OSP implementation established | At least 25% of strategic plan objectives fully achieved or on track | At least 50% of strategic plan objectives fully achieved or on track | At least 70% of strategic plan objectives fully achieved or on track | At least 75% of strategic plan objectives fully achieved or on track | Strategic plan is well-designed and aligned with capacity and context; leadership and staff are committed to implementation; adequate funding is available | Mid-term and end-term strategic plan evaluations, annual progress reports, scorecards, board meeting minutes | Annual performance reviews, strategic plan tracking tools, KPI dashboards, internal audit reports | Annually | Inadequate resource mobilization, misalignment between operations and strategy, external shocks (e.g., political/economic instability) | National & Landscape levels | DC & PMEL team
| 2 | Satisfied and engaged Staff | By 2030, level of CCO staff performance is maintained at at least 90% and competent and dedicated staff are retained at 95% relative to 2024 baseline. | % score of competent and accountable staff retained | 0 | Baseline information established | At least 80% of competent and accountable staff retained | At least 80% of competent and accountable staff retained | At least 90% of competent and accountable staff retained | At least 95% of competent and accountable staff retained | • Sufficient financial resources are available for staff capacity-building, incentives, and retention programs • Leadership remains committed to staff development • External factors (e.g., political, economic) remain stable | • Annual HR reports • Performance appraisal results • Staff satisfaction surveys • Exit interview reports | • Staff performance evaluation forms • Annual staff satisfaction questionnaires • HR MIS system • Exit interview templates | Annually | • High staff turnover due to external opportunities • Burnout or poor morale due to workload or unmet expectations • Budget constraints reducing investment in staff welfare | National & Landscape levels | CLT
|  |  |  | % score in performance evaluation |  |  | At least 75% average staff score in performance evaluation | At least 80% average staff score in performance evaluation | At least 90% average staff score in performance evaluation | At least 95% average staff score in performance evaluation | [6 empty] | CLT & PMs/TLs
|  |  |  | Score (%) of landscape staff satisfaction on wellbeing conditions. |  |  | At least 75% of sites-based staff are satisfied with the wellbeing conditions | At least 80% of sites-based staff are satisfied with the wellbeing conditions | At least 90% of sites-based staff are satisfied with the wellbeing conditions | At least 95% of sites-based staff are satisfied with the wellbeing conditions | [6 empty] | CLT & PMs
| 3 | Full compliance with Policies achieved | By 2030, WWF CCO has achieved 100% compliance with the required policies and procedures for quality delivery in the implementation of its 2026-2030 OSP | % of compliance with procedures and policies | 95% Compliance with procedures and policies | 98% Compliance with procedures and policies | 100% Compliance with procedures and policies | 100% Compliance with procedures and policies | 100% Compliance with procedures and policies | 100% Compliance with procedures and policies | Adequate staff capacity and leadership commitment to enforce compliance | Annual compliance audit reports, M&E system outputs, external audit findings | Audit tools, compliance dashboard | Annually | Inadequate funding, staff turnover, resistance to accountability mechanisms | National & Landscape levels | CLT & PMs/TLs
|  |  |  | % Score of level of implementation and efficiency of the governance structure in place Structured system put in place Number of documents shared | 80% implementation and efficiency of the governance structure in place | 85% implementation and efficiency of the governance structure in place | 90% implementation and efficiency of the governance structure in place | 95% implementation and efficiency of the governance structure in place | 98% implementation and efficiency of the governance structure in place | 100% implementation and efficiency of the governance structure in place |  |  |  | Annually
| 4 | This can be intergrated as indicators in 1 | By 2030, at least 90% of WWF CCO staff are satisfied at atleast 50% with the governance and leadership system as compared to 2026 baseline | % of staff satisfied with the governance and leadership system | 0 | Baseline information collected | At least 75% of staff are satisfied with the governance and leadership system | At least 80% of staff are satisfied with the governance and leadership system | At least 85% of staff are satisfied with the governance and leadership system | At least 95% of staff are satisfied with the governance and leadership system | Staff feel safe to express honest feedback; leadership engages meaningfully with feedback Core values and policies are well communicated and enforced | Staff satisfaction reports; survey summaries; leadership action plans | Staff perception survey tool | Annually | Low participation rates; perception of survey ineffectiveness | National & Landscape levels | CLT & PMs/TLs
|  |  |  | % of the governance and leadership system that are marked satisfactory | 0 | Baseline information collected | At least 30% of the governance and leadership system that are marked satisfactory | At least 35% of the governance and leadership system that are marked satisfactory | At least 40% of the governance and leadership system that are marked satisfactory | At least 50% of the governance and leadership system that are marked satisfactory
| 1.1 |  | By 2028 WWF CCO has institutionalized management decision-making and communication culture and systems to enable agility and effectiveness in conservation programme delivery relative to 2023 baseline | Evidence of functional decision-making and internal communication systems; improved decision turnaround times | 0 | Baseline information established | At least 1 decision made to improve on internal and effectiveness in OSP delivery | At least 1 new decision made to improve on internal and effectiveness in OSP delivery | At least 1 new decision made to improve on internal and effectiveness in OSP delivery | At least 1 new decision made to improve on internal and effectiveness in OSP delivery | Leadership is committed; systems are adopted organization-wide; training is effective | Performance reviews, dashboards, survey results, decision logs | Internal audits, HR reports, staff surveys, management meeting minutes | Annually | Resistance to change, staff turnover, weak IT infrastructure | National & Landscape levels | DN & CLT
| 1.2 |  | By 2028, CCO has an integrated information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline By 2028, technical and operational delivery is improved compared to 2023 baseline. | % of teams reporting improved access to and use of timely data/information; frequency of use of the knowledge system | 0 | Baseline information for IT satisfaction survey established | At least 75% staff satisfaction survey score on IT | At least 85% staff satisfaction survey score on IT | At least 90% staff satisfaction survey score on IT | At least 95% staff satisfaction survey score on IT | Digital literacy is sufficient across teams; systems are interoperable; staff are willing to share knowledge | Reports from KM system, case studies, increased documentation and learning products | KM system usage data, user feedback surveys, IT system reports | Annually | Low usage by staff, poor data quality, siloed departments | Annually | IT & PMs/TLs
| 1.3 |  | By 2028, CCO has an integrated monitoring, evaluation, learning, information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline | % of programmes using integrated MELIKM data for decision-making and reporting; quality of data collected and used | At least 60% of technical and operations delivery of CCO strategy achieved | At least 70% of technical and operations delivery of CCO strategy achieved | At least 75% of technical and operations delivery of CCO strategy achieved | At least 80% of technical and operations delivery of CCO strategy achieved | At least 85% of technical and operations delivery of CCO strategy achieved | 90% of technical and operations delivery of CCO strategy achieved | Sufficient capacity and tools; commitment to learning and adaptation; resources for implementation | Evaluation reports, adaptive management decisions, improved outcomes in program reports | MEL reports, learning sessions, data dashboards, system analytics | Annually | Inadequate data use, fragmented systems, MEL fatigue | Annually | PMEL & PMs/TLs
| 2.1 |  | By 2028,the level of implementation of WWF core values and policies by all staff is atleast 90% relative to 2025 baseline | % adherence to core values based on compliance tracking and disciplinary records | 0 | Baseline information established | At least 75% of CCO staff adherence to core values based on compliance tracking and disciplinary records | At least 80% of CCO staff adherence to core values based on compliance tracking and disciplinary records | At least 90% of CCO staff adherence to core values based on compliance tracking and disciplinary records | At least 90% of CCO staff adherence to core values based on compliance tracking and disciplinary records | Core values and policies are well communicated and enforced | Ethics reports, incident tracking reports, HR disciplinary data | Internal audit checklists; non-compliance log | Annually | Inconsistent enforcement; fear of reporting violations | National & Landscape levels | CLT & PMs/TLs
| 2.2 |  | By FY'27, WWF CCO has developed and implemented an integrated science-based country strategy for the conservation of natural resources and the sustainable use of these resources by the local communities/indigenous people in the landscapes where CCO works By 2026, the CCO has a well-structured, adequately staffed, and supportive work environment that enhances staff performance, safety, and retention. | Country Strategy developed, approved and operationalized in priority landscapes | WWF CCO OSP developed and validated | At least 25% of strategic plan objectives being implemented | At least 50% of strategic plan objectives being implemented | At least 60% of strategic plan objectives being implemented | At least 75% of strategic plan objectives being implemented | Strategic plan is well-designed and aligned with capacity and context; leadership and staff are committed to implementation; adequate funding is available | Stakeholder engagement is effective; adequate scientific data and expertise are available; political environment remains supportive | Approved strategy document, implementation plans, evidence of activities in landscapes | Strategy documents, implementation reports, landscape assessments, stakeholder feedback tools | Annually | Political interference, limited stakeholder buy-in, lack of resources | National & Landscape levels | CLT & PMs/TLs
| 3.1 |  | By 2029, WWF CCO ensures full institutional compliance (100%) with all required internal and external policies, procedures, and quality standards related to the implementation of its 2026–2030 Office Strategic Plan (OSP), thereby enabling consistent, transparent, and high-quality delivery across all programmes and operations. By 2030, WWF CCO has an institutionalized compliance framework and systems that ensure consistent adherence to policies, partner agreements, and OSP standards. | % of organizational units meeting compliance requirements in annual reviews | 0 | Baseline information established | At least 90% of organizational units are meeting compliance requirements in annual reviews | At least 95% of organizational units are meeting compliance requirements in annual reviews | 100% of organizational units are meeting compliance requirements in annual reviews | 100% of organizational units are meeting compliance requirements in annual reviews | External standards remain stable and achievable; external partners cooperate | Internal quality assurance reports, partner evaluation reports, independent verification | Annual partner reviews, internal QA assessments | Annually | Regulatory changes, low partner compliance, operational disruptions | National & Landscape levels | CLT & PMs/TLs
OM Priorities outcomes | 3 | Fundraising | By end 2028, CCO is a viable, trusted and strategic partner for donors, CSOs, IPLC, private sector, government and other conservation and development players to work in synergy in delivering its conservation vision relative to 2020 baseline | Increase in number of partnerships, events co-hosted, joint publications, and endorsement of plans compared to 2020 baseline | 0 | Baseline information established | At least 1 new credible & functional partnership | At least 2 new credible & functional partnership | At least 3 new credible & functional partnership | At least 4 new credible & functional partnership | Stakeholders see added value in partnering with CCO; Political environment remains conducive; Resources are available for engagement activities | Partnership agreements, Event reports, Published materials, Endorsement letters | Stakeholder surveys, Partnership tracking matrix, Event reports, Document review | Annually | Political instability; Shifts in donor or partner priorities; Internal capacity constraints | National & Landscape levels | CLT & PMs/TLs
| 5 | Fundraising | 50% income growth i.e increased to FCFA 10,000,000,000 (US$ 20,000,000) achieved by CCO from a diversified fundraising base and surplus unrestricted income improved relative to the 2023 baseline | Total annual income and proportion of unrestricted income from diversified sources (public, private, foundations, etc.) |  | Baseline information established |  |  |  |  | Fundraising strategy is effectively implemented; donor interest remains strong; CCO has capacity to manage funds | Audited financial statements, donor portfolio reports | Financial records, donor reports, fundraising dashboards |  | Economic downturns, changing donor priorities, over-reliance on few sources | National & Landscape levels | DN & CLT
OM Priorities Outputs | 1.1 |  | By 2028 WWF CCO has institutionalized management decision-making and communication culture and systems to enable agility and effectiveness in conservation programme delivery relative to 2023 baseline
| 1.1.1 |  | 1. CCO staff awareness and use of the different channels and tools have increased by at least 75% by 2027 | % of staff reporting increased awareness and use of communications tools (email, intranet, newsletter, Teams, etc.) | [6 empty] | Tools are accessible and user-friendly; communications team provides training; leadership encourages use | Staff surveys, internal communication reports | Staff feedback forms, system usage analytics |  | Low digital literacy; tool fatigue; inconsistent rollout
| 1.1.2 |  | 2. Staff knowledge on use of internal and external communications tools, and clearance procedure enhanced by at least 75% by 2027 | % of staff demonstrating correct use of tools and procedures in practice and feedback | [6 empty] | Communication protocols are well documented; staff are trained and supported | Post-training evaluations, content review logs | Training attendance sheets, knowledge assessments |  | Lack of follow-up support; unclear procedures; staff turnover
| 1.1.3 |  | 3. CCO staff effectively receiving information and communication through the internal and external communications channels have increased by at least 75% by 2027 | % of staff who feel well-informed through internal channels (newsletters, intranet, email, meetings, etc.) | [6 empty] | Messages are relevant, timely, and accessible; channels are functioning well | Annual staff surveys, feedback sessions | Survey data, internal communications metrics |  | Communication overload; inconsistent messaging
| 1.1.4 |  | 4. CCO staff are writing and publishing quality reports, articles, position papers, etc. | Number and quality of staff-authored publications produced and shared annually | [6 empty] | Staff have writing skills, time, and institutional support; editorial process is in place | Publication records, editorial reviews, online analytics | Publication repository, web stats, citation tracking |  | Poor writing capacity; lack of editorial support; unclear guidance
| 1.1.5 |  | 5. Staff perception of WWF external communications has improved by at least 75% by 2027 | % of staff expressing positive perception of WWF’s public messaging and visibility | [6 empty] | External communication aligns with brand values; internal communications promote it effectively | Staff perception surveys, communications audit | Annual perception survey, social media engagement review |  | Disconnection between internal and external messages; external missteps
| 1.1.6 |  | 6. At least 75% of senior staff members are equipped with crisis communications and media interview skills | % of senior staff trained and confident in crisis response and media engagement | [6 empty] | Senior staff availability and willingness to participate; practical, scenario-based training delivered | Training records, post-training evaluations | Media training sessions, simulation exercises |  | Lack of senior staff buy-in; insufficient follow-up practice
| 1.2 |  | By 2028, CCO has an integrated information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline By 2028, technical and operational delivery is improved compared to 2023 baseline.
| 7.1 |  | 1. Logistics department is 100% equipped with an interactive tool to facilitate operations by January 2024 | Operational logistics tool fully deployed and used by staff (target: 100%) | [6 empty] | Tool is user-friendly; staff are trained; procurement and IT support available | Tool implementation reports, usage analytics | Deployment checklist, user feedback surveys |  | Resistance to change, technical issues
| 7.2 |  | 2. CCO is 100% equipped with an efficient electronic filing system for easy retrieval of information by June 2026 | All departments using standardized electronic filing system; retrieval time reduced | [6 empty] | Adequate IT infrastructure; staff follow protocols; system maintained | Internal audits, user satisfaction reports | File system audit logs, document access logs |  | Inconsistent use; technical breakdown; poor archiving discipline
| 7.3 |  | 3. Staff are at least 90% satisfied with information services based on survey report | ≥90% of staff report satisfaction in annual survey | [6 empty] | Information needs are well understood; services are responsive; feedback loop in place | Staff satisfaction survey report | Online/physical surveys, focus group discussions |  | Lack of responsiveness from info services; survey bias
| 7.4 |  | 4. Staff are at least 90% satisfied with logistics support based on survey report | ≥90% of staff satisfied with travel, procurement, fleet, and event support services | [6 empty] | Logistics services are timely, responsive, and adequately resourced | Survey reports, service usage records | Annual satisfaction survey, suggestion boxes |  | Delays in procurement; poor communication
| 7.5 |  | 5. Green and sustainable energy is 100% installed in Yaoundé and field offices to solve power outages | % of offices fully powered by solar/renewable systems (target: 100%) | [6 empty] | Technical assessments support feasibility; budget available; local suppliers engaged | Technical installation reports, energy audit | Energy bills, backup power use reports, system maintenance logs |  | Installation delays; poor maintenance; high upfront costs
| 7.6 |  | 6. Internet Connectivity reliable in Yaoundé Office | ≥95% uptime of internet connection measured monthly | [6 empty] | Reliable service provider; backup options available | Network performance logs, IT reports | Internet uptime monitoring software |  | Provider outages; equipment failure
| 7.7 |  | 7. Local Infrastructure in Yaoundé and field offices are upgraded to enterprise-based standard | % of sites meeting infrastructure checklist aligned with enterprise standard (target: 100%) | [6 empty] | Clear standard defined; budget available; renovations implemented in phases | Infrastructure audit report | Facilities checklist, procurement and renovation reports |  | Funding gaps; supply chain delays; remote site challenges
| 7.8 |  | 8. Digital dexterity of the staff ensured | % of staff proficient in using core digital tools and platforms (target: ≥90%) | [6 empty] | Training is prioritized; tools are relevant to job functions; staff willing to learn | Pre/post-training evaluations, IT support tickets | Digital literacy assessment, LMS reports, user support stats |  | Training fatigue; varying skill levels; lack of follow-up
| 1.3 |  | By 2028, CCO has an integrated monitoring, evaluation, learning, information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline
| 8.1 |  | 1. Accountability, credibility, and transparency with both internal staff, external donors, and other accountability bodies/stakeholders enhanced | Number of internal audits completed, donor compliance reports submitted on time, % of staff and partners reporting increased trust | [6 empty] | Leadership commitment to transparency; adequate systems for reporting and feedback | Internal audit reports, donor reports, stakeholder feedback reports | Annual surveys, audit tools, partner/stakeholder consultations |  | Misalignment between reporting tools and donor/stakeholder expectations; weak internal controls
| 8.2 |  | 2. Ownership of the work by staff, partners, and stakeholders, and therefore sustainability of the work for the future strengthened | % of projects with active partner/stakeholder engagement in design and implementation phases | [6 empty] | Stakeholders are genuinely involved and empowered; staff understand value of co-creation | Project documentation, partnership agreements, feedback forms | Engagement logs, co-creation workshop reports |  | Tokenistic participation; time constraints; weak communication
| 8.3 |  | 3. Improved staff efficiency to support the overall effort to professionalize and institutionalize WWF Cameroon Country Office processes and work, contributing to streamlining processes and promoting social cohesion among staff | % improvement in staff satisfaction, reduced turnaround time for core processes, improved internal communication scores | [6 empty] | Clear roles and responsibilities; process mapping and documentation in place; leadership supports culture of efficiency | Process audit reports, satisfaction surveys, performance reviews | HR data, workflow assessments, internal comms surveys |  | Process fatigue; resistance to change; unclear process owners
| 8.4 |  | 4. OD support is contributing effectively to achieving the CCO strategic plan | % of strategic plan goals positively impacted by OD interventions (target: ≥75%) | [6 empty] | OD initiatives aligned with strategic goals; leadership provides resources and support | Strategic plan progress reports, OD activity reports | Monitoring matrix, strategic KPIs, staff feedback |  | Fragmented OD efforts; weak linkage with strategy implementation
| 8.5 |  | 5. Lessons learned are used to inform decision-making, facilitate improved performance, to track changes, risks, and assumptions, and for adaptive management | % of projects/programs applying learning in subsequent planning and reporting cycles; number of documented learning products | [6 empty] | A learning culture is promoted; systems exist to capture and use lessons | After-action reviews, learning reports, adaptive action plans | Knowledge management tools, MEL reports, learning workshop outputs |  | Lessons not documented or revisited; low staff engagement in learning
| 2.1 |  | By 2028,the level of implementation of WWF core values and policies by all staff is atleast 90% relative to 2025 baseline
| 2.1.1 |  | All staff trained (including refreshers) on WWF core values, ethics, and code of conduct by June 2026 and annual refreshers done | % of staff completing initial and refresher trainings annually | [6 empty] | Training resources and schedules are available; staff are motivated to attend | Training attendance records; post-training assessments | E-learning modules, attendance registers, feedback forms |  | Competing priorities; limited trainer availability
| 2.1.3 |  | Staff recognition program established to reward compliance with WWF values and policies | # of staff recognized annually for exemplary value-based behavior | [6 empty] | Recognition is seen as meaningful; nominations are fairly evaluated | Award records; internal communication showcasing awardees | Nomination forms, recognition logs |  | Perceived favoritism; low participation
| 2.1.2 |  | Quarterly staff compliance assessments integrated into performance reviews on quarterly basis | % of performance reviews including compliance criteria | [6 empty] | HR systems are able to accommodate quarterly evaluations | Performance appraisal reports; staff scorecards | HRIS; appraisal templates |  | Staff fatigue from frequent reviews; inconsistent manager enforcement
| 2.1.4 |  | Biannual internal audits on policy compliance and staff conduct conducted with 100% response rate annually | % of audit recommendations addressed and compliance gaps closed | [6 empty] | Audit teams have capacity and independence; findings are acted upon | Audit reports; management response matrices | Audit checklists, F&C tracking sheets |  | Audit fatigue; poor management follow-through
| 2.1.5 |  | Leadership and line managers trained to model and reinforce WWF core values in their teams by December 2027 | % of managers trained and applying values-based leadership practices | [6 empty] | Leadership is committed to role-modelling; training is tailored and practical | Training reports; 360° feedback; team climate assessments | Training rosters, pre/post assessments |  | Resistance to change; unclear expectations
| 2.2 |  | By FY'27, WWF CCO has developed and implemented an integrated science-based country strategy for the conservation of natural resources and the sustainable use of these resources by the local communities/indigenous people in the landscapes where WWF CCO works By 2026, the CCO has a well-structured, adequately staffed, and supportive work environment that enhances staff performance, safety, and retention.
| 2.2.1 |  | 1. Organisational design completed (org chart, functions and roles) by December 2025 | Approved organizational structure, finalized organogram, and updated job descriptions in use | [6 empty] | Leadership and staff support change; external consultant (if used) delivers quality input; resources allocated for the process | Final org chart, HR records, Board or SMT approval minutes | HR files, org design documentation, staff feedback survey |  | Resistance to change; delays in approval; scope creep
| 2.2.2 |  | 2. Key vacancies filled by December 2025 | % of critical positions filled (target: 100%) | [6 empty] | Qualified candidates are available and willing to join; recruitment process is timely and well-resourced | HR recruitment records; Contracts signed; Onboarding reports | Vacancy tracker, interview records, recruitment reports |  | Talent scarcity; competition from other organizations; lengthy recruitment process
| 2.2.3 |  | 3. Improved organizational culture and enabling environment at CCO for enhanced staff performance and retention by Dec 2026 | Results of staff satisfaction survey (target: ≥75% positive); turnover rate reduced by 30% | [6 empty] | Leadership commitment to culture change; feedback mechanisms in place; HR systems support performance and growth | Staff surveys, retention reports, exit interviews | Employee satisfaction survey, HR MIS reports, performance appraisals |  | Resistance to culture change; weak leadership modelling; insufficient HR capacity
| 2.2.4 |  | 4. Improved health and security conditions (program disaster plans) for CCO staff by June 2026 | Disaster preparedness plans developed, tested, and implemented; % of staff trained in safety protocols | [6 empty] | Sufficient budget and expertise; collaboration with safety/security experts; staff participation in drills | Disaster response plan document, training reports, audit results | Risk management plans, security incident reports, training attendance sheets |  | Unpredictable crises; low staff engagement in training; inadequate infrastructure
| 3.1 |  | By 2029, WWF CCO ensures full institutional compliance (100%) with all required internal and external policies, procedures, and quality standards related to the implementation of its 2026–2030 Office Strategic Plan (OSP), thereby enabling consistent, transparent, and high-quality delivery across all programmes and operations. By 2030, WWF CCO has an institutionalized compliance framework and systems that ensure consistent adherence to policies, partner agreements, and OSP standards.
| 3.1.1 |  | Compliance Framework for OSP 2026–2030 developed, approved, and disseminated across WWF CCO with training provided to 10% of WWF CCO staff by December 2025 | Approved framework available; % of staff trained | [6 empty] | Leadership support; availability of technical expertise | Approved compliance framework; training attendance records | Training reports; staff feedback forms |  | Delays in approval; limited participation in training
| 3.1.2 |  | Annual compliance audits conducted with corrective actions implemented | # of audits conducted annually; % of corrective actions implemented | [6 empty] | Audit team capacity; cooperation of departments | Audit reports; corrective action logs; follow-up review reports | Audit checklists; corrective action tracking sheets |  | Low compliance response; audit fatigue
| 3.1.3 |  | Digital compliance tracking system (dashboard) designed, deployed, and updated quarterly | System developed and used; # of updates per year | [6 empty] | IT infrastructure in place; staff use the system | System logs; usage data; compliance issue resolution reports | System analytics dashboard; user feedback tools |  | Technical glitches; low adoption
| 3.1.4 |  | Quarterly management reviews and compliance oversight reports produced and acted upon | # of reviews held; % of action items addressed | [6 empty] | Leadership commitment; effective data collection | Meeting minutes; follow-up action trackers; compliance reports | Review templates; action tracking matrices |  | Low participation or follow-through; competing priorities
| 3.1.5 |  | Compliance clauses and reporting mechanisms integrated into all partner agreements and monitored annually | % of agreements with compliance clauses; # of partner compliance reports submitted | [6 empty] | Procurement/legal teams follow policy; partners accept terms | Signed contracts; partner monitoring reports | Compliance checklist for contracts; partner reporting templates |  | Partner resistance; poor follow-up from WWF teams
| 3.1.6 |  | Comprehensive documentation system for compliance maintained for all OSP-related projects annually | % of projects with complete and updated compliance documentation | [6 empty] | Staff understand documentation protocols; archiving systems exist | Document repository; M&E reports; project audit files | Documentation templates; file review logs |  | Poor recordkeeping; lack of standardization
| 3 | Resource Acquisition | By end 2028, CCO is a viable, trusted and strategic partner for donors, CSOs, IPLC, private sector, government and other conservation and development players to work in synergy in delivering its conservation vision relative to 2020 baseline
| 3.1 |  | The endorsement of the CCO private sector engagement plan by QAC facilitated | Engagement plan endorsed and officially documented by QAC | [6 empty] | QAC is supportive of CCO’s direction and open to collaboration | Official QAC documentation of endorsement | Meeting minutes, correspondence, signed endorsement letter |  | Resistance from QAC; Changes in QAC leadership
| 3.2 |  | At least 4 new strategic partnership agreements signed with CCO | Number of signed partnership MOUs/agreements | [6 empty] | Clear value proposition presented by CCO; Willing partners exist | Signed MOUs; Communications from partners | Partnership tracking database; Document review |  | Competition for partners; Misalignment of interests
| 3.3 |  | At least 2 conservation events/fora/discourse co-organized with strategic partners annually | Number of co-organized events per year | [6 empty] | Partners are willing and able to co-host; Sufficient budget and staff time | Event agendas, Participant lists, Reports | Event calendars, Reports, Invitations |  | Logistical challenges; Lack of interest or capacity from partners
| 3.4 |  | At least one proposal, one position paper, one publication jointly developed and shared with the right audience annually | Number of joint documents developed and disseminated | [6 empty] | Partners have technical capacity and willingness to co-develop content | Published materials, Media coverage, Website analytics | Document repository, Communication records |  | Limited partner capacity or time; Disagreements on content
| 5 | Resource Acquisition | 50% income growth i.e increased to FCFA 10,000,000,000 (US$ 20,000,000) achieved by CCO from a diversified fundraising base and surplus unrestricted income improved relative to the 2023 baseline
| 5.1 |  | 1. Funds through joint proposals with corporate entities increased by 10% by June 2026 and by 20% by Dec 2028 | % increase in funds from joint proposals with corporate entities | [6 empty] | Assumptions | Means of Verification | Data Collection Tool
| 5.2 |  | 2. At least one joint proposal submitted to PSPs after every two years is approved for funding | Number of approved proposals submitted to Public Sector Partners every two years (target: ≥1) | [6 empty] | Strong partnerships with corporate sector; proposals aligned with shared goals (CSR/sustainability); economic stability | Financial statements, grant agreements | Fundraising database, proposal tracker
| 5.3 |  | 3. At least one proposal submitted to Foundations after every two years is approved for funding | Number of approved foundation proposals every two years (target: ≥1) | [6 empty] | PSPs maintain strong interest in conservation; quality of proposals is high; compliance with donor guidelines | Donor approval letters, contracts, progress reports | Proposal submission and outcome tracker
| 5.4 |  | 4. At least 4 new donors are committing 200,000 US$ per year to CCO | Number of new donors annually committing ≥$200,000 | [6 empty] | Foundations have funding calls aligned with CCO strategy; quality and relevance of proposals are strong | Grant award letters, donor agreements | Foundation proposal tracker, donor database
| 5.5 |  | 5. Funds mobilized through the Network have increased by at least 20% by 2025 | % increase in income from WWF Network sources by 2025 (baseline 2023) | [6 empty] | Effective donor cultivation and stewardship; clear value proposition and trust in CCO’s delivery | Signed donor agreements, financial records | Donor pipeline tracker, income reports
| 5.6 |  | 6. By 2028, mobilize funds close to 20,000,000 US$ | Total cumulative funds raised by 2028 (target: US$ 20M) | [6 empty] | Continued prioritization of CCO by Network offices; CCO delivers on program quality | Network financial reports, joint funding agreements | Network fundraising dashboard, income analysis tool

## OSP M&E Plan revision2
OM M&E plan | # |  | Description | Indicator | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Assumptions | Means of Verification | Data Collection Tool | Frequency of Measurement | Risks | Location | Responsible
OM Priorities Theory of Change
OM Goals | 1 | Operational Excellence Demonstrated | By 2030, WWF CCO demonstrates operational excellence by achieving at least 75% of its strategic plan goals | % of strategic plan objectives fully achieved or on track by 2030 (target: ≥75%) | 0 | Baseline Information on OSP implementation established | At least 25% of strategic plan objectives fully achieved or on track | At least 50% of strategic plan objectives fully achieved or on track | At least 70% of strategic plan objectives fully achieved or on track | At least 75% of strategic plan objectives fully achieved or on track | Strategic plan is well-designed and aligned with capacity and context; leadership and staff are committed to implementation; adequate funding is available | Mid-term and end-term strategic plan evaluations, annual progress reports, scorecards, board meeting minutes | Annual performance reviews, strategic plan tracking tools, KPI dashboards, internal audit reports | Annually | Inadequate resource mobilization, misalignment between operations and strategy, external shocks (e.g., political/economic instability) | National & Landscape levels | DC & PMEL team
|  |  |  | % of staff satisfied with the governance and leadership system | 0 | Baseline information collected | At least 75% of staff are satisfied with the governance and leadership system | At least 80% of staff are satisfied with the governance and leadership system | At least 85% of staff are satisfied with the governance and leadership system | At least 95% of staff are satisfied with the governance and leadership system | Staff feel safe to express honest feedback; leadership engages meaningfully with feedback Core values and policies are well communicated and enforced | Staff satisfaction reports; survey summaries; leadership action plans | Staff perception survey tool | Annually | Low participation rates; perception of survey ineffectiveness | National & Landscape levels | CLT & PMs/TLs
|  |  |  | % of the governance and leadership system that are marked satisfactory | 0 | Baseline information collected | At least 30% of the governance and leadership system that are marked satisfactory | At least 35% of the governance and leadership system that are marked satisfactory | At least 40% of the governance and leadership system that are marked satisfactory | At least 50% of the governance and leadership system that are marked satisfactory
| 2 | Staff performance, satisfaction, and retention | By 2030, the level of CCO staff performance, satisfaction, and retention is maintained at 90% or higher relative to the 2024 baseline. | % score of competent and accountable staff retained | 0 | Baseline information established | At least 80% of competent and accountable staff retained | At least 80% of competent and accountable staff retained | At least 90% of competent and accountable staff retained | At least 95% of competent and accountable staff retained | • Sufficient financial resources are available for staff capacity-building, incentives, and retention programs • Leadership remains committed to staff development • External factors (e.g., political, economic) remain stable | • Annual HR reports • Performance appraisal results • Staff satisfaction surveys • Exit interview reports | • Staff performance evaluation forms • Annual staff satisfaction questionnaires • HR MIS system • Exit interview templates | Annually | • High staff turnover due to external opportunities • Burnout or poor morale due to workload or unmet expectations • Budget constraints reducing investment in staff welfare | National & Landscape levels | CLT
|  |  |  | % score in performance evaluation |  |  | At least 75% average staff score in performance evaluation | At least 80% average staff score in performance evaluation | At least 90% average staff score in performance evaluation | At least 95% average staff score in performance evaluation | [6 empty] | CLT & PMs/TLs
|  |  |  | Score (%) of landscape staff satisfaction on wellbeing conditions. |  |  | At least 75% of sites-based staff are satisfied with the wellbeing conditions | At least 80% of sites-based staff are satisfied with the wellbeing conditions | At least 90% of sites-based staff are satisfied with the wellbeing conditions | At least 95% of sites-based staff are satisfied with the wellbeing conditions | [6 empty] | CLT & PMs
| 3 | Full compliance with Policies and procedures | By 2030, WWF CCO has achieved 100% compliance with the required policies and procedures | % of compliance with procedures and policies | 95% Compliance with procedures and policies | 98% Compliance with procedures and policies | 100% Compliance with procedures and policies | 100% Compliance with procedures and policies | 100% Compliance with procedures and policies | 100% Compliance with procedures and policies | Adequate staff capacity and leadership commitment to enforce compliance | Annual compliance audit reports, M&E system outputs, external audit findings | Audit tools, compliance dashboard | Annually | Inadequate funding, staff turnover, resistance to accountability mechanisms | National & Landscape levels | CLT & PMs/TLs
|  |  |  | % Score of level of implementation and efficiency of the governance structure in place Structured system put in place Number of documents shared | 80% implementation and efficiency of the governance structure in place | 85% implementation and efficiency of the governance structure in place | 90% implementation and efficiency of the governance structure in place | 95% implementation and efficiency of the governance structure in place | 98% implementation and efficiency of the governance structure in place | 100% implementation and efficiency of the governance structure in place |  |  |  | Annually
OM Priorities outcomes | 1.1 | Institutionalized management decision-making | By 2028 WWF CCO has institutionalized management decision-making and communication culture and systems to enable agility and effectiveness in conservation programme delivery relative to 2023 baseline | Evidence of functional decision-making and internal communication systems; improved decision turnaround times | 0 | Baseline information established | At least 1 decision made to improve on internal and effectiveness in OSP delivery | At least 1 new decision made to improve on internal and effectiveness in OSP delivery | At least 1 new decision made to improve on internal and effectiveness in OSP delivery | At least 1 new decision made to improve on internal and effectiveness in OSP delivery | Leadership is committed; systems are adopted organization-wide; training is effective | Performance reviews, dashboards, survey results, decision logs | Internal audits, HR reports, staff surveys, management meeting minutes | Annually | Resistance to change, staff turnover, weak IT infrastructure | National & Landscape levels | DN & CLT
| 1.2 | Technical and operational Deivery Improved | By 2028, technical and operational delivery is improved compared to 2023 baseline. | % of teams reporting improved access to and use of timely data/information; frequency of use of the knowledge system | 0 | Baseline information for IT satisfaction survey established | At least 75% staff satisfaction survey score on IT | At least 85% staff satisfaction survey score on IT | At least 90% staff satisfaction survey score on IT | At least 95% staff satisfaction survey score on IT | Digital literacy is sufficient across teams; systems are interoperable; staff are willing to share knowledge | Reports from KM system, case studies, increased documentation and learning products | KM system usage data, user feedback surveys, IT system reports | Annually | Low usage by staff, poor data quality, siloed departments | Annually | IT & PMs/TLs
| 1.3 | Integrated PMEL | By 2028, CCO has an integrated monitoring, evaluation, learning, information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline | % of programmes using integrated MELIKM data for decision-making and reporting; quality of data collected and used | At least 60% of technical and operations delivery of CCO strategy achieved | At least 70% of technical and operations delivery of CCO strategy achieved | At least 75% of technical and operations delivery of CCO strategy achieved | At least 80% of technical and operations delivery of CCO strategy achieved | At least 85% of technical and operations delivery of CCO strategy achieved | 90% of technical and operations delivery of CCO strategy achieved | Sufficient capacity and tools; commitment to learning and adaptation; resources for implementation | Evaluation reports, adaptive management decisions, improved outcomes in program reports | MEL reports, learning sessions, data dashboards, system analytics | Annually | Inadequate data use, fragmented systems, MEL fatigue | Annually | PMEL & PMs/TLs
| 2.1 | Core Values implemented | By 2028,the level of implementation of WWF core values and policies by all staff is atleast 90% relative to 2025 baseline | % adherence to core values based on compliance tracking and disciplinary records | 0 | Baseline information established | At least 75% of CCO staff adherence to core values based on compliance tracking and disciplinary records | At least 80% of CCO staff adherence to core values based on compliance tracking and disciplinary records | At least 90% of CCO staff adherence to core values based on compliance tracking and disciplinary records | At least 90% of CCO staff adherence to core values based on compliance tracking and disciplinary records | Core values and policies are well communicated and enforced | Ethics reports, incident tracking reports, HR disciplinary data | Internal audit checklists; non-compliance log | Annually | Inconsistent enforcement; fear of reporting violations | National & Landscape levels | CLT & PMs/TLs
| 2.2 | Estbalished Organizational Structure | By 2026, the CCO has a well-structured, adequately staffed, and supportive work environment | Country Strategy developed, approved and operationalized in priority landscapes | WWF CCO OSP developed and validated | At least 25% of strategic plan objectives being implemented | At least 50% of strategic plan objectives being implemented | At least 60% of strategic plan objectives being implemented | At least 75% of strategic plan objectives being implemented | Strategic plan is well-designed and aligned with capacity and context; leadership and staff are committed to implementation; adequate funding is available | Stakeholder engagement is effective; adequate scientific data and expertise are available; political environment remains supportive | Approved strategy document, implementation plans, evidence of activities in landscapes | Strategy documents, implementation reports, landscape assessments, stakeholder feedback tools | Annually | Political interference, limited stakeholder buy-in, lack of resources | National & Landscape levels | CLT & PMs/TLs
| 3.1 | Institutionalized compliance framework | By 2030, WWF CCO has an institutionalized compliance framework and systems that ensure consistent adherence to policies, procedures, partner agreements, and OSP standards. | % of organizational units meeting compliance requirements in annual reviews | 0 | Baseline information established | At least 90% of organizational units are meeting compliance requirements in annual reviews | At least 95% of organizational units are meeting compliance requirements in annual reviews | 100% of organizational units are meeting compliance requirements in annual reviews | 100% of organizational units are meeting compliance requirements in annual reviews | External standards remain stable and achievable; external partners cooperate | Internal quality assurance reports, partner evaluation reports, independent verification | Annual partner reviews, internal QA assessments | Annually | Regulatory changes, low partner compliance, operational disruptions | National & Landscape levels | CLT & PMs/TLs
OM Priorities Outputs | 1.1 | Institutionalized management decision-making | By 2028 WWF CCO has institutionalized management decision-making and communication culture and systems to enable agility and effectiveness in conservation programme delivery relative to 2023 baseline
| 1.1.1 |  | 1. CCO staff awareness and use of the different channels and tools have increased by at least 75% by 2027 | % of staff reporting increased awareness and use of communications tools (email, intranet, newsletter, Teams, etc.) | [6 empty] | Tools are accessible and user-friendly; communications team provides training; leadership encourages use | Staff surveys, internal communication reports | Staff feedback forms, system usage analytics |  | Low digital literacy; tool fatigue; inconsistent rollout
| 1.1.2 |  | 2. Staff knowledge on use of internal and external communications tools, and clearance procedure enhanced by at least 75% by 2027 | % of staff demonstrating correct use of tools and procedures in practice and feedback | [6 empty] | Communication protocols are well documented; staff are trained and supported | Post-training evaluations, content review logs | Training attendance sheets, knowledge assessments |  | Lack of follow-up support; unclear procedures; staff turnover
| 1.1.3 |  | 3. CCO staff effectively receiving information and communication through the internal and external communications channels have increased by at least 75% by 2027 | % of staff who feel well-informed through internal channels (newsletters, intranet, email, meetings, etc.) | [6 empty] | Messages are relevant, timely, and accessible; channels are functioning well | Annual staff surveys, feedback sessions | Survey data, internal communications metrics |  | Communication overload; inconsistent messaging
| 1.1.4 |  | 4. CCO staff are writing and publishing quality reports, articles, position papers, etc. | Number and quality of staff-authored publications produced and shared annually | [6 empty] | Staff have writing skills, time, and institutional support; editorial process is in place | Publication records, editorial reviews, online analytics | Publication repository, web stats, citation tracking |  | Poor writing capacity; lack of editorial support; unclear guidance
| 1.1.5 |  | 5. Staff perception of WWF external communications has improved by at least 75% by 2027 | % of staff expressing positive perception of WWF’s public messaging and visibility | [6 empty] | External communication aligns with brand values; internal communications promote it effectively | Staff perception surveys, communications audit | Annual perception survey, social media engagement review |  | Disconnection between internal and external messages; external missteps
| 1.1.6 |  | 6. At least 75% of senior staff members are equipped with crisis communications and media interview skills | % of senior staff trained and confident in crisis response and media engagement | [6 empty] | Senior staff availability and willingness to participate; practical, scenario-based training delivered | Training records, post-training evaluations | Media training sessions, simulation exercises |  | Lack of senior staff buy-in; insufficient follow-up practice
| 1.2 | Technical and operational Deivery Improved | By 2028, technical and operational delivery is improved compared to 2023 baseline.
| 7.1 |  | 1. Logistics department is 100% equipped with an interactive tool to facilitate operations by January 2024 | Operational logistics tool fully deployed and used by staff (target: 100%) | [6 empty] | Tool is user-friendly; staff are trained; procurement and IT support available | Tool implementation reports, usage analytics | Deployment checklist, user feedback surveys |  | Resistance to change, technical issues
| 7.2 |  | 2. CCO is 100% equipped with an efficient electronic filing system for easy retrieval of information by June 2026 | All departments using standardized electronic filing system; retrieval time reduced | [6 empty] | Adequate IT infrastructure; staff follow protocols; system maintained | Internal audits, user satisfaction reports | File system audit logs, document access logs |  | Inconsistent use; technical breakdown; poor archiving discipline
| 7.3 |  | 3. Staff are at least 90% satisfied with information services based on survey report | ≥90% of staff report satisfaction in annual survey | [6 empty] | Information needs are well understood; services are responsive; feedback loop in place | Staff satisfaction survey report | Online/physical surveys, focus group discussions |  | Lack of responsiveness from info services; survey bias
| 7.4 |  | 4. Staff are at least 90% satisfied with logistics support based on survey report | ≥90% of staff satisfied with travel, procurement, fleet, and event support services | [6 empty] | Logistics services are timely, responsive, and adequately resourced | Survey reports, service usage records | Annual satisfaction survey, suggestion boxes |  | Delays in procurement; poor communication
| 7.5 |  | 5. Green and sustainable energy is 100% installed in Yaoundé and field offices to solve power outages | % of offices fully powered by solar/renewable systems (target: 100%) | [6 empty] | Technical assessments support feasibility; budget available; local suppliers engaged | Technical installation reports, energy audit | Energy bills, backup power use reports, system maintenance logs |  | Installation delays; poor maintenance; high upfront costs
| 7.6 |  | 6. Internet Connectivity reliable in Yaoundé Office | ≥95% uptime of internet connection measured monthly | [6 empty] | Reliable service provider; backup options available | Network performance logs, IT reports | Internet uptime monitoring software |  | Provider outages; equipment failure
| 7.7 |  | 7. Local Infrastructure in Yaoundé and field offices are upgraded to enterprise-based standard | % of sites meeting infrastructure checklist aligned with enterprise standard (target: 100%) | [6 empty] | Clear standard defined; budget available; renovations implemented in phases | Infrastructure audit report | Facilities checklist, procurement and renovation reports |  | Funding gaps; supply chain delays; remote site challenges
| 7.8 |  | 8. Digital dexterity of the staff ensured | % of staff proficient in using core digital tools and platforms (target: ≥90%) | [6 empty] | Training is prioritized; tools are relevant to job functions; staff willing to learn | Pre/post-training evaluations, IT support tickets | Digital literacy assessment, LMS reports, user support stats |  | Training fatigue; varying skill levels; lack of follow-up
| 1.3 | Integrated PMEL | By 2028, CCO has an integrated monitoring, evaluation, learning, information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline
| 8.1 |  | 1. Accountability, credibility, and transparency with both internal staff, external donors, and other accountability bodies/stakeholders enhanced | Number of internal audits completed, donor compliance reports submitted on time, % of staff and partners reporting increased trust | [6 empty] | Leadership commitment to transparency; adequate systems for reporting and feedback | Internal audit reports, donor reports, stakeholder feedback reports | Annual surveys, audit tools, partner/stakeholder consultations |  | Misalignment between reporting tools and donor/stakeholder expectations; weak internal controls
| 8.2 |  | 2. Ownership of the work by staff, partners, and stakeholders, and therefore sustainability of the work for the future strengthened | % of projects with active partner/stakeholder engagement in design and implementation phases | [6 empty] | Stakeholders are genuinely involved and empowered; staff understand value of co-creation | Project documentation, partnership agreements, feedback forms | Engagement logs, co-creation workshop reports |  | Tokenistic participation; time constraints; weak communication
| 8.3 |  | 3. Improved staff efficiency to support the overall effort to professionalize and institutionalize WWF Cameroon Country Office processes and work, contributing to streamlining processes and promoting social cohesion among staff | % improvement in staff satisfaction, reduced turnaround time for core processes, improved internal communication scores | [6 empty] | Clear roles and responsibilities; process mapping and documentation in place; leadership supports culture of efficiency | Process audit reports, satisfaction surveys, performance reviews | HR data, workflow assessments, internal comms surveys |  | Process fatigue; resistance to change; unclear process owners
| 8.4 |  | 4. OD support is contributing effectively to achieving the CCO strategic plan | % of strategic plan goals positively impacted by OD interventions (target: ≥75%) | [6 empty] | OD initiatives aligned with strategic goals; leadership provides resources and support | Strategic plan progress reports, OD activity reports | Monitoring matrix, strategic KPIs, staff feedback |  | Fragmented OD efforts; weak linkage with strategy implementation
| 8.5 |  | 5. Lessons learned are used to inform decision-making, facilitate improved performance, to track changes, risks, and assumptions, and for adaptive management | % of projects/programs applying learning in subsequent planning and reporting cycles; number of documented learning products | [6 empty] | A learning culture is promoted; systems exist to capture and use lessons | After-action reviews, learning reports, adaptive action plans | Knowledge management tools, MEL reports, learning workshop outputs |  | Lessons not documented or revisited; low staff engagement in learning
| 2.1 | Core Values implemented | By 2028,the level of implementation of WWF core values and policies by all staff is atleast 90% relative to 2025 baseline
| 2.1.1 |  | All staff trained (including refreshers) on WWF core values, ethics, and code of conduct by June 2026 and annual refreshers done | % of staff completing initial and refresher trainings annually | [6 empty] | Training resources and schedules are available; staff are motivated to attend | Training attendance records; post-training assessments | E-learning modules, attendance registers, feedback forms |  | Competing priorities; limited trainer availability
| 2.1.3 |  | Staff recognition program established to reward compliance with WWF values and policies | # of staff recognized annually for exemplary value-based behavior | [6 empty] | Recognition is seen as meaningful; nominations are fairly evaluated | Award records; internal communication showcasing awardees | Nomination forms, recognition logs |  | Perceived favoritism; low participation
| 2.1.2 |  | Quarterly staff compliance assessments integrated into performance reviews on quarterly basis | % of performance reviews including compliance criteria | [6 empty] | HR systems are able to accommodate quarterly evaluations | Performance appraisal reports; staff scorecards | HRIS; appraisal templates |  | Staff fatigue from frequent reviews; inconsistent manager enforcement
| 2.1.4 |  | Biannual internal audits on policy compliance and staff conduct conducted with 100% response rate annually | % of audit recommendations addressed and compliance gaps closed | [6 empty] | Audit teams have capacity and independence; findings are acted upon | Audit reports; management response matrices | Audit checklists, F&C tracking sheets |  | Audit fatigue; poor management follow-through
| 2.1.5 |  | Leadership and line managers trained to model and reinforce WWF core values in their teams by December 2027 | % of managers trained and applying values-based leadership practices | [6 empty] | Leadership is committed to role-modelling; training is tailored and practical | Training reports; 360° feedback; team climate assessments | Training rosters, pre/post assessments |  | Resistance to change; unclear expectations
| 2.2 | Estbalished Organizational Structure | By 2026, the CCO has a well-structured, adequately staffed, and supportive work environment
| 2.2.1 |  | 1. Organisational design completed (org chart, functions and roles) by December 2025 | Approved organizational structure, finalized organogram, and updated job descriptions in use | [6 empty] | Leadership and staff support change; external consultant (if used) delivers quality input; resources allocated for the process | Final org chart, HR records, Board or SMT approval minutes | HR files, org design documentation, staff feedback survey |  | Resistance to change; delays in approval; scope creep
| 2.2.2 |  | 2. Key vacancies filled by December 2025 | % of critical positions filled (target: 100%) | [6 empty] | Qualified candidates are available and willing to join; recruitment process is timely and well-resourced | HR recruitment records; Contracts signed; Onboarding reports | Vacancy tracker, interview records, recruitment reports |  | Talent scarcity; competition from other organizations; lengthy recruitment process
| 2.2.3 |  | 3. Improved organizational culture and enabling environment at CCO for enhanced staff performance and retention by Dec 2026 | Results of staff satisfaction survey (target: ≥75% positive); turnover rate reduced by 30% | [6 empty] | Leadership commitment to culture change; feedback mechanisms in place; HR systems support performance and growth | Staff surveys, retention reports, exit interviews | Employee satisfaction survey, HR MIS reports, performance appraisals |  | Resistance to culture change; weak leadership modelling; insufficient HR capacity
| 2.2.4 |  | 4. Improved health and security conditions (program disaster plans) for CCO staff by June 2026 | Disaster preparedness plans developed, tested, and implemented; % of staff trained in safety protocols | [6 empty] | Sufficient budget and expertise; collaboration with safety/security experts; staff participation in drills | Disaster response plan document, training reports, audit results | Risk management plans, security incident reports, training attendance sheets |  | Unpredictable crises; low staff engagement in training; inadequate infrastructure
| 3.1 | Institutionalized compliance framework | By 2030, WWF CCO has an institutionalized compliance framework and systems that ensure consistent adherence to policies, procedures, partner agreements, and OSP standards.
| 3.1.1 |  | Compliance Framework for OSP 2026–2030 developed, approved, and disseminated across WWF CCO with training provided to 10% of WWF CCO staff by December 2025 | Approved framework available; % of staff trained | [6 empty] | Leadership support; availability of technical expertise | Approved compliance framework; training attendance records | Training reports; staff feedback forms |  | Delays in approval; limited participation in training
| 3.1.2 |  | Annual compliance audits conducted with corrective actions implemented | # of audits conducted annually; % of corrective actions implemented | [6 empty] | Audit team capacity; cooperation of departments | Audit reports; corrective action logs; follow-up review reports | Audit checklists; corrective action tracking sheets |  | Low compliance response; audit fatigue
| 3.1.3 |  | Digital compliance tracking system (dashboard) designed, deployed, and updated quarterly | System developed and used; # of updates per year | [6 empty] | IT infrastructure in place; staff use the system | System logs; usage data; compliance issue resolution reports | System analytics dashboard; user feedback tools |  | Technical glitches; low adoption
| 3.1.4 |  | Quarterly management reviews and compliance oversight reports produced and acted upon | # of reviews held; % of action items addressed | [6 empty] | Leadership commitment; effective data collection | Meeting minutes; follow-up action trackers; compliance reports | Review templates; action tracking matrices |  | Low participation or follow-through; competing priorities
| 3.1.5 |  | Compliance clauses and reporting mechanisms integrated into all partner agreements and monitored annually | % of agreements with compliance clauses; # of partner compliance reports submitted | [6 empty] | Procurement/legal teams follow policy; partners accept terms | Signed contracts; partner monitoring reports | Compliance checklist for contracts; partner reporting templates |  | Partner resistance; poor follow-up from WWF teams
| 3.1.6 |  | Comprehensive documentation system for compliance maintained for all OSP-related projects annually | % of projects with complete and updated compliance documentation | [6 empty] | Staff understand documentation protocols; archiving systems exist | Document repository; M&E reports; project audit files | Documentation templates; file review logs |  | Poor recordkeeping; lack of standardization

## Implementation Plan
| Output Number | Output Statement | FY26 Cost (XAF) | FY27 Cost (XAF) | FY28 Cost (XAF) | FY29 Cost (XAF) | FY30 Cost (XAF) | Total (XAF) | Current Project (CPM Project #) | Target Funding Source
READ Me First. OD Costs should include: A. Human Resources and Capacity Development B. Organisational Governance and Compliance C. Operational Efficiency and Process Improvement D. Technology and Systems E. Stakeholder Engagement and Communications | Please enter the output number | Please list all the outputs identified under the Factors & Outcome tab as well as the M&E plan. During the annual planning and budgeting process, the Programme will have opportunities to further refine and detail the activities and costs. The initial costing of the priority outputs can be estimated, which will be used to estimate the cost of total OSP implementation and the development of the financial plan. Please make sure to include outputs related to M&E, ESSF and other risk mitigation, etc. | [5 empty] | This column will be automatically sum up the total. | If the activity is already funded, please indicate the relevant CPM number(s). | If there is a funding gap and have prospective funding sources, please indicate the source.
|  | By 2028,the level of implementation of WWF core values and policies by all staff is atleast 90% relative to 2025 baseline | [5 empty] | 0
|  | All staff trained (including refreshers) on WWF core values, ethics, and code of conduct by June 2026 and annual refreshers done | 20000000 | 20000000 | 20000000 | 25000000 | 30000000 | 115000000
|  | Quarterly staff compliance assessments integrated into performance reviews on quarterly basis | 10000000 | 10000000 | 15000000 | 15000000 | 15000000 | 65000000
|  | Staff recognition program established to reward compliance with WWF values and policies | 10000000 | 10000000 | 20000000 | 20000000 | 20000000 | 80000000
|  | Biannual internal audits on policy compliance and staff conduct conducted with 100% response rate annually | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
|  | Leadership and line managers trained to model and reinforce WWF core values in their teams by December 2027 | 20000000 | 20000000 | 20000000 | 25000000 | 30000000 | 115000000
|  | ANNUAL TOTAL BUDGET FOR OPERATIONAL EXCELLENCE | 70000000 | 70000000 | 85000000 | 95000000 | 105000000 | 425000000
|  | By 2029, WWF CCO ensures full institutional compliance (100%) with all required internal and external policies, procedures, and quality standards related to the implementation of its 2026–2030 Office Strategic Plan (OSP), thereby enabling consistent, transparent, and high-quality delivery across all programmes and operations. | [5 empty] | 0
|  | Compliance Framework for OSP 2026–2030 developed, approved, and disseminated across WWF CCO with training provided to 10% of WWF CCO staff by December 2025 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 100000000
|  | Annual compliance audits conducted with corrective actions implemented | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
|  | Digital compliance tracking system (dashboard) designed, deployed, and updated quarterly | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 100000000
|  | Quarterly management reviews and compliance oversight reports produced and acted upon | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
|  | Compliance clauses and reporting mechanisms integrated into all partner agreements and monitored annually | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
|  | Comprehensive documentation system for compliance maintained for all OSP-related projects annually | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
|  | ANNUAL TOTAL BUDGET FOR GOVERNANCE & LEADERSHIP | 80000000 | 80000000 | 80000000 | 80000000 | 80000000 | 400000000
|  | By FY'27, WWF CCO has developed and implemented an integrated science-based country strategy for the conservation of natural resources and the sustainable use of these resources by the local communities/indigenous people in the landscapes where WWF CCO works | [5 empty] | 0
|  | Organisational design completed (org chart, functions and roles) by December 2025 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
|  | Key vacancies filled by December 2025 | 60000000 | 70000000 | 80000000 | 90000000 | 100000000 | 400000000
|  | Improved organizational culture and enabling environment at CCO for enhanced staff performance and retention by Dec 2026 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
|  | Improved health and security conditions (program disaster plans) for CCO staff by June 2026 | 20000000 | 25000000 | 30000000 | 40000000 | 50000000 | 165000000
|  | ANNUAL TOTAL BUDGET FOR PEOPLE, CAPACITIES, OD AND WELLBEING (LANDSCAPES) | 100000000 | 115000000 | 130000000 | 150000000 | 170000000 | 665000000
|  | By 2028 WWF CCO has institutionalized management decision-making and communication culture and systems to enable agility and effectiveness in conservation programme delivery relative to 2023 baseline | [5 empty] | 0
|  | CCO staff awareness and use of the different channels and tools have increased by at least 75% by 2027 | 10000000 | 10000000 | 15000000 | 15000000 | 15000000 | 65000000
|  | Staff knowledge on use of internal and external communications tools, and clearance procedure enhanced by at least 75% by 2027 | 5000000 | 10000000 | 15000000 | 15000000 | 15000000 | 60000000
|  | CCO staff effectively receiving information and communication through the internal and external communications channels have increased by at least 75% by 2027 | 10000000 | 15000000 | 20000000 | 25000000 | 30000000 | 100000000
|  | CCO staff are writing and publishing quality reports, articles, position papers, etc. | 5000000 | 10000000 | 15000000 | 20000000 | 20000000 | 70000000
|  | Staff perception of WWF external communications has improved by at least 75% by 2027 | 10000000 | 15000000 | 20000000 | 20000000 | 25000000 | 90000000
|  | At least 75% of senior staff members are equipped with crisis communications and media interview skills | 10000000 | 15000000 | 20000000 | 20000000 | 25000000 | 90000000
|  | ANNUAL TOTAL BUDGET FOR EXTERNAL AND INTERNAL COMMUNICATION | 50000000 | 75000000 | 105000000 | 115000000 | 130000000 | 475000000
|  | By 2028, CCO has an integrated information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline | [5 empty] | 0
|  | Logistics department is 100% equipped with an interactive tool to facilitate operations by January 2024 | 30000000 | 40000000 | 50000000 | 60000000 | 75000000 | 255000000
|  | CCO is 100% equipped with an efficient electronic filing system for easy retrieval of information by June 2026 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
|  | Staff are at least 90% satisfied with information services based on survey report | 5000000 | 10000000 | 10000000 | 10000000 | 10000000 | 45000000
|  | Staff are at least 90% satisfied with logistics support based on survey report | 5000000 | 10000000 | 10000000 | 10000000 | 10000000 | 45000000
|  | Green and sustainable energy is 100% installed in Yaoundé and field offices to solve power outages | 20000000 | 30000000 | 40000000 | 50000000 | 60000000 | 200000000
|  | Internet Connectivity reliable in Yaoundé Office | 10000000 | 20000000 | 20000000 | 20000000 | 20000000 | 90000000
|  | Local Infrastructure in Yaoundé and field offices are upgraded to enterprise-based standard | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 100000000
|  | Digital dexterity of the staff ensured | 10000000 | 20000000 | 20000000 | 20000000 | 20000000 | 90000000
|  | ANNUAL TOTAL BUDGET FOR ENABLING INTEGRATED INFORMATION SYSTEM | 110000000 | 160000000 | 180000000 | 200000000 | 225000000 | 875000000
|  | By 2028, CCO has an integrated monitoring, evaluation, learning, information and knowledge management system that is enhancing at least 75% of technical and operations delivery of CCO strategy relative to 2023 baseline | [5 empty] | 0
|  | Accountability, credibility, and transparency with both internal staff, external donors, and other accountability bodies/stakeholders enhanced | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 50000000
|  | Ownership of the work by staff, partners, and stakeholders, and therefore sustainability of the work for the future strengthened | 20000000 | 25000000 | 25000000 | 25000000 | 25000000 | 120000000
|  | Improved staff efficiency to support the overall effort to professionalize and institutionalize WWF Cameroon Country Office processes and work, contributing to streamlining processes and promoting social cohesion among staff | 20000000 | 25000000 | 30000000 | 35000000 | 40000000 | 150000000
|  | OD support is contributing effectively to achieving the CCO strategic plan | 30000000 | 40000000 | 45000000 | 50000000 | 50000000 | 215000000
|  | Lessons learned are used to inform decision-making, facilitate improved performance, to track changes, risks, and assumptions, and for adaptive management | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 100000000
|  | ANNUAL TOTAL BUDGET M&E OF THE OM | 100000000 | 120000000 | 130000000 | 140000000 | 145000000 | 635000000
|  | TOTAL | 510000000 | 620000000 | 710000000 | 780000000 | 855000000 | 3475000000