## Programme Profile
Read Me First
Programme Name | Please enter the Name of the Programme (Max 20 words) See the guidance on the approach to the Programme and Project Planning | DRC Forest Program
Program Lead | Please enter the Name of the Program Lead
Program Team Member | Please list the name of Program Staff. This will be the list of staff who will have access to the Program information in the new PMEL system.
Program Duration | Please indicate the duration of Program. Minimum Duration of the Program is 5 years. | FROM: | FY2026
|  | TO: | FY2030
Programme Description | Please enter a short description of the Programme (Max 200 words) | Forest The WWF DRC Forest and Freshwater Programme aims to conserve most critical ecosystems in four landscapes, while supporting communities to thrive sustainably. Centered on high-value forests, dense forests, spawning grounds, and peatlands, the programme promotes integrated, community-led solutions that address deforestation, habitat degradation, and unsustainable resource use. The program reduces illegal logging and pressure on forests by advancing sustainable forest management, improving law enforcement, and promoting alternative energy. At the same time, it empowers farmers and fishers with knowledge, tools, and market access to adopt climate-smart practices that enhance food security and income while protecting vital habitats. The programme directly contributes to the goals of the Global Biodiversity Framework (GBF), particularly targets related to ecosystem integrity, sustainable use, and Indigenous and community rights. It also aligns with the UN Sustainable Development Goals (SDGs), notably Goals 13 (Climate Action), 15 (Life on Land), and 14 (Life Below Water), as well as WWF’s global 2030 targets on halting deforestation, restoring degraded habitats, and enabling sustainable livelihoods. With a focus on local ownership, inclusive governance, and long-term resilience, the Forest and Freshwater Programme is building a future where nature and people thrive together across DRC’s most ecologically significant landscapes.
Program Focus / Focal Area | Please select one or more Conservation and/or Human well being Focus areas that your program will be focusing on. Please make sure this is a subset of what's selected in the OSP.
Geographic Scope (Landscape) | Please list all the operational land/seascapes that are within the scope of the Program. For each land/seascape, provide short description of why the scape is critical in the context of this Program (max 200 words per land/seascape). Example: Name of the land/seascape: Description max 200 words. All land/seascapes must must apply ESSF. Guidance on landscape definition is here | Name of land/seascape | Description (Max 200 words)
|  | Salonga Landscape | The Salonga landscape encompasses one of the largest intact blocks of lowland forest in the Congo Basin and as such, is of exceptional importance for biodiversity, CO2 sequestration and the stabilization of hydrological systems at both regional and global levels. The size and integrity of forest, with its extensive network of river systems provides secure habitat for forest elephants, bonobos, Congo peacocks, bongos, giant pangolins and eight other species of diurnal primates, with high numbers of bird and freshwater fish species as well. At the centre of the landscape and occupying over a third of our area of intervention, is the Salonga National Park (33,676 km2), the largest national park in Africa, and the third largest tropical forest park in the world. The Park is divided into southern (17,323 km2) and northern (16,353 km2) blocks, separated by a corridor approximately 45 km wide. The Park was declared a UNESCO World Heritage Site in 1984, and reclassified as one of the sites in danger in 1999.
|  | Virunga Landscape | Our zone of intervention in the Virunga landscape is located in the province of North Kivu, along the western border of Virunga National Park, the first national park created in Africa, famous for the iconic mountain gorilla and also home to the eastern lowland gorilla and chimpanzee. It is an area of rich faunal biodiversity, with 210 mammalian species, 21 of which are endemic to DRC, and over 700 species of birds, including several endemics. The region lies within the Albertine Rift, has volcanic mountains and rugged terrain with average slopes of greater than 15%. The province itself, an area of 59,483 km2, has a population of approximately 8.9 million inhabitants spread over six territories: Beni, Lubero, Masisi, Nyiragongo, Rutshuru, and Walikale. The agricultural sector is of paramount importance, providing nearly six out of ten jobs. Rural communities depend highly on access to natural resources for their livelihoods, and supplying the demand from urban areas for products including charcoal and bush meat is placing unsustainable pressure on the environment and wildlife.
|  | Lacs Tumba-Mai Ndombe | The Lacs Tumba-Mai Ndombe landscape lies along the western border of the DRC, and includes one of the largest wetlands in the world. In the northern zone, there are varied forest stands including swamp forests on peatland, limbali forests and secondary forests. The wetland ecosystem provides important bird habitat and was designated as a Ramsar Site in 2008. The diverse ecosystems are home to emblematic and endemic species of fauna, including large mammals, reptiles, amphibians and fish. There are also high densities of two threatened species of African apes, chimpanzees (Pan troglodytes) and bonobos (Pan paniscus), as well as forest elephants (Loxodonta cyclotis), hippopotamus (Hippopotamus amphibius), approximately 16 species of diurnal monkeys, seven species of duikers, and leopards. There are four protected areas within the landscape: the Ngiri Triangle Nature Reserve, the Tumba Lediima Reserve, the Eala Botanical Garden and the Mabali Scientific Reserve. The first three are managed by the Institut Congolais pour la Conservation de la Nature (ICCN) and the last by the DRC Ministry of Scientific Research. There are also community forest concessions of which 6, covering 14,900 ha, have been set up with the primary objectives of conservation and bonobo ecotourism (Malebo area, located in the Bateke-Nord chiefdom). The Malebo area contains some of the highest densities of bonobos recorded (0.79 bonobo/km²). The landscape is home to more than two million people, with almost half resident in the city of Mbandaka to the north, and the remainder in smaller towns (Lukolela, Makanza, Bikoro, Bomongo, Inongo, Kwamouth, Bolobo, etc.) and villages situated along the rivers and lakes. Farming, fishing, hunting, and collecting non-timber forest products (NTFPs) are the main sources of income for rural communities.
|  | Itombwe | Itombwe landscape is based in Bukavu, the largest city in the province of South Kivu. Areas of concern to conservation efforts include the Natural Reserve of Itombwe (RNI), located at the western escarpment of the Albertine Rift, at the northern end of Lake Tanganyika. The RNI occupies an area of 5,732 km2 in the Itombwe Massif, which is part of the African Rift Lakes Region, one of the 35 global priority places under the WWF Global Priority Framework (GPF). Flagship species in the region are the lowland gorilla, chimpanzee, and a small population of forest elephants among other protected species in the DRC. The reserve has been identified as a site of significant importance for the conservation of threatened and endemic birds, amphibians, and various endangered large mammals. There are approximately 1,182,000 inhabitants in the province, who are very unevenly distributed: there is a high concentration in the eastern part, along the main roads, shores and low slopes near Lake Tanganyika. This is where the major urban centres such as Luvungi, Sange, Uvira, Nundu, Baraka, are located. The largely rural population is dependent on subsistence agriculture and exploitation of natural resources. There is a high level of insecurity in the region due to armed militia groups
|  | Luki Project Site | The Luki project site centres in and around the Luki Biosphere Reserve (RBL), which was created in 1976, and is recognized by UNESCO. The 33,000 ha reserve is a community protected area in the larger Mayombe forest ecosystem, located in the province of Kongo Central. The presence of the Central African chimpanzee (Pan troglodytes troglodytes) in the Reserve was recently confirmed. The Reserve is the only remaining forested area without significant degradation, as the province is relatively small and densely populated. There are two large cities, Boma and Matadi, and the area is within a day’s travel to Kinshasa. As a result, forests surrounding the reserve have been decimated both by agricultural expansion and harvesting for timber and charcoal production.
Thematic Scope (Practices) | Please list all the thematic that are relevant to the scope of the OSP. (Choice: Finance & Administration, Fundraising, Communications, P&C, Partnership, PMEL, etc.). For each theme, provide short description of why the theme is critical in the context of the OSP (max 200 words per theme). Example: Name of the theme: Description max 200 words. See Guidance by PPMS Step - Element 1.2 | Name of Thematic Scope | Description (Max 200 words)
Forest

## Situation Analysis
Read Me First
Political | Please enter the concise analysis (narrative) of context and trends (political, social, economic, climate & environmental, and institutional) in country that has effects on the scope of the Programme. Depending on the nature of the program, some context may be more relevant than the others. (See Guidance by PPMS Step - Element 1.3, and IUCN-CMP Unified classification of Threat 2.0s) | The political situation in the target landscapes reflects a variety of dynamics depending on local realities. In the Virunga region, political complexity remains high due to persistent security tensions. The DRC government has instituted a state of siege in conflict-affected provinces, particularly North Kivu, accompanied by significant security, judicial, administrative and constitutional reforms. The Disarmament, Demobilization, Reintegration and Stabilization Program (PDDRC-S) supports this security dynamic. However, the reform of the Independent National Electoral Commission (CENI) in 2022 has raised concerns about possible electoral tensions. On the other hand, the DRC's active participation in the Nairobi and Luanda peace processes underlines a commitment to long-term stability in the east of the country. In comparison, the Lac Tumba Mai-Ndombé landscape presents a relatively stable and peaceful provincial political context, supported by innovative policies, particularly in terms of peatland and biodiversity preservation. This stability is accompanied by a recent improvement in respect for the rights of indigenous peoples, thanks to the enactment of specific laws reinforcing their protection. Similarly, in the Mayombe Mangroves landscape, the political framework is strengthened by provincial autonomy established by the law on the free administration of the provinces. This autonomy encourages local management in key areas such as the environment, land and energy. WWF plays a key role in working closely with the authorities and stakeholders to ensure effective implementation of environmental policies. Finally, in the Salonga National Park, sustained efforts are being made to strengthen governance and security. Particular emphasis is placed on the application of a robust environmental and social framework, with the overriding aim of preventing human rights abuses and ensuring the sustainable and respectful management of the park's resources.
Social |  | In the Virunga region, complexity remains high due to persistent insecurity for over 30 years, exacerbated by the activities of rebel groups such as the M23. The provinces of North and South Kivu are experiencing massive internal population displacements, severe food insecurity, and widespread human rights violations, including sexual violence and indiscriminate shelling. This major humanitarian crisis continues to weigh heavily on peace efforts, despite regional initiatives such as the Nairobi and Luanda processes, and government reforms aimed at stabilizing eastern DRC. In contrast, the Lac Tumba Mai-Ndombé landscape displays a diverse and relatively stable social framework, inhabited by a cultural mosaic composed mainly of farmers, hunters, fishermen and gatherers. Although the precise representation of indigenous populations is uncertain, their recent recognition thanks to new legislation bears witness to a positive evolution in the protection of their rights. Large towns such as Inongo and Mbandaka are major socio-economic hubs, with local populations heavily dependent on water resources. The Mayombe Mangrove landscape, on the other hand, presents a mono-ethnic context mainly dominated by ethnic Kongo groups (Yombe, Woyo, Asolongo and Mboma), living in harmony in an urban ano-rural setting. This cultural homogeneity contributes to a stable political environment, facilitated by provincial autonomy established by the law on the free administration of the provinces, which enables effective local management, particularly in the environmental field. Finally, in the Salonga National Park, current efforts are focused on strengthening governance and environmental and social security. Significant action is being taken to prevent human rights abuses and ensure sustainable management of the park's natural resources, despite the challenges posed by the region's isolation and logistical complexity.
Economic |  | The Virunga region remains marked by chronic instability due to the prolonged presence of rebel groups and the illicit exploitation of its abundant natural resources. The provinces of North and South Kivu are rich in precious minerals such as coltan, gold, cassiterite and wolframite, highly prized resources that fuel a complex clandestine trade involving regional and international players. This illegal trade deprives the Congolese state of substantial revenues, while indirectly financing armed conflict. Violent clashes also lead to massive population displacement, exacerbating a major humanitarian crisis characterized by serious human rights violations. In contrast, the Lac Tumba Mai-Ndombe landscape features a local economy dominated by agriculture and fishing, which are the main sources of income for the communities. Despite the presence of largely inactive industrial logging concessions, artisanal and illegal logging and the growing production of charcoal represent major economic and environmental challenges for this region. In the Mayombe Mangrove landscape, the state remains the main employer, while the local economy is essentially based on agriculture, fishing and small-scale trade. However, the lack of opportunities is driving many young people into unsustainable activities such as illegal logging and charcoal-making, threatening the natural resources of the protected areas. Agricultural products such as cocoa, palm oil, coffee, cassava, bananas and corn are important economic assets. Finally, the Salonga National Park is pursuing its efforts in terms of environmental and social governance to ensure sustainable management, despite significant logistical challenges linked to geographical isolation. Targeted initiatives aim to strengthen the protection of natural resources while guaranteeing respect for human rights.
Climate & Environmental |  | The Virunga region remains marked by chronic instability, exacerbated by the presence of rebel groups and the illicit exploitation of its abundant natural resources. The provinces of North and South Kivu, rich in strategic minerals such as coltan, gold and cassiterite, suffer the effects of a complex clandestine trade involving regional and international players. This illegal trade directly fuels armed conflict, while depriving the Congolese state of vital financial resources. In addition, the effects of climate change are aggravating the situation, leading to catastrophic flooding, mass displacement and increased pressure on already fragile local communities. This dynamic also contributes to the recruitment of young people into armed groups, fuelling a vicious circle of violence and poverty. By comparison, the Lac Tumba Mai-Ndombé landscape is characterized by a predominantly agricultural and fish-farming economy but is facing increasing pressure on its forest resources. Rapid deforestation, largely due to artisanal logging and charcoal production, threatens the integrity of the vast rainforests and peatlands, essential for climate regulation. The environmental situation is worrying, with deforestation rates well above the national average, jeopardizing the region's unique biodiversity. In the Mayombe Mangrove landscape, the state remains the main employer, but local economic activities remain limited, pushing young people towards unsustainable practices such as charcoal-making and illegal logging. The hot, humid equatorial climate exacerbates environmental vulnerability, and unsustainable agricultural practices and recurrent bush fires threaten forest, savannah and aquatic ecosystems. Finally, in the Salonga National Park, despite its geographical isolation and the associated logistical challenges, initiatives continue to strengthen environmental and social governance to ensure the sustainable protection of its exceptional biodiversity, while ensuring respect for the rights of local populations.
Institutional |  | The Virunga region continues to face persistent instability, amplified by the presence of armed groups and the illegal exploitation of strategic natural resources. The provinces of North and South Kivu, rich in essential minerals such as coltan, gold and cassiterite, are subject to a complex clandestine trade involving regional and international players, which finances conflicts and impoverishes the Congolese state. The situation is exacerbated by climate change, illustrated by recurrent large-scale flooding such as that which recently occurred in South Kivu province. Faced with these challenges, initiatives such as the Priority Action Plan (PAP 2025) in North Kivu and the Provincial Development Plan (2024-2028) in South Kivu are being implemented with the support of international partners to improve living conditions and strengthen the resilience of local communities. In the Lac Tumba Mai-Ndombe landscape, shared between the Equateur and Mai-Ndombe provinces, the dominant economic activities are agriculture and fishing, which play a key role for local communities. However, artisanal logging and the growing production of charcoal represent significant environmental pressures. A decentralized institutional structure, comprising provincial governments, provincial assemblies and local authorities, collaborates with institutions such as the Institut Congolais pour la Conservation de la Nature (ICCN) to ensure sustainable management of natural resources. The Mayombe Mangrove landscape, located entirely within the province of Kongo Central, benefits from a provincial administration structured around a governor and a provincial assembly. Despite this favorable institutional context, limited economic opportunities are driving young people towards the unsustainable exploitation of natural resources. The State and various stakeholders, notably the ICCN, the Local Steering Committee (CLP) and civil society, are working together to ensure the sustainable management of natural resources. Finally, the Salonga National Park is pursuing its environmental and social protection efforts, despite major logistical and geographical constraints. Targeted initiatives are being deployed to ensure the conservation of biodiversity and the protection of local communities' rights.

## Stakeholder Analysis
| Stakeholder Name | Stakeholder Description | Stakeholder Type | Engagement Stage (planning, Implementation, MEL) | Engagement methods & strategies | Due Diligence (Y/N)
READ Me First | Please list key groups of stakeholders (people and organizations) who will be influenced by, have an impact on, or will help implement conservation to engage during the Programme planning, implementation, monitoring, and learning. Max 20 words. See Guidance by PPMS Step - Element 1.4 | Please briefly explain the significance of engaging with the stakeholder, and what you expect from the effective engagement. max 200 words | Please indicate the type of stakeholders (individual or organization): - Indigenous People & Local Communities - Civil Society Organization - Government's / Public Sector Organization - Companies / Private Sector - Universities / Research Organization - Other | Please indicate what stage each stakeholder group will be engaged - Programme planning, implementation, M&E, and Learning, etc. | Please describe how each stakeholder group will be engaged. Make sure that stakeholders will have regular access to the Programme information and, as appropriate, are aware of complaints procedures and feedback mechanisms. | For corporate & philanthropic partners (major donors, trusts, and foundations), please indicate if the due diligence is already conducted or not. For Other stakeholders, put NA. Corporate Partnership Rules & Guidelines Philanthropy Due Diligence
| ACUCOBA | Association of farmers from the BATANGI and BAMATE communities | SHOW JUMPING | Designing, Planning, implementation and monitoring | Service Agreement. Discussion of different types of restoration for different kinds of land use. | Yes
| APLORERU | Association of Local Nurserymen for the Reforestation of Rusthuru | SHOW JUMPING | Designing, Planning, implementation and monitoring | Service Agreement. Discussion of different types of restoration for different kinds of land use. | Yes
| ASPA | Action Solidaire pour la Protection des Abeilles (Solidarity Action for the Protection of Bees) | SHOW JUMPING | Planning, implementation and monitoring | Service agreement. Discussion on the promotion of the honey value chain | Yes
| CEMADI | Center for Managerial Education for Integral Development | SHOW JUMPING | Designing, Planning, implementation and monitoring | Service Agreement. Discussion on the promotion of the honey value chain | Yes
| CENED | Center for Nutritional and Environmental Education for Development | SHOW JUMPING | Designing, Planning, implementation and monitoring | Service Agreement. Discussion of different types of restoration for different kinds of land use. | Yes
| CICEKI | Complexe d'initiatives des Cultivateurs du Kivu | SHOW JUMPING | Designing, Planning, implementation and monitoring | Service Agreement. Discussion of different types of restoration for different kinds of land use. | Yes
| COOPAL | Lubero Planters' Cooperative | SHOW JUMPING | Designing, Planning, implementation and monitoring | Service Agreement. Discussion in support charcoal value chain | Yes
| CRRDC | Red Cross Comité provincial du Nord-Kivu | Government Agency | Designing, Planning, implementatio n and monitoring | MoU, Establishing grievance and redress mechanism | Yes
| FODE | Front Opérationnel de Défenseurs des Ecosystèmes Ecologiques | SHOW JUMPING | Designing, Planning and implementation | Service Agreement. Discussion of different types of restoration for different kinds of land use. | Yes
| INITIAM | Enhanced Intelligent Technology Initiative | SHOW JUMPING | Implementation and monitoring | Service Agreement. | Yes
| ONDE | Organization of Naturalists for the Defense of the Environment | SHOW JUMPING | Designing, Planning, implementation and monitoring | Service Agreement. Discussion of different types of restoration for different kinds of land use. | Yes
| PAEDE | Support Program for Farmers and Breeders for Endogenous Development | SHOW JUMPING | Implementation | Service Agreement | Yes
| RAPNAV | Network of Associations for the Protection of Nature around Virunga | Network CSO | Designing, Planning, implementation and monitoring | Service Agreement | Yes
| PIDP | Integrated Program for the Development of the Pygmy People in Kivu | SHOW JUMPING | Implementation | Service Agreement | Yes
| North Kivu Civil Society | Société civile Force Vive du Nord-Kivu | Network CSO | Implementation | MoU. Advocacy | Yes
| UGADEC | Union of Conservation Associations Gorillas for Community Development in Eastern DR Congo | Network CSO | Implementation | MoU. Supporting Community forest concessions | Yes
| APAB | Batwa Indigenous Peoples Association | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| CAFEPADE | Caisse des femmes paysannes pour le développement | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| CBFC | Consortium Brave Femmes du Congo | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| Young Methodists |  | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| SOCEARUCO | Environmental and agrarian civil society of Congo | Network CSO | Designing, Planning, implementation and monitoring | MoU. Advocacy | Yes
| TRAFEED | Networking with Federations of Women and Children in Need | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| NVD |  | Society civil organization | Planning & implementation | NVD, being an Executing Agency under the PIREDD plateau project, is involved in the planning and implementation of activities, regularly participating in project meetings. | Yes
| GI-Agro |  | Society civil organization | Planning & implementation | CIAPAFED, being an Executing Agency within the PIREDD plateau project, is involved in the planning and implementation of activities, regularly participating in project meetings. | Yes
| CIAPAFED |  | Society civil organization | Planning & implementation | Quarterly meetings, reporting, sharing action plans, (how we work with partners) | Yes
| Mbou Mon Tour, |  | Society civil organization | implementation |  | Yes
| Private companies - SOGENAC (cattle rearing) |  | private sector | Planning & implementation
| ERA Congo (carbon credit) |  | private sector | Learning
| SODEFOR (logging) |  | private sector | Learning
| Local communities managing CFCL |  | Local communities | implementation
| Academics and scientists monitoring peatlands and forests - University of Gembloux |  | University | Learning
| Univ of Kisang ani, Univ Mbandaka |  | University | Learning
| Governorates |  | Public sector | Planning
| ICCN, |  | Public sector | Planning & implementation
| RSM |  |  | Learning
| Provincial and territorial administrations |  | Public sector | Planning & implementation | The provincial and territorial administration participates in the implementation of PIREDD project activities, and is involved in monitoring.
| RF Norway |  | Society civil organization | Learning
| ERAIFT |  | Haute Ecole and Research | Planning & implementation | Involved in the planning and implementation of Alliance Verte, EU-Luki, PASAGAR and other projects
| ACODED/AMAR |  | NGO | implementation | Stakeholder in the implementation of the Alliance Verte project
| ADEV |  | NGO | implementation | Stakeholder in the implementation of the Alliance Verte project
| Caritas Matadi |  | NGO | implementation | Stakeholder in the implementation of the Alliance Verte project
| CCPN |  | NGO | implementation | Stakeholder in the implementation of the Alliance Verte project
| ULB-Coopération |  | INGO | Research & Development | Implements research and development projects in the landscape
| UKV |  | University | Training and Research | Stakeholder in the Alliance Verte project
| ISDR- Kinzau and ISEA-Tshela |  | Universities | Training and Research | Stakeholder in the Alliance Verte project
| Provincial Government |  | Public institution | implementation | Monitoring and evaluation of project implementation in the landscape
| Decentralized and centralized territorial entities |  | Public institution | Monitoring and evaluation | Monitoring and evaluation of project implementation in the landscape
| CARG |  | Farmers' civil society | Monitoring and assessment | Monitoring and evaluation of project implementation in the landscape
| ICCN |  | Public institution | Planning | Participates in planning projects in the Marine Park
| CLP |  | Public institution | Planning | Participates in project planning at the Luki Reserve
| CLDs |  | Farmers' civil society | Implementation | Project beneficiaries in the landscape

## Focus & Goals
| Conservation Focus | Relevant OSP Goals | Key Assumptions
READ Me First | Please list each conservation focus / focal interest. Biodiversity Focal Interests can be focal species or habitats/ ecological systems. Human Wellbeing Focal Interests can be those component of human wellbeing affected by the status of biodiversity focal interests (material and non-material benefits obtained by ecosystem. Please ensure that focus / focal interest is a subset of those selected under the OSP. You may define further detail. | Based on the focus / focal interest selected, Please select the OSP Goal that your program is aiming to deliver. Please list the OSP Goal statement. | Please identify the key assumptions that underpin the logical sequences linking strategies to one or more focal interests. Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment.
Example | Coral Reef in Beta seascape. | Live coral reef covers at least 25% of the reef within the priority coastal seascapes in country Y. | WWF or its partner organization can monitor the live coral reef coverage in the coastal Beta seascape with proper funding.
| High-value conservation (HCV) forest | By 2035, at least 90% of the targeted high-value conservation forest in targeted landscapes is kept intact compared to the 2025 baseline. | 1. No sudden environmental disturbances that could lead to additional clearance of HCV forest surface
| Dense Forest | By 2035, dense forests in the targeted landscapes is maintained 100% intact in the targeted PAs, and 95% in the non-PAs compared to 2025 | 1. No sudden environmental disturbances that could lead to additional clearance of dense forest surface

## Narrative TOC
Read Me First
Narrative Theory of Change | Please articulate the Theory of Change in Narrative. A Theory of Change (ToC) should be underpinned by evidence of the logic. Articulate the causal pathway that leads from the current to the desired situation, describing how the Programme activities will deliver the envisioned Programme Outputs and Outcomes, and ultimately the Programme/OSP Goals. Key risks associated with the key assumptions along the Theory of Change to achieve its Programme Outcomes and Goals must be articulated. A risk is potential future event that may impact achievement of goals. Assumptions are explicit statements of what the CO assumes is true. The logical sequences must link activities to one or more focal interests as reflected in a theory of change. Assumptions may also express how external variables may influence the achievement of results. Max. 500 words See Guidance by PPMS Step - Element 2.1 | The Forest and Freshwater Programme in DRC seeks to safeguard critical ecosystems, secure biodiversity, and improve the livelihoods of local communities by addressing the root causes of forest degradation and freshwater ecosystem decline while ensuring an inclusive conservation agenda. This theory of change is premised on the belief that sustainable conservation outcomes can be achieved by simultaneously strengthening governance and enforcement, supporting community-driven solutions, and improving practices in agriculture and forestry. WWF will support the development of sustainable forest management plans and policies, alongside improved law enforcement through partnerships with authorities and transboundary collaboration. These efforts will contribute to reducing illegal logging and improve forest monitoring. Better enforcement enables stronger market regulation, curbing overexploitation of timber, leading to maintaining the integrity of high conservation value forests and dense forest cover. Community engagement and participation is central. Through awareness-raising and capacity-building, farmers adopt sustainable practices that reduce shifting cultivation, and drainage of lowland areas. Adopting improved practices will contribute to the protection of forest, while also enhancing food security and income. Other support to increase adoption of best practices will include training, improved inputs, pilot farms, and market access. The programme will promote alternative energy solutions, such as improved cookstoves, charcoal kilns, and biogas, to relieve pressure on forests while supporting fuelwood plantations and advocating for favourable energy taxation. As communities adopt cleaner energy, reliance on wood fuel will decrease, reducing deforestation and emissions. The programme also invests in ecosystem restoration, using reforestation, assisted natural regeneration, and incentives like Payment for Ecosystem Services. These efforts will create local benefits while restoring degraded areas. Empowering communities to manage natural resources is key. WWF will support the registration of community forest concessions, development of inclusive management plans, and creation of accountable governance structures. This secures land rights, reduces conflict, and ensures communities, especially women and IPLC, lead conservation and development efforts. These strategies reinforce one another. Strong governance reduces external pressures, improved practices protect habitats and sustain livelihoods, and clean energy reduces forest dependence
Opportunities for Innovation | Please articulate priority areas of innovation and research where needed. Innovation and Research activities must be included in the Programme Implementation Plan, Max. 500 words

## Program M&E Plan
Programme M&E plan | Program | Prog_ID | Relevant Geographic Scope | Focus | Priority Threats / Other Factors | Result ID | Result Name | Goal, Outcome and Output Statement | Indicator | Description | Means of Verification (Source of Data) | Data Collection and Analysis Methodology | Frequency of Measurement | Key Assumptions & Risks | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Location | Responsible
| Forest Conservation | 2 |  | Forest (High-value conservation (HCV) forest) |  | 2.1 |  | By 2035, at least 90% of the targeted high-value conservation forest in targeted landscapes is kept intact compared to the 2025 baseline. | % of HCV forest that is kept intact | Forest intactness refers to the state of a forest that is largely free from significant human disturbance and fragmentation, retaining its natural structure and function Target forest/habitats include (Services, forest clearings, baïs) | Clearing and other HCVs, monitoring database | Data collection through camera traps and permanent presence of biomonitoring teams: Records on the size of the sites, the species present, the number of individuals visiting per species, the period of visit of species, etc. | Annual | 1. No sudden environmental disturbances that could lead to additional clearance of HCV forest surface | 80% |  |  |  |  | 90%
[9 empty] | Rate of use of HCV forest clearings of wildlife | This indicator gives the viability of the forest clearing | Clearing and other HCVs, monitoring database | Data collection through camera traps and permanent presence of biomonitoring teams: Records on the size of the sites, the species present, the number of individuals visiting per species, the period of visit of species, etc. Rate of use: Average number of visits per species / day over one year | Annual |  | TBD
| Forest Conservation | 2 |  | Forest (Dense Forest) |  | 2.2 |  | By 2035, dense forests in the targeted landscapes is maintained 100% intact in the targeted PAs, and at least 95% in the non-PAs compared to 2020 | Number of hectares of targeted forests maintained intact in PAs | Ha of dense forests measured in targeted PAs | Land cover monitoring data | Remote sensing | Endline | 1. No sudden environmental disturbances that could lead to additional clearance of dense forest surface | Salonga : 335000 Mayombe/Luki/PMM: 109000 |  |  |  |  | Salonga : 335000 Mayombe/Luki/PMM: 109000
[9 empty] | Number of ha of targeted forests maintained intact in Non-PAs | Ha of dense forests measured in targeted NON PAs | Land cover monitoring data | Remote sensing | Endline |  | LTMN :334471 Salonga : 248530 Mayombe/LukiTBD Virunga/Itombwe: 320000 |  |  |  |  | LTMN :334471 Salonga : 300000 Mayombe/Luki: Virunga/Itombwe: 320000
[9 empty] | Number of tone of above ground carbon dioxide (Co2) Stocked | Carbon stock in above ground biomass in targeted areas | Carbon stock study database | Field based study combined with remote sensing | Annual |  | TBD
| Cross Cutting | 1 2 3 |  | Human Wellbeing |  | 4.1 |  | By 2035, the wellbeing of targeted communities in targeted landscapes is improved by 20% relative to 2025 baseline. | Wellbeing score | Wellbeing includes materials for good life, social cohesion, rights, access to natural resources/5 categories of wellbeing | Wellbeing survey data (with linked database) | Socioeconomic survey related to wellbeing aspects supported. | Endline | There are no major conflicts, displacements, or political interference that would disrupt livelihoods, services, or community cohesion. | LTMN : 0.3 Salonga :0.52 Mayombe/Luki: Virunga/Itombwe |  |  |  |  | LTMN : 0.35 Salonga : 0.55 Mayombe/Luki: Virunga/Itombwe
Outcomes | Forest Conservation |  |  | Forest (High-value conservation (HCV) forest) | Conversion of HCV to other land uses | 2.1.1 | Zero conversion in HCV | By 2030, zero Ha of HCV forests converted to other land uses in targeted landscapes | Area (ha) of HCV mapped | Land-use plans are enforced and not overridden by economic or political interests | Land cover monitoring data Field verification | Remote sensing Field verification | Endline | Protection of HCV is not overridden by economic or political interests The law enforcement is effective in protecting the HCV forest,/ Institutional and legal enforcement capacity exists to prevent unauthorized land conversion or encroachment. Conflict between conservation vs development interest remain manageable and does affrect HCV | LTMN: 442268 Salonga: 3350000 Mayombe-Mangrove: 28 477 Vir/Itombwe:320000 | LTMN: 442268 Salonga: 3350000 Mayombe-Mangrove:28 477 Vir/Itombwe | LTMN: 442268 Salonga: 3350000 Mayombe-Mangrove:28 477 Vir/Itombwe | LTMN: 442268 Salonga: 3350000 Mayombe-Mangrove:28 477 Vir/Itombwe | LTMN: 442268 Salonga: 3350000 Mayombe-Mangrove:28 477 Vir/Itombwe | LTMN: 442268 Salonga: 3350000 Mayombe-Mangrove:28 477 Vir/Itombwe
| Forest Conservation |  |  | Forest (Dense Forest) | Land clearing for Agriculture | 2.2.1 | Forest cleared for agriculture reduced | By 2030, area of forest cleared for agriculture in the targeted landscape is reduced by at least 30%, compared to the 2025 baseline. | Area (ha) of forest converted for agricultural use annually |  | Land cover monitoring data Field verification | Remote sensing Field verification | Endline | 1. Farmers practice sustainable yield-boosting methods that reduce the need to clear new land. 2. Farmers will not see increased yield as an incentive to expand their lands 3. Climate, economic and market situations remain stable | LTMN: TBD Salonga: TBD Mayombe-Mangrove:95, 19 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:80 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:70 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:60 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:66,49 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:66,49 Vir/Itombwe: TBD
| Forest Conservation |  |  | Forest (Dense Forest) | poor/unsustainable agricultural practice | 2.2.2 | Best agricultural practices supported | By 2030, at least 80% of targeted farmers supported in priority landscapes use best agricultural practices. | # of farmers applying low-carbon agricultural techniques | Targeted farmers include farmers of cassava, rice, etc. Best practices include practices follow Deforestation and Carbon Free -DCF program, deforestation, Nature positive practices, etc. | Farm Survey database | Farm Survey | Annually | Other external factors, such as climate or market forces, will not affect the production and prices in a manner that farmers don’t see the benefits of good practices The community and agribusiness will accept changing their farming practice to sustainable yield boosting practices Farmers will not see increased yield as an incentive to expand farming land | LTMN: 1046 Salonga:10000 Mayombe-Mangrove:200 Vir/Itombwe:28 974 | LTMN: 1046 Salonga:1000 Mayombe-Mangrove:200 Vir/Itombwe: | LTMN: 1000 Salonga:10000 Mayombe-Mangrove:200 Vir/Itombwe: | LTMN:1000 Salonga:500 Mayombe-Mangrove:200 Vir/Itombwe: | LTMN: 1000 Salonga:500 Mayombe-Mangrove:200 Vir/Itombwe: | LTMN: 1000 Salonga:500 Mayombe-Mangrove:200 Vir/Itombwe:28 974
| Forest Conservation |  |  | Forest (Dense Forest) | Poor and/or weak governance, management, and capacities | 2.2.3 | community with management plans established | By 2030, at least 600,000 ha of community forests are established and operate with approved management plans | # of community forest with improved management with support from WWF | Define Community Forest | Community Forests database | Project Implementation activity | Annually | National and local authorities continue to support and process community forest applications within a reasonable timeframe. Management plans are formally approved by relevant government authorities. IPLC apply best management practices in managing their community forest, even after the end of the support | LTMN: 14 Salonga:06 Mayombe-Mangrove:0 Vir/Itombwe:22 | LTMN: 14 Salonga:1 Mayombe-Mangrove:0 Vir/Itombwe:0 | LTMN:5 Salonga:2 Mayombe-Mangrove:1 Vir/Itombwe:0 | LTMN: 1 Salonga:1 Mayombe-Mangrove:0 Vir/Itombwe:0 | LTMN:2 Salonga:1 Mayombe-Mangrove:0 Vir/Itombwe:0 | LTMN: 4 Salonga:1 Mayombe-Mangrove:2 Vir/Itombwe:3
| Forest Conservation |  |  | Forest (HCV, Dense Forest) | Minning, Logging, conversion to other land uses Cutting for firewood & charcoal] Artisan/industrial exploitation of wood | 2.2.4 | Habitats are restored | By 2030, 100,000 ha of targeted habitats are restored. | Hectares of habitat restored | The targeted areas include savannahs, forest, mangroves. | Restoration Database | Field restoration activity: Recording of restored area size | Annually | Relevant stakeholders and partners will take part in restoration activities Landholders and communities understand and support restoration | LTMN: 25226 Salonga:0 Mayombe-Mangrove:8722 | LTMN: 25226 Salonga:0 Mayombe-Mangrove:8752 | LTMN: 3000 Salonga:0 Mayombe-Mangrove:8786 | LTMN: 3300 Salonga:0 Mayombe-Mangrove:8792 | LTMN:3600 Salonga:0 Mayombe-Mangrove:8832 | LTMN: 38226 Salonga:0 Mayombe-Mangrove:8882
| Cross Cutting |  |  | Human Wellbeing | Human rights abuse | 4.1.1 | Conservation related complaints reduced | By 2030, the percentage of conservation related complaints related to CCO-supported conservation activities in target landscapes is reduced by at least 90%. | % of conservation related complaints related to CCO conservation activities | This will be measured on national level not on program level. Numerator: Number of conservation related complaints related to CCO conservation activities Divided by: Denominator: Number of conservation related complaints | Grievance mechanism database | Grievance mechanism system | Annually | There is confidence and trust in grievance redress mechanisms and are communities are using it to report | LTMN : 100% (10 complaints) Salonga: 100% (78 complaints) Mayombe/Luki:0% Vir / Itombwe:100% ( 7 complaints) | LTMN : 100% Salonga : 60% Mayombe/Luki:0% Vir / Itombwe: | LTMN : 80% Sal : 50% Mayombe/Luki:0% Vir / Itombwe: | LTMN : 50% Sal : 40% Mayombe/Luki:TBD Vir / Itombwe: | LTMN : 30% Sal : 30% Mayombe/Luki:TBD Vir / Itombwe: | LTMN : 10% Sal : 20% Mayombe/Luki:TBD Vir / Itombwe:10%
[9 empty] | Number of human rights violation cases by WWF's or implementing partners staff |  | Grievance mechanism database | Grievance mechanism system | Annually |  | Salonga:55 | Salonga:45 | Salonga:35 | Salonga:25 | Salonga:15 | Salonga:5
| Cross Cutting |  |  | Human Wellbeing | Weak support to conservation | 4.1.2 | Positive perception on conservation improved | By 2030, at least 80% of targeted IPLCs in CCO-supported landscapes have a positive perception towards conservation projects/ideas. | % of targeted IPLC who have a positive perception towards CCO-supported conservation projects/ ideas | This will be measured on national level not on program level. | Perception survey data | Perception Survey | Annually | Conservation efforts produce tangible social or economic benefits for IPLCs (e.g., jobs, ecosystem services, access rights) | LTMN : TBD Sal : 63% Mayombe/Luki:TBD Vir / Itombwe:58% | LTMN : Sal : 63% Mayombe/Luki Vir / Itombwe | LTMN : Sal : 65% Mayombe/Luki Vir / Itombwe | LTMN : Sal : 66% Mayombe/Luki Vir / Itombwe | LTMN : Sal : 67% Mayombe/Luki Vir / Itombwe | LTMN : Sal : 68% Mayombe/Luki Vir / Itombwe:58%
| Cross Cutting |  |  | Human Wellbeing | Poverty and lack of buy in to conservation | 4.1.3 | Students supported | By 2030, at least 20% of supported students complete primary or secondary school education | % supported primary school students that have completed their primary education |  | School Records | School Records | Annually | Parents/guardians and communities value and support education—especially for girls and IPs No major disruptions (e.g., political instability, natural disasters, pandemics) impact schooling | Salonga: 3567 | 4000 | 4500 | 5000 | 5500 | 6000
| Cross Cutting |  |  | Human Wellbeing | Poverty | 4.1.4 | Household income increased | By 2030, targeted IPLC gain at least a 10% increase in household income from WWF-supported activities compared to the 2025 baseline | Average household income of targeted IPLC | Household income could be derived from IGA value chains, tourism, etc. | Household survey data | Household survey on WWF-supported activities | Midline (only measured half way and at the end) | Markets remain stable or grow for the products/services linked to WWF-supported activities Climate and environmental conditions do not severely disrupt production (e.g., droughts, disease, flooding) | LTMN :TBD Sal :TBD Mayombe/Luki TBD Vir / Itombwe TBD
[9 empty] | Average total annual income gained by IPLC through direct employment in conservation related activities | The income that is paid to IPLC directly from conservation activities | HR salary data | HR salary checks | Annually |  | LTMN :TBD Sal :TBD Mayombe/Luki TBD Vir / Itombwe TBD
| Cross Cutting |  |  | Human Wellbeing | Poverty | 4.1.5 | Access to materials of good life improved | By 2030, the number of targeted IPLC communities in WWF-supported landscapes having access to materials of good life has increased by at least 50% relative to the 2025 baseline | % of targeted IPLC communities in the WWF-supported landscapes that have access to materials of good life | Access means the ability for the targeted group to make use of the materials. Materials of good life include portable water, health care, natural resources, food, education and traditional sites inside PAs. Communities refers to a group of people living in one village. Numerator: Number of targeted communities with access to the materials of a good life Denominator: Number of targeted communities | Community survey as well as program data (with linked database) | Community surveys and program progress reports | Annually | Communities are not subjected to conflict, displacement, or governance instability that disrupt access to basic needs or services. | Salonga : 6% | Salonga : 6% | Salonga : 6,5% | Salonga:7% | Salonga : 8% | Salonga : 9%
| Cross Cutting |  |  | Human Wellbeing | Exclusion of IPLCs Inadequate or Weak policy on Protection of IPLC rights | 4.1.6 | policies & decisions promoting IPLC rights enacted | By 2030, at least one new or revised policies or decisions promoting the rights and interests of IPLC enacted with WWF support | Number of new or revised policy or decisions promoting the rights and interests of IPLC enacted with WWF support | policies include decrees or other circular decisions | Policy and advocacy database (With validated analyses and report) | Policy and advocacy activities | Annually | The government is willing to engage with WWF and partners (incl. IPLC) in the propositions, enacting and reviewing of the policies/ decisions | LTMN :TBD Salonga Decret of CFCL : 17 Mayombe/Luki TBD Vir / Itombwe TBD
Ouputs | [5 empty] | 2.1.1.1 |  | By 2030, at least 50% of LDCs in priority landscapes are supported in sustainable agriculture. | # of households adopting sustainable agriculture practices in target areas | [5 empty] | LTMN 28312 Mayombe-Mangrove:10000 Salonga:10000 | LTMN Mayombe-Mangrove: 2000 | LTMN Mayombe-Mangrove:2000 | LTMN Mayombe-Mangrove:2000 | LTMN Mayombe-Mangrove:2000 | LTMN Mayombe-Mangrove:2000 Salonga:13500
[6 empty] | 2.1.1.2 |  | By 2027, HCV forest areas are fully mapped and demarcated in all targeted landscapes, with GIS data integrated into national or regional land-use planning systems. | Ares (Ha) of High Conservation Value forests converted to other land uses | [5 empty] | LTMN: TBD Salonga: TB Mayombe-Mangrove:95, 19 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:80 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:70 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:60 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:66,49 Vir/Itombwe: TBD | LTMN: TBD Salonga: TBD Mayombe-Mangrove:66,49 Vir/Itombwe: TBD
[6 empty] | 2.1.1.3 |  | By 2028, Formal agreements (e.g., MOUs, conservation easements, or community protocols) covering 100% of mapped HCV areas are signed with landowners, communities, or custodians. | # of MoUs signed | [5 empty] | LTMN:0 Salonga:01 Mayombe-Mangrove:0 Vir/Itombwe:0 | LTMN:3 Salonga:01 Mayombe-Mangrove:1 Vir/Itombwe:0 | LTMN:5 Salonga:01 Mayombe-Mangrove:0 Vir/Itombwe:0 | LTMN:2 Salonga:01 Mayombe-Mangrove:0 Vir/Itombwe:0 | LTMN:2 Salonga:01 Mayombe-Mangrove:0 Vir/Itombwe:0 | LTMN:2 Salonga:01 Mayombe-Mangrove:0 Vir/Itombwe:0
[6 empty] | 2.2.4.1 |  | By 2030, at least 100,000 ha of degraded areas (savannahs, forests, mangroves) are under restoration | Area (ha) of degraded ecosystems mapped and prioritized for restoration | [5 empty] | LTMN:2868 Mayombe-Mangrove:12522 Virunga-Itombwe:TBD | LTMN:2868 Mayombe-Mangrove:12522 | LTMN:2868 Mayombe-Mangrove:12522 | LTMN:2868 Mayombe-Mangrove:12522 | LTMN:2868 Mayombe-Mangrove:12522
[6 empty] | 2.2.1.1 |  | By 2030, the coverage of community monitoring activities in local community forest concessions (LCFCs) is increased by at least 20% compared with 2025. | Coverage area in LCFCs % of local community forest concessions are covered by community monitoring | [5 empty] | LTMN:TBD Mayombe-Mangrove:TBD Vir/Itombwe:TBD
[6 empty] | 2.2.1.2 |  | A forest-clearing monitoring and enforcement system is operational, with community and government participation, across all high-risk zones in the targeted landscape. | % of High-Risk Areas Covered by Patrols/ surveillence | [5 empty] | LTMN:0% Mayombe-Mangrove:20% Vir/Itombwe:55% | LTMN:10% Mayombe-Mangrove:30% Vir/Itombwe:55% | LTMN:15% Mayombe-Mangrove:40% Vir/Itombwe:60% | LTMN:20% Mayombe-Mangrove:50% Vir/Itombwe:70% | LTMN:30% Mayombe-Mangrove:60% Vir/Itombwe:80%
[8 empty] | By 2030, at least 80% of small-scale farmers in priority landscapes are trained in sustainable agriculture. | Number of training sessions conducted on sustainable agruclture | [5 empty] | LTMN:7 Salonga: Mayombe-Mangrove:4 Vir/Itombwe:TBD | LTMN:5 Salonga: Mayombe-Mangrove:4 Vir/Itombwe:TBD | LTMN:5 Salonga: Mayombe-Mangrove:4 Vir/Itombwe:TBD | LTMN:5 Salonga: Mayombe-Mangrove:4 Vir/Itombwe:TBD | LTMN:5 Salonga: Mayombe-Mangrove:4 Vir/Itombwe:TBD | LTMN:5 Salonga: Mayombe-Mangrove:4 Vir/Itombwe:TBD
[6 empty] | 2.2.2.2 |  | By 2030, Extension services or farmer field schools are operational in all priority landscapes | # of smallholder farmers actively engaged in and regularly participating in cooperative activities. | [5 empty] | LTMN:396 Mayombe-Mangrove:2 Vir/Itombwe:TBD
[6 empty] | 2.2.2.3 |  | Incentive mechanisms (e.g., inputs, market access, certification, or micro-finance) are in place to support at least 80% of targeted farmers | # of Smallholder Farmers with Access to Farming Inputs | [5 empty] | LTMN:1046 Mayombe-Mangrove:200 Vir/Itombwe:TBD Salonga:1000 |  |  |  | LTMN:6000 Mayombe-Mangrove:200 Vir/Itombwe:TBD Salonga:12500
[6 empty] | 2.2.3.1 |  | By 2030, at least 80% of Local community forest concessions will be supported by WWF and its partners to develop Sustainable Management Plans (SMPs). | # of forest management plans in place | [5 empty] | LTMN:14 Mayombe-Mangrove:0 Vir/Itombwe:22 Salonga:06
[9 empty] | Area (ha) of Local community forest concessions under sustainable management plan | [5 empty] | LTMN:TBD Mayombe-Mangrove:32000 Vir/Itombwe:0 Salonga:178424 |  |  |  |  | LTMN:TBD Mayombe-Mangrove:32000 Vir/Itombwe:0 Salonga:0
[6 empty] | 2.2.3.2 |  | By 2030, at least 30% of simplified community forest concession management plans are implemented with support from WWF and its partners | Area (ha) of community-managed forest areas under sustainable management practices | [5 empty] | LTMN:78852 Mayombe-Mangrove:0 Vir/Itombwe:341 645 Salonga178424
[6 empty] | 4.1.1.1 |  | By 2026, grievance redress mechanisms (GRMs) are established in 100% of target landscapes with annual tracking and response of cases. | % landscapres with grievance Mechanisms in place | [5 empty] | LTMN/Plateau:100% Sal : 100% Mayombe/Luki: 60% Vir / Itombwe:100% | LTMN/Plateau:100% Sal : 100% Mayombe/Luki: 80% Vir / Itombwe:100% | LTMN/Plateau:100% Sal : 100% Mayombe/Luki: 100% Vir / Itombwe:100% | LTMN/Plateau:100% Sal : 100% Mayombe/Luki: 100% Vir / Itombwe:100% | LTMN/Plateau:100% Sal : 100% Mayombe/Luki: 100% Vir / Itombwe:100% | LTMN/Plateau:100% Sal : 100% Mayombe/Luki: 100% Vir / Itombwe:100%
[9 empty] | % of reported grievances that are related to WWF work | [5 empty] | LTMN/Malebo :100% Salonga : 70% Mayombe/Luki: 30% | LTMN/Malebo :100% Salonga : 80% Mayombe/Luki: 100% | LTMN/Malebo :100% Salonga : 100% Mayombe/Luki: 100% | LTMN/Malebo :100% Salonga : 100% Mayombe/Luki: 100% | LTMN/Malebo :100% Salonga : 100% Mayombe/Luki: 100% | LTMN/Malebo :100% Salonga : 100% Mayombe/Luki: 100%
[6 empty] | 4.1.1.2 |  | By 2030, the number of Human rights violations (physical and moral violations) linked to WWF's activities in priority landscapes are reduced | Number of reported human rights violations cases associated with WWF-supported activities | [5 empty] | Salonga:55 | Salonga:45 | Salonga:35 | Salonga:25 | Salonga:15 | Salonga:5
[6 empty] | 4.1.1.3 |  | By 2030, at least 100% of ESSF flagship tools (ESIA, CGES, MGP, GBV Action Plan, Gender Analysis, HSSE Action Plan, Stakeholder Engagement Plan, and IP Engagement Plan) are developed, adopted, and implemented. | % of landscapes that have implemented 80% of their ESSF actions | [5 empty] | LTMN: 70% Sal : 70% Mayombe/Luki: 40% Vir / Itombwe:70% | LTMN: 70% Sal : 70% Mayombe/Luki: 60% Vir / Itombwe:70% | LTMN: 80% Sal : 80% Mayombe/Luki: 80% Vir / Itombwe:70% | LTMN: 90% Sal : 90% Mayombe/Luki: 100% Vir / Itombwe:80% | LTMN: 95% Sal : 95% Mayombe/Luki: 100% Vir / Itombwe:90% | LTMN:100% Sal : 100% Mayombe/Luki: 100% Vir / Itombwe:100%
[6 empty] | 4.1.1.4 |  | By 2030, Salonga ecoguards are trained on human-right based approaches to law enforcement | Number of eco-guards trained in human rights-based approaches to law enforcement | [5 empty] | Sal : 210 Mayombe/Luki: 60 | Sal :62 Mayombe/Luki: 15 | Sal : 0 Mayombe/Luki: 0 | Sal : 50 Mayombe/Luki: 0 | Sal : 30 Mayombe/Luki: 0 | Sal :30 Mayombe/Luki: 0
[9 empty] | % of trained eco-guards who demonstrate knowledge of human rights-based approaches in law enforcement | [5 empty] | Salonga 80% | 82% | 85% | 90% | 95% | 100%
[6 empty] | 4.1.2.1 |  | By 2020, studies or surveys on the negative perception of IPs/LCs living in the SNP and its periphery with regard to conservation are carried out. | Number of perception studies or surveys conducted | [5 empty] | TBD | TBD | TBD | TBD | TBD | TBD
[6 empty] | 4.1.3.1 |  | By 2030, at least 5% of pupils in SNP (Monkoto & Yokelelu) will be supported through the provision of school supplies. | Number of pupils provided with school supplies | [5 empty] | Salonga: 3567 | 4000 | 4500 | 5000 | 5500 | 5500
[6 empty] | 4.1.4.1 |  | By 2030, at least 50% of households in targeted IP/LC communities are actively participating in at least one WWF-supported innovative income-generating activity (PES, biodiversity credits, LCFCs, or micro-enterprises). | % of benefit sharing mechanisms that are functional | [5 empty] | LTMN:16 % Sal : TBD Mayombe/Luki: TBD Vir / Itombwe:TBD | LTMN:16 % Sal : TBD Mayombe/Luki: TBD Vir / Itombwe:TBD | LTMN:20 % Sal : TBD Mayombe/Luki: TBD Vir / Itombwe:TBD | LTMN:30% Sal : TBD Mayombe/Luki: TBD Vir / Itombwe:TBD | LTMN:45 % Sal : TBD Mayombe/Luki: TBD Vir / Itombwe:TBD | LTMN:50 % Sal : TBD Mayombe/Luki: TBD Vir / Itombwe:TBD
[6 empty] | 4.1.4.2 |  | By 2030, at least 36 structures are supported to implement Payment for Ecosystem Services (PES) schemes | % of target structures supported to implement PES scheme | [5 empty] | LTMN :4 Mayombe/Luki:3 Vir-Itombwe:19 | LTMN : 3 Mayombe/Luki:0 Vir-Itombwe:0 | LTMN :0 Mayombe/Luki:0 | LTMN :0 Mayombe/Luki:0 | LTMN :0 Mayombe/Luki:0 | LTMN :1 Mayombe/Luki:0 Vir-Itombwe:1
[6 empty] | 4.1.4.3 |  | By 2030, WWF facilitates partnerships with at least 120 LCFCs, OECMs, and private sector entities to promote the delivery and sustainability of ecosystem services in target landscapes. | Number of partnership agreements signed or established | [5 empty] | LTMN :0 Mayombe/Luki:1 | LTMN :2 Mayombe/Luki:0 | LTMN :1 Mayombe/Luki:0 | LTMN :0 Mayombe/Luki:0 | LTMN :0 Mayombe/Luki:0 | LTMN :0 Mayombe/Luki:0
[6 empty] | 4.1.4.4 |  | By 2030, partnerships is established with at least three operators to facilitate fund transfer for PES and other credit mechanisms. | Number of partnerships entered with operators to facilitate funds transfer to community | [5 empty] | LTMN :1 Sal : 1 Mayombe/Luki: 1 Vir / Itombwe:1 |  | LTMN :1 Sal : 1 Mayombe/Luki: 1 Vir / Itombwe:1 |  |  | LTMN :1 Sal : 1 Mayombe/Luki: 1 Vir / Itombwe:1
[9 empty] | Number of people receiving funds from established operators | [5 empty] | LTMN :0 Sal : 0 Mayombe/Luki: 0 Vir / Itombwe:0
[6 empty] | 4.1.4.5 |  | By 2030, at least 5 value chains (rice, charcoal, honey, etc.) are developed with market access in priority landscapes. | Number of value chains developed | [5 empty] | LTMN :0 Sal : 3 Mayombe/Luki: 2 Vir / Itombwe:2 | LTMN :0 Sal : 1 Mayombe/Luki: 1 Vir / Itombwe:0 | LTMN :1 Sal : 1 Mayombe/Luki: 0 Vir / Itombwe:0 | LTMN :1 Sal : 1 Mayombe/Luki: 0 Vir / Itombwe:0 | LTMN :1 Sal : 0 Mayombe/Luki: 1 Vir / Itombwe:0 | LTMN :1 Sal : 1 Mayombe/Luki: 0 Vir / Itombwe:0
[6 empty] | 4.1.5.1 |  | By 2030, at least 4 water points (e.g., boreholes, wells) are constructed or rehabilitated in underserved IPLC communities within WWF-supported landscapes. | # of water sources protected | [5 empty] | Mayombe-Mangroves: 2 Salonga: 4 | Mayombe-Mangroves: 2 Salonga: 1 | Mayombe-Mangroves: 1 Salonga: 1 | Mayombe-Mangroves: 2 Salonga: 1 | Mayombe-Mangroves: 1 Salonga: 1 | Mayombe-Mangroves: 0 Salonga: 1
[6 empty] | 4.1.5.2 |  | By 2030, livelihood support is provided to at least 50000 IP&LC communities in priority landscapes | % of ragetet IP &LC households provided with livelihood support | [5 empty] | Virunga: 28974 |  |  |  |  | Virunga: 28974
[6 empty] | 4.1.5.3 |  | By 2030, at least 15 solar-powered lighting or energy systems are installed in schools, health centers, or public spaces in priority villages. | Number of functional renewable energy installations | [5 empty] | LTMN :0 Salonga: 2 Mayombe/Luki: 0 | LTMN :0 Salonga: 2 Mayombe/Luki: 0 | LTMN :0 Salonga: 2 Mayombe/Luki: 0 | LTMN :0 Salonga: 2 Mayombe/Luki: 0 | LTMN :0 Salonga: 2 Mayombe/Luki: 0 | LTMN :0 Salonga: 2 Mayombe/Luki: 0
[6 empty] | 4.1.5.4 |  | By 2030, all targeted IPLC communities define their "priorities of good life" through a participatory assessment, + these are integrated into local development planning. | Number of community-defined development plans incorporating “good life” priorities | [5 empty] | LTMN :14 Mayombe/Luki: 0
[6 empty] | 4.1.6.1 |  | By 2030, at least 50% of decisions taken by protected area managers will take into account the interests of IPs/LCs in accessing resources. | % of documented PA decisions (e.g., access rules, zoning, benefit-sharing) that include IPLC consultation records | [5 empty] | Salonga 20% | 25% | 30% | 35% | 40% | 50%
[6 empty] | 4.1.6.2 |  | By 2030, WWF commissions and disseminates at least one legal/policy gap analysis on IPLC rights and access to resources across supported landscapes. | Number of policy/legal analysis reports completed and shared with decision-makers | [5 empty] | 0 | 1 | 1 | 1 |  | 3
[6 empty] | 4.1.6.3 |  | By 2030, at least 3 multi-stakeholder consultation meetings are held with government, civil society, and IPLC representatives to advocate for IPLC-inclusive policy reforms. | Number of stakeholder meetings convened with documented participation from IPLCs | [5 empty] | Salonga:15 | Salonga:2 | Salonga:2 | Salonga:2 | Salonga:2 | Salonga:2
[6 empty] | 4.1.6.4 |  | By 2030, WWF provides technical support in the development, revision, or validation of at least one draft policy, decree, or strategy that explicitly safeguards IPLC rights and access to natural resources. | Number of policy drafts/revisions with WWF-supported IPLC language or provisions | [5 empty] | National level:0 |  | 1 |  |  | 1
[6 empty] | 4.1.7.1 |  | By 2030, representatives from WWF-supported landscapes in DRC participate in cross-border steering committee meetings on biodiversity and environmental governance, with documented contributions. | % of cross-border meetings attended by WWF-supported landscape representatives | [5 empty] | Virunga: 0% | 10% | 30% | 50% | 70% | 100%
[6 empty] | 4.1.7.2 |  | By 2030, WWF provides technical, financial, or coordination support to the implementation of at least 6 national and international biodiversity-related strategies or frameworks (e.g., NBSAP, NDC, 30x30), including documented actions and results. | Number of biodiversity-related national/international frameworks receiving documented WWF implementation support | [5 empty] | TBD | TBD | TBD | TBD | TBD | TBD
[6 empty] | 4.1.7.3 |  | By 2030, at least USD 50 million will be mobilized internationally by the Congolese government (MEDD) to finance nature conservation and Climate Action with the support of WWF-DRC. | Total USD committed to DRC for nature conservation and climate action (with WWF support) | [5 empty] | 0 | 0 | 20 | 20 | 10 | 50
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Margaret Madira The OSP risk assessment needs to be completed as already mentioned before

## Result Chain (hidden)
| Conservation Focus of the Programme | Priority Threats / Other Factors | Result ID | Program Outcomes | Relevant Geographic Scope | Relevant Thematic Scope | Annual Result - Year 1 | Output (Annual Result) - Year 2 | Output (Annual Result) - Year 3 | Output (Annual Result) - Year 4 | Output (Annual Result) - Year 5 | Key Assumptions & Risks | Sustainability & Exit Plan
READ Me First | Please copy the list of Conservation Focus from the previous tab. | For each Conservation Focus please list the priority threat (or other factors). Please use one line for each threat/factor. If a single threats affect more than one Conservation Focus, please list all the relevant conservation focus/focal interest under the column B. CMP Direct Threat Classification is available here - https://docs.google.com/spreadsheets/d/1rJSNz1LG_KOqoudVFglodx47HZ9LR-M6iVlRYMvn9Wk/edit#gid=310830663 Please ensure that priority threats/other factors are subset of those selected under the OSP. You may define further in detail. |  | Please Describe the desired reduction of threats (or changes to the identified factors). Please make sure the statement is SMART. | Please indicate the relevant Geographic Scope for each Outcome statement. Ensure to use one of the Geographic scope identified in the Scope tab of OSP Design Template. | Please indicate the relevant Thematic Scope for each Goal statement. Ensure to use one of the Thematic scope identified in the Scope tab of OSP Design Template. | Please define measurable Programme Annual Results which are milestones in achieving Programme outcomes. Therefore Programme Outcome must be embedded in the Programme Outputs. Outputs must represent tangible deliverables, within our area of control, that are critical to achieving the Programme Outcomes, in line with the Theory of Change. If there are areas of innovation and/or research, please make sure to include those outputs and activities as well. See the guidance on the approach to the Programme and Project Planning |  |  |  |  | Please identify the key assumptions that underpin the logical sequences linking Outputs, and Outcomes, and to one or more Goals Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment. WWF policies do not require risk assessment at program level but at Office level and at Project level. However each Program team is encouraged to perform Program Risk assessment. Use the Office risk register template in such case. | Please describe how your program aims to ensure the sustainability of the program outcome and an eventual exit by WWF. See Guidance by PPMS Step - Element 2.3
Example | Coral Reef Marine priority species | Overfishing / unsustainable fisheries |  | By 2030, fisheries management plans are in place (implemented & monitored) in 80% of coastal fisheries in ABC coastal communities. | Beta seascape | Ocean | Awareness of unsustainable fisheries increased in ABC coastal communities by 50% | Technical capacity of 10 fisheries communities built on fisheries management plan | 5 fisheries communities developed fisheries management plan | 4 fisheries communities developed fisheries management plan |  | Local communities can improve (or at least maintain) the economic state after the fisheries management plan. | Creation of alternative sustainable income to ensure that the sustainable implementation of the fisheries management plan. Also, inclusion of CSO (and their capacity building) in the project implementation to enable the eventual exit of WWF and transition of responsibility to the local CSO.
[5 empty] | Beta seascape | Ocean | Baseline assessment of current fisheries practices conducted for 10 fisheries in ABC coastal community |  |  | 50% of coastal fisheries are implementing and monitoring fisheries management plan | 80% of coastal fisheries are implementing and monitoring fisheries management plan
Note on I1: @hwilliams@wwfint.org, also here we should be align the language _Assigned to hwilliams@wwfint.org_ -Philip Kahuho

## Programme Implementation Plan
| Outcome ID | Outcome Name | Output ID | Output Statement | FY26 Cost | FY27 Cost | FY28 Cost | FY29 Cost | FY30 Cost | Total Output Cost + Management fee | Current Project (CPM Project #) | Target Funding Source
READ Me First |  |  | Please enter the FY of planned Annual Results. It should capture the full length of the OSP. | Please list all the outputs identified under Program M&E Tab. During the annual planning and budgeting process, the Programme will have opportunities to further refine and detail the activities and costs. The initial costing of the programme outputs can be estimated, which will be used to estimate the cost of total OSP implementation and the development of the financial plan. Please make sure to include outputs related to M&E, ESSF and other risk mitigation, etc. | [6 empty] | If the activity is already funded, please indicate the relevant CPM number(s). | If there is a funding gap and have prospective funding sources, please indicate the source.
| 2.1.1 | Zero conversion in HCV | 2.1.1.1 | By 2030, at least 50% of LDCs in priority landscapes are supported in sustainable agriculture. | 250000 | 250000 | 250000 | 250000 | 250000 | 1406250 | ABC224678
| 2.1.1 | Zero conversion in HCV | 2.1.1.2 | By 2027, HCV forest areas are fully mapped and demarcated in all targeted landscapes, with GIS data integrated into national or regional land-use planning systems. | 250000 | 300000 | 200000 | 200000 | 0 | 1068750 | ABCC224678
| 2.1.1 | Zero conversion in HCV | 2.1.1.3 | By 2028, Formal agreements (e.g., MOUs, conservation easements, or community protocols) covering 100% of mapped HCV areas are signed with landowners, communities, or custodians. | 20000 | 20000 | 20000 | 20000 | 20000 | 112500 | ABCC224678
| 2.2.4 | Habitats are restored | 2.2.4.1 | By 2030, at least 100,000 ha of degraded areas (savannahs, forests, mangroves) are under restoration | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 5625000
| 2.2.1 | Forest cleared for agriculture reduced | 2.2.1.1 | By 2030, the coverage of community monitoring activities in local community forest concessions (LCFCs) is increased by at least 20% compared with 2025. | 200000 | 200000 | 200000 | 200000 | 200000 | 1125000
| 2.2.1 | Forest cleared for agriculture reduced | 2.2.1.2 | A forest-clearing monitoring and enforcement system is operational, with community and government participation, across all high-risk zones in the targeted landscape. | 40000 | 40000 | 40000 | 40000 | 40000 | 225000
| 2.2.2 | Best agricultural practices supported | 2.2.2.1 | By 2030, at least 80% of small-scale farmers in priority landscapes are trained in sustainable agriculture. | 50000 | 50000 | 50000 | 50000 | 50000 | 281250
| 2.2.2 | Best agricultural practices supported | 2.2.2.2 | By 2030, Extension services or farmer field schools are operational in all priority landscapes | 50000 | 50000 | 50000 | 50000 | 50000 | 281250
| 2.2.2 | Best agricultural practices supported | 2.2.2.3 | Incentive mechanisms (e.g., inputs, market access, certification, or micro-finance) are in place to support at least 80% of targeted farmers | 50000 | 50000 | 50000 | 50000 | 50000 | 281250
| 2.2.3 | community with management plans established | 2.2.3.1 | By 2030, at least 80% of Local community forest concessions will be supported by WWF and its partners to develop Sustainable Management Plans (SMPs). | 300000 | 300000 | 0 | 0 | 0 | 675000
| 2.2.3 | community with management plans established | 2.2.3.2 | By 2030, at least 30% of simplified community forest concession management plans are implemented with support from WWF and its partners | 150000 | 150000 | 0 | 0 | 0 | 337500
| 4.1.1 | Conservation related complaints reduced | 4.1.1.1 | By 2026, grievance redress mechanisms (GRMs) are established in 100% of target landscapes with annual tracking and response of cases. | 0 | 0 | 0 | 0 | 0 | 0
| 4.1.1 | Conservation related complaints reduced | 4.1.1.3 | By 2030, at least 100% of ESSF flagship tools (ESIA, CGES, MGP, GBV Action Plan, Gender Analysis, HSSE Action Plan, Stakeholder Engagement Plan, and IP Engagement Plan) are developed, adopted, and implemented. | 50000 | 50000 | 50000 | 50000 | 50000 | 281250
| 4.1.1 | Conservation related complaints reduced | 4.1.1.4 | By 2030, Salonga ecoguards are trained on human-right based approaches to law enforcement | 20000 | 20000 | 20000 | 20000 | 20000 | 112500
| 4.1.2 | Positive perception on conservation improved | 4.1.2.1 | By 2020, studies or surveys on the negative perception of IPs/LCs living in the SNP and its periphery with regard to conservation are carried out. | 0 | 20000 | 0 | 0 | 20000 | 45000
| 4.1.3 | Students supported | 4.1.3.1 | By 2030, at least 5% of pupils in SNP (Monkoto & Yokelelu) will be supported through the provision of school supplies. | 30000 | 30000 | 30000 | 30000 | 30000 | 168750
| 4.1.4 | Household income increased | 4.1.4.1 | By 2030, at least 50% of households in targeted IP/LC communities are actively participating in at least one WWF-supported innovative income-generating activity (PES, biodiversity credits, LCFCs, or micro-enterprises). | 800000 | 800000 | 800000 | 800000 | 800000 | 4500000
| 4.1.4 | Household income increased | 4.1.4.2 | By 2030, at least 36 structures are supported to implement Payment for Ecosystem Services (PES) schemes | 400000 | 400000 | 400000 | 400000 | 400000 | 2250000
| 4.1.4 | Household income increased | 4.1.4.3 | By 2030, WWF facilitates partnerships with at least 120 LCFCs, OECMs, and private sector entities to promote the delivery and sustainability of ecosystem services in target landscapes. | 200000 | 200000 | 200000 | 200000 | 200000 | 1125000
| 4.1.4 | Household income increased | 4.1.4.4 | By 2030, partnerships is established with at least three operators to facilitate fund transfer for PES and other credit mechanisms. | 100000 | 100000 | 100000 | 100000 | 100000 | 562500
| 4.1.4 | Household income increased | 4.1.4.5 | By 2030, at least 5 value chains (rice, charcoal, honey, etc.) are developed with market access in priority landscapes. | 100000 | 100000 | 100000 | 100000 | 100000 | 562500
| 4.1.5 | Access to materials of good life improved | 4.1.5.1 | By 2030, at least 4 water points (e.g., boreholes, wells) are constructed or rehabilitated in underserved IPLC communities within WWF-supported landscapes. | 40000 | 40000 | 40000 | 40000 | 40000 | 225000
| 4.1.5 | Access to materials of good life improved | 4.1.5.2 | By 2030, livelihood support is provided to at least 5,000 IP&LC communities in priority landscapes | 1434000 | 1200000 | 1770000 | 1770000 | 1757000 | 8922375
| 4.1.6 | policies & decisions promoting IPLC rights enacted | 4.1.6.1 | By 2030, at least 50% of decisions taken by protected area managers will take into account the interests of IPs/LCs in accessing resources. | 50000 | 52000 | 51000 | 51000 | 50000 | 285750
Total Annual Cost + Management Fee |  |  |  |  | 6282000 | 6099750 | 6098625 | 6098625 | 5880375 | 30459375

## Learning Questions
Learning Questions
READ Me First | Please articulate specific learning questions that your program will regularly reflect on for the learning priority. Max 100 words.
Example | - To what extent are the program's activities effective in achieving the planned results? - What worked and what didn’t? - Were there any unintended consequences? (positive or negative/ internal or external) - Were there any emergent results? (more than the planned results)