## Programme Profile
Read Me First
Programme Name | Please enter the Name of the Programme (Max 20 words) See the guidance on the approach to the Programme and Project Planning
Program Lead | Please enter the Name of the Program Lead
Program Team Member | Please list the name of Program Staff. This will be the list of staff who will have access to the Program information in the new PMEL system.
Program Duration | Please indicate the duration of Program. Minimum Duration of the Program is 5 years. | FROM: | FY2026
|  | TO: | FY2030
Programme Description | Please enter a short description of the Programme (Max 200 words) |  | FreshWater The WWF DRC Freshwater Conservation Programme aims to safeguard critical freshwater ecosystems, including rivers, peatlands, wetlands, and spawning grounds, within the Virunga and Lacs Tumba Mai Ndombe landscapes. These habitats are under mounting pressure from, unplanned and unsustainable development, unsustainable fishing, destructive traditional practices, water pollution, poor farming methods, and climate change impacts. Recognizing these freshwater systems' ecological and socio-economic value, the programme takes an inclusive approach to conservation. WWF will provide IPLCs with training in sustainable fishing and climate-smart agriculture, particularly lowland rice farming in peatlands. Integrated land and water resource planning helps maintain hydrological balance and peatland wetness, while restoration efforts boost carbon sequestration and ecosystem resilience. The programme will also promote alternative livelihoods, legal compliance, policy alignment with national climate strategies, and sustainable development. This ensures stronger community ownership, sustainable use of resources, and long-term biodiversity conservation. This program is aligned with WWF’s Global Goal of Zero Loss of Habitat and directly contributes to the GBF (Targets 2, 8, and 9), SDGs (Goals 6, 13, 14 and 17) as well as Ramsar Convention on Wetlands and the Convention on Biological Diversity (CBD). This integrated and inclusive conservation approach will ensure improved management of freshwater ecosystems and provide long-term socio-economic benefits to communities depending on these ecosystems.
Program Focus / Focal Area | Please select one or more Conservation and/or Human well being Focus areas that your program will be focusing on. Please make sure this is a subset of what's selected in the OSP.
Geographic Scope (Landscape) | Please list all the operational land/seascapes that are within the scope of the Program. For each land/seascape, provide short description of why the scape is critical in the context of this Program (max 200 words per land/seascape). Example: Name of the land/seascape: Description max 200 words. All land/seascapes must must apply ESSF. Guidance on landscape definition is here | Name of land/seascape | Description (Max 200 words)
|  | Virunga Landscape | Our zone of intervention in the Virunga landscape is located in the province of North Kivu, along the western border of Virunga National Park, the first national park created in Africa, famous for the iconic mountain gorilla and also home to the eastern lowland gorilla and chimpanzee. It is an area of rich faunal biodiversity, with 210 mammalian species, 21 of which are endemic to DRC, and over 700 species of birds, including several endemics. The region lies within the Albertine Rift, has volcanic mountains and rugged terrain with average slopes of greater than 15%. The province itself, an area of 59,483 km2, has a population of approximately 8.9 million inhabitants spread over six territories: Beni, Lubero, Masisi, Nyiragongo, Rutshuru, and Walikale. The agricultural sector is of paramount importance, providing nearly six out of ten jobs. Rural communities depend highly on access to natural resources for their livelihoods, and supplying the demand from urban areas for products including charcoal and bush meat is placing unsustainable pressure on the environment and wildlife.
|  | Lacs Tumba-Mai Ndombe | The Lake Tumba-Mai Ndombe landscape lies along the western border of the DRC, and includes one of the largest wetlands in the world. In the northern zone, there are varied forest stands including swamp forests on peatland, limbali forests and secondary forests. The wetland ecosystem provides important bird habitat and was designated as a Ramsar Site in 2008. The diverse ecosystems are home to emblematic and endemic species of fauna, including large mammals, reptiles, amphibians and fish. There are also high densities of two threatened species of African apes, chimpanzees (Pan troglodytes) and bonobos (Pan paniscus), as well as forest elephants (Loxodonta cyclotis), hippopotamus (Hippopotamus amphibius), approximately 16 species of diurnal monkeys, seven species of duikers, and leopards. There are four protected areas within the landscape: the Ngiri Triangle Nature Reserve, the Tumba Lediima Reserve, the Eala Botanical Garden and the Mabali Scientific Reserve. The first three are managed by the Institut Congolais pour la Conservation de la Nature (ICCN) and the last by the DRC Ministry of Scientific Research. There are also community forest concessions of which 6, covering 14,900 ha, have been set up with the primary objectives of conservation and bonobo ecotourism (Malebo area, located in the Bateke-Nord chiefdom). The Malebo area contains some of the highest densities of bonobos recorded (0.79 bonobo/km²). The landscape is home to more than two million people, with almost half resident in the city of Mbandaka to the north, and the remainder in smaller towns (Lukolela, Makanza, Bikoro, Bomongo, Inongo, Kwamouth, Bolobo, etc.) and villages situated along the rivers and lakes. Farming, fishing, hunting, and collecting non-timber forest products (NTFPs) are the main sources of income for rural communities.
Thematic Scope (Practices) | Please list all the thematic that are relevant to the scope of the OSP. (Choice: Finance & Administration, Fundraising, Communications, P&C, Partnership, PMEL, etc.). For each theme, provide short description of why the theme is critical in the context of the OSP (max 200 words per theme). Example: Name of the theme: Description max 200 words. See Guidance by PPMS Step - Element 1.2 | Name of Thematic Scope | Description (Max 200 words)
Freshwater

## Situation Analysis
Read Me First
Political | Please enter the concise analysis (narrative) of context and trends (political, social, economic, climate & environmental, and institutional) in country that has effects on the scope of the Programme. Depending on the nature of the program, some context may be more relevant than the others. (See Guidance by PPMS Step - Element 1.3, and IUCN-CMP Unified classification of Threat 2.0s) | The political situation in the target landscapes reflects a variety of dynamics depending on local realities. In the Virunga region, political complexity remains high due to persistent security tensions. The DRC government has instituted a state of siege in conflict-affected provinces, particularly North Kivu, accompanied by significant security, judicial, administrative and constitutional reforms. The Disarmament, Demobilization, Reintegration and Stabilization Program (PDDRC-S) supports this security dynamic. However, the reform of the Independent National Electoral Commission (CENI) in 2022 has raised concerns about possible electoral tensions. On the other hand, the DRC's active participation in the Nairobi and Luanda peace processes underlines a commitment to long-term stability in the east of the country. In comparison, the Lac Tumba Mai-Ndombé landscape presents a relatively stable and peaceful provincial political context, supported by innovative policies, particularly in terms of peatland and biodiversity preservation. This stability is accompanied by a recent improvement in respect for the rights of indigenous peoples, thanks to the enactment of specific laws reinforcing their protection. Similarly, in the Mayombe Mangroves landscape, the political framework is strengthened by provincial autonomy established by the law on the free administration of the provinces. This autonomy encourages local management in key areas such as the environment, land and energy. WWF plays a key role in working closely with the authorities and stakeholders to ensure effective implementation of environmental policies. Finally, in the Salonga National Park, sustained efforts are being made to strengthen governance and security. Particular emphasis is placed on the application of a robust environmental and social framework, with the overriding aim of preventing human rights abuses and ensuring the sustainable and respectful management of the park's resources.
Social |  | In the Virunga region, complexity remains high due to persistent insecurity for over 30 years, exacerbated by the activities of rebel groups such as the M23. The provinces of North and South Kivu are experiencing massive internal population displacements, severe food insecurity, and widespread human rights violations, including sexual violence and indiscriminate shelling. This major humanitarian crisis continues to weigh heavily on peace efforts, despite regional initiatives such as the Nairobi and Luanda processes, and government reforms aimed at stabilizing eastern DRC. In contrast, the Lac Tumba Mai-Ndombé landscape displays a diverse and relatively stable social framework, inhabited by a cultural mosaic composed mainly of farmers, hunters, fishermen and gatherers. Although the precise representation of indigenous populations is uncertain, their recent recognition thanks to new legislation bears witness to a positive evolution in the protection of their rights. Large towns such as Inongo and Mbandaka are major socio-economic hubs, with local populations heavily dependent on water resources. The Mayombe Mangrove landscape, on the other hand, presents a mono-ethnic context mainly dominated by ethnic Kongo groups (Yombe, Woyo, Asolongo and Mboma), living in harmony in an urban ano-rural setting. This cultural homogeneity contributes to a stable political environment, facilitated by provincial autonomy established by the law on the free administration of the provinces, which enables effective local management, particularly in the environmental field. Finally, in the Salonga National Park, current efforts are focused on strengthening governance and environmental and social security. Significant action is being taken to prevent human rights abuses and ensure sustainable management of the park's natural resources, despite the challenges posed by the region's isolation and logistical complexity.
Economic |  | The Virunga region remains marked by chronic instability due to the prolonged presence of rebel groups and the illicit exploitation of its abundant natural resources. The provinces of North and South Kivu are rich in precious minerals such as coltan, gold, cassiterite and wolframite, highly prized resources that fuel a complex clandestine trade involving regional and international players. This illegal trade deprives the Congolese state of substantial revenues, while indirectly financing armed conflict. Violent clashes also lead to massive population displacement, exacerbating a major humanitarian crisis characterized by serious human rights violations. In contrast, the Lac Tumba Mai-Ndombe landscape features a local economy dominated by agriculture and fishing, which are the main sources of income for the communities. Despite the presence of largely inactive industrial logging concessions, artisanal and illegal logging and the growing production of charcoal represent major economic and environmental challenges for this region. In the Mayombe Mangrove landscape, the state remains the main employer, while the local economy is essentially based on agriculture, fishing and small-scale trade. However, the lack of opportunities is driving many young people into unsustainable activities such as illegal logging and charcoal-making, threatening the natural resources of the protected areas. Agricultural products such as cocoa, palm oil, coffee, cassava, bananas and corn are important economic assets. Finally, the Salonga National Park is pursuing its efforts in terms of environmental and social governance to ensure sustainable management, despite significant logistical challenges linked to geographical isolation. Targeted initiatives aim to strengthen the protection of natural resources while guaranteeing respect for human rights.
Climate & Environmental |  | The Virunga region remains marked by chronic instability, exacerbated by the presence of rebel groups and the illicit exploitation of its abundant natural resources. The provinces of North and South Kivu, rich in strategic minerals such as coltan, gold and cassiterite, suffer the effects of a complex clandestine trade involving regional and international players. This illegal trade directly fuels armed conflict, while depriving the Congolese state of vital financial resources. In addition, the effects of climate change are aggravating the situation, leading to catastrophic flooding, mass displacement and increased pressure on already fragile local communities. This dynamic also contributes to the recruitment of young people into armed groups, fuelling a vicious circle of violence and poverty. By comparison, the Lac Tumba Mai-Ndombé landscape is characterized by a predominantly agricultural and fish-farming economy but is facing increasing pressure on its forest resources. Rapid deforestation, largely due to artisanal logging and charcoal production, threatens the integrity of the vast rainforests and peatlands, essential for climate regulation. The environmental situation is worrying, with deforestation rates well above the national average, jeopardizing the region's unique biodiversity. In the Mayombe Mangrove landscape, the state remains the main employer, but local economic activities remain limited, pushing young people towards unsustainable practices such as charcoal-making and illegal logging. The hot, humid equatorial climate exacerbates environmental vulnerability, and unsustainable agricultural practices and recurrent bush fires threaten forest, savannah and aquatic ecosystems. Finally, in the Salonga National Park, despite its geographical isolation and the associated logistical challenges, initiatives continue to strengthen environmental and social governance to ensure the sustainable protection of its exceptional biodiversity, while ensuring respect for the rights of local populations.
Institutional |  | The Virunga region continues to face persistent instability, amplified by the presence of armed groups and the illegal exploitation of strategic natural resources. The provinces of North and South Kivu, rich in essential minerals such as coltan, gold and cassiterite, are subject to a complex clandestine trade involving regional and international players, which finances conflicts and impoverishes the Congolese state. The situation is exacerbated by climate change, illustrated by recurrent large-scale flooding such as that which recently occurred in South Kivu province. Faced with these challenges, initiatives such as the Priority Action Plan (PAP 2025) in North Kivu and the Provincial Development Plan (2024-2028) in South Kivu are being implemented with the support of international partners to improve living conditions and strengthen the resilience of local communities. In the Lac Tumba Mai-Ndombe landscape, shared between the Equateur and Mai-Ndombe provinces, the dominant economic activities are agriculture and fishing, which play a key role for local communities. However, artisanal logging and the growing production of charcoal represent significant environmental pressures. A decentralized institutional structure, comprising provincial governments, provincial assemblies and local authorities, collaborates with institutions such as the Institut Congolais pour la Conservation de la Nature (ICCN) to ensure sustainable management of natural resources. The Mayombe Mangrove landscape, located entirely within the province of Kongo Central, benefits from a provincial administration structured around a governor and a provincial assembly. Despite this favorable institutional context, limited economic opportunities are driving young people towards the unsustainable exploitation of natural resources. The State and various stakeholders, notably the ICCN, the Local Steering Committee (CLP) and civil society, are working together to ensure the sustainable management of natural resources. Finally, the Salonga National Park is pursuing its environmental and social protection efforts, despite major logistical and geographical constraints. Targeted initiatives are being deployed to ensure the conservation of biodiversity and the protection of local communities' rights.

## Stakeholder Analysis
| Stakeholder Name | Stakeholder Description | Stakeholder Type | Engagement Stage (planning, Implementation, MEL) | Engagement methods & strategies | Due Diligence (Y/N)
READ Me First | Please list key groups of stakeholders (people and organizations) who will be influenced by, have an impact on, or will help implement conservation to engage during the Programme planning, implementation, monitoring, and learning. Max 20 words. See Guidance by PPMS Step - Element 1.4 | Please briefly explain the significance of engaging with the stakeholder, and what you expect from the effective engagement. max 200 words | Please indicate the type of stakeholders (individual or organization): - Indigenous People & Local Communities - Civil Society Organization - Government's / Public Sector Organization - Companies / Private Sector - Universities / Research Organization - Other | Please indicate what stage each stakeholder group will be engaged - Programme planning, implementation, M&E, and Learning, etc. | Please describe how each stakeholder group will be engaged. Make sure that stakeholders will have regular access to the Programme information and, as appropriate, are aware of complaints procedures and feedback mechanisms. | For corporate & philanthropic partners (major donors, trusts, and foundations), please indicate if the due diligence is already conducted or not. For Other stakeholders, put NA. Corporate Partnership Rules & Guidelines Philanthropy Due Diligence
| CENED | Center for Nutritional and Environmental Education for Development | SHOW JUMPING | Designing, Planning, implementation and monitoring | Service Agreement. Discussion of different types of restoration for different kinds of land use. | Yes
| CRRDC | Red Cross Comité provincial du Nord-Kivu | Government Agency | Designing, Planning, implementatio n and monitoring | MoU, Establishing grievance and redress mechanism | Yes
| FODE | Front Opérationnel de Défenseurs des Ecosystèmes Ecologiques | SHOW JUMPING | Designing, Planning and implementation | Service Agreement. Discussion of different types of restoration for different kinds of land use. | Yes
| INITIAM | Enhanced Intelligent Technology Initiative | SHOW JUMPING | Implementation and monitoring | Service Agreement. | Yes
| ONDE | Organization of Naturalists for the Defense of the Environment | SHOW JUMPING | Designing, Planning, implementation and monitoring | Service Agreement. Discussion of different types of restoration for different kinds of land use. | Yes
| RAPNAV | Network of Associations for the Protection of Nature around Virunga | Network CSO | Designing, Planning, implementation and monitoring | Service Agreement | Yes
| PIDP | Integrated Program for the Development of the Pygmy People in Kivu | SHOW JUMPING | Implementation | Service Agreement | Yes
| North Kivu Civil Society | Société civile Force Vive du Nord-Kivu | Network CSO | Implementation | MoU. Advocacy | Yes
| UGADEC | Union of Conservation Associations Gorillas for Community Development in Eastern DR Congo | Network CSO | Implementation | MoU. Supporting Community forest concessions | Yes
| APAB | Batwa Indigenous Peoples Association | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| CAFEPADE | Caisse des femmes paysannes pour le développement | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| CBFC | Consortium Brave Femmes du Congo | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| Young Methodists |  | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| SOCEARUCO | Environmental and agrarian civil society of Congo | Network CSO | Designing, Planning, implementation and monitoring | MoU. Advocacy | Yes
| TRAFEED | Networking with Federations of Women and Children in Need | SHOW JUMPING | Implementation | MoU. Advocacy | Yes
| CIAPAFED |  | Society civil organization | Planning & implementation | Quarterly meetings, reporting, sharing action plans, (how we work with partners) | Yes
| ERA Congo (carbon credit) |  | private sector | Learning
| SODEFOR (logging) |  | private sector | Learning
| Local communities managing CFCL |  | Local communities | implementation
| Academics and scientists monitoring peatlands and forests - University of Gembloux |  | University | Learning
| Univ of Kisang ani, Univ Mbandaka |  | University | Learning
| Governorates |  | Public sector | Planning
| ICCN, |  | Public sector | Planning & implementation
| RSM |  |  | Learning
| Provincial and territorial administrations |  | Public sector | Planning & implementation | The provincial and territorial administration participates in the implementation of PIREDD project activities, and is involved in monitoring.
| RF Norway |  | Society civil organization | Learning
| ERAIFT |  | Haute Ecole and Research | Planning & implementation | Involved in the planning and implementation of Alliance Verte, EU-Luki, PASAGAR and other projects
| ACODED/AMAR |  | NGO | implementation | Stakeholder in the implementation of the Alliance Verte project
| ADEV |  | NGO | implementation | Stakeholder in the implementation of the Alliance Verte project
| CCPN |  | NGO | implementation | Stakeholder in the implementation of the Alliance Verte project
| ULB-Coopération |  | INGO | Research & Development | Implements research and development projects in the landscape
| UKV |  | University | Training and Research | Stakeholder in the Alliance Verte project
| Provincial Government |  | Public institution | implementation | Monitoring and evaluation of project implementation in the landscape
| Decentralized and centralized territorial entities |  | Public institution | Monitoring and evaluation | Monitoring and evaluation of project implementation in the landscape
| CLP |  | Public institution | Planning | Participates in project planning at the Luki Reserve
| CLDs |  | Farmers' civil society | Implementation | Project beneficiaries in the landscape

## Focus & Goals (hidden)
| Conservation Focus | Relevant OSP Goals | Key Assumptions
READ Me First | Please list each conservation focus / focal interest. Biodiversity Focal Interests can be focal species or habitats/ ecological systems. Human Wellbeing Focal Interests can be those component of human wellbeing affected by the status of biodiversity focal interests (material and non-material benefits obtained by ecosystem. Please ensure that focus / focal interest is a subset of those selected under the OSP. You may define further detail. | Based on the focus / focal interest selected, Please select the OSP Goal that your program is aiming to deliver. Please list the OSP Goal statement. | Please identify the key assumptions that underpin the logical sequences linking strategies to one or more focal interests. Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment.
Example | Coral Reef in Beta seascape. | Live coral reef covers at least 25% of the reef within the priority coastal seascapes in country Y. | WWF or its partner organization can monitor the live coral reef coverage in the coastal Beta seascape with proper funding.

## Focus & Goal
| Conservation Focus | Relevant OSP Goals | Key Assumptions
READ Me First | Please list each conservation focus / focal interest. Biodiversity Focal Interests can be focal species or habitats/ ecological systems. Human Wellbeing Focal Interests can be those component of human wellbeing affected by the status of biodiversity focal interests (material and non-material benefits obtained by ecosystem. Please ensure that focus / focal interest is a subset of those selected under the OSP. You may define further detail. | Based on the focus / focal interest selected, Please select the OSP Goal that your program is aiming to deliver. Please list the OSP Goal statement. | Please identify the key assumptions that underpin the logical sequences linking strategies to one or more focal interests. Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment.
Example | Coral Reef in Beta seascape. | Live coral reef covers at least 25% of the reef within the priority coastal seascapes in country Y. | WWF or its partner organization can monitor the live coral reef coverage in the coastal Beta seascape with proper funding.
| Habitats (Spawning grounds) | By 2035, at least 90% of targeted peatland areas are kept intact compared to the 2026 baseline. | 1. Pollution, Climate conditions and other environmental hazards do not destroy the spawning areas
| Habitat (Peatlands) | By 2035, at least 90% of targeted peatland areas are kept intact compared to the 2026 baseline. | Pollution, Climatic hazards, and other environmental hazards do not destroy the peatlands areas

## Narrative TOC
| Read Me First | Freshwater
Narrative Theory of Change | Please articulate the Theory of Change in Narrative. A Theory of Change (ToC) should be underpinned by evidence of the logic. Articulate the causal pathway that leads from the current to the desired situation, describing how the Programme activities will deliver the envisioned Programme Outputs and Outcomes, and ultimately the Programme/OSP Goals. Key risks associated with the key assumptions along the Theory of Change to achieve its Programme Outcomes and Goals must be articulated. A risk is potential future event that may impact achievement of goals. Assumptions are explicit statements of what the CO assumes is true. The logical sequences must link activities to one or more focal interests as reflected in a theory of change. Assumptions may also express how external variables may influence the achievement of results. Max. 500 words See Guidance by PPMS Step - Element 2.1 | The WWF DRC Freshwater Programme is designed to safeguard the integrity of freshwater ecosystems and peatlands, while supporting communities to sustainably manage natural resources. Unsustainable agriculture, destructive fishing practices, pollution, and hydrological disruption are key drivers of degradation across freshwater systems. This is further exacerbated by climate change, which alters rainfall patterns and increases the risk of peatland drying, fire, and carbon release. To address these threats, the programme takes a holistic and community-centered approach. The foundation of the programme lies in promoting sustainable management of freshwater ecosystems, including peatlands, rivers, and wetlands. This involves training farmers and fishers on climate-smart agricultural practices and non-destructive fishing techniques, enabling them to shift away from practices that encroach on sensitive habitats or degrade spawning grounds. As farmers adopt improved practices and reduce harmful inputs, ecosystems are protected from unsustainable use, and water abstraction and pollution are minimized. By developing integrated land-use and water resource management plans that balance conservation and development, the programme helps maintain peatland wetness and regulate hydrological functions. Complementary efforts to restore degraded rivers, wetlands and peatlands enhance carbon sequestration and climate resilience. Providing alternative livelihoods further reduces community pressure on freshwater ecosystems. Through inclusive planning and decision-making, Indigenous Peoples and local communities gain ownership of conservation solutions, strengthening long-term sustainability. Promoting legal compliance and integrating peatland protection into national climate strategies and NDCs enhances political commitment and attracts international support. Together, these actions contribute to the goals of keeping at least 90% of targeted spawning grounds and peatlands intact. By 2030, the programme aims for 75% of supported fishers and smallholder farmers to adopt sustainable practices, leading to restored habitats, protected water systems, and resilient livelihoods.
Opportunities for Innovation | Please articulate priority areas of innovation and research where needed. Innovation and Research activities must be included in the Programme Implementation Plan, Max. 500 words

## Program M&E Plan
Programme M&E plan | Program | Prog_ID | Relevant Geographic Scope | Focus | Priority Threats / Other Factors | Result ID | Results Name | Goal, Outcome and Output Statement | Indicator | Description | Means of Verification (Source of Data) | Data Collection and Analysis Methodology | Frequency of Measurement | Key Assumptions & Risks | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Location | Responsible
| Freshwater Conservation | 3 |  | Habitats (Spawning grounds) |  | 3.1 | Fresh water | By 2035, at 90% of targeted spawning areas in priority landscapes are kept intact compared to the 2026 baseline. | Percent of the targeted spawning areas kept intact | We need more information to determine how this will be measured Spawning areas will be mapped. Numerator: Denominator: |  |  |  | 1. Pollution, Climate conditions and other environmental hazards do not destroy the spawning areas | LTMN : TBD Virunga/Itombwe:TBD |  |  |  |  | LTMN : TBD Virunga/Itombwe:TBD
| Freshwater Conservation | 3 |  | Habitat (Peatlands) |  | 3.2 | Fresh water peatlands | By 2035, at least 90% of targeted peatland areas are kept intact compared to the 2026 baseline. | Percent of targeted peatland maintained intact | Numerator: number of hectares of targeted peatland that is intact Denominator: Total hectares of targeted peatland | Peatland cover monitoring database | Peatland cover monitoring, Remote sensing | Endline | Pollution, Climatic hazards, and other environmental hazards do not destroy the peatlands areas | LTMN :8810,1ha Virunga/Itombwe:TBD |  |  |  |  | LTMN :8810,1ha Virunga/Itombwe:TBD
| Cross Cutting | 1 2 3 |  | Human Wellbeing |  | 4.1 | Human well-being | By 2035, the wellbeing of targeted communities in targeted landscapes is improved by 20% relative to 2025 baseline. | Wellbeing score | Wellbeing includes materials for good life, social cohesion, rights, access to natural resources/5 categories of wellbeing | Wellbeing survey data (with linked database) | Socioeconomic survey related to wellbeing aspects supported. | Endline | There are no major conflicts, displacements, or political interference that would disrupt livelihoods, services, or community cohesion. | LTMN : 0.3 Salonga :0.52 Virunga/Itombwe:TBD |  |  |  |  | LTMN : 0.35 Salonga : 0.55 Virunga/Itombwe
Programme Outcomes | Freshwater Conservation |  |  | Habitat (Spawning grounds) | Unsustainable Fishing practices Destructive Traditional Practices Pollution Water abstraction | 3.1.1 | Sustainable fishing practices improved | By 2030, at least 75% of supported fishermen are practicing sustainable fishing practices in spawning grounds, compared to the 2025 baseline. | Percent of targeted fishermen practicing sustainable fishing practice |  | Fishery monitoring data | Fishery monitoring: regular data collection on fishing gears, quantity and size of fishery products, period of fishing, spawning areas, etc. | Annually | Fishermen adopt improved practices There is availability of gears that support the sustainable and non-destructive practices (Can we control this) Socioeconomic incentives of adopting sustainable practices are sustainable and encourage the continuity of practices | LTMN : 0% Salonga:0% Virunga/Itombwe:TBD | LTMN : 10% Salonga:10% Virunga/Itombwe:TBD | LTMN : 30% Salonga:20% Virunga/Itombwe:TBD | LTMN : 50% Salonga:50% Virunga/Itombwe:TBD | LTMN : 60% Salonga:60% Virunga/Itombwe:TBD | LTMN : 75% Salonga:75% Virunga/Itombwe:TBD
| Freshwater Conservation |  |  | Habitat (Peatlands) | Poor farming practices around peatlands | 3.2.1 | Sustainable rice farming practices - peatland | By 2030, at least 75% of supported IPLC are practicing sustainable lowland rice farming practices in peatland areas, compared to the 2025 baseline. | Percent of targeted rice farmers practicing sustainable rice farming practice |  | Farming Practices monitoring database | Farming Practices monitoring | Annually | Farmers are willing to change practices There is availability of inputs, tools and resources that support the sustainable and non-destructive practices (Can we control this) | LTMN :17% Mangroves:TBD |  |  |  |  | LTMN :75% Mangroves:TBD
| Cross Cutting |  |  | Human Wellbeing | Human rights abuse | 4.1.1 | Conservation related complaints reduced | By 2030, the percentage of conservation related complaints related to CCO-supported conservation activities in target landscapes is reduced by at least 90%. | % of conservation related complaints related to CCO conservation activities | This will be measured on national level not on program level. Numerator: Number of conservation related complaints related to CCO conservation activities Divided by: Denominator: Number of conservation related complaints | Grievance mechanism database | Grievance mechanism system | Annually | There is confidence and trust in grievance redress mechanisms and are communities are using it to report | LTMN : 100% (10 complaints) Salonga: 100% (78 complaints) Mayombe/Luki:0% Vir / Itombwe:TBD | LTMN : 100% Salonga : 60% Mayombe/Luki:0% Vir / Itombwe:TBD | LTMN : 80% Sal : 50% Mayombe/Luki:0% Vir / Itombwe:TBD | LTMN : 50% Sal : 40% Mayombe/Luki:TBD Vir / Itombwe:TBD | LTMN : 30% Sal : 30% Mayombe/Luki:TBD Vir / Itombwe:TBD | LTMN : 10% Sal : 20% Mayombe/Luki:TBD Vir / Itombwe:TBD
| Cross Cutting |  |  | Human Wellbeing | Weak support to conservation | 4.1.2 | Positive perception on conservation improved | By 2030, at least 80% of targeted IPLCs in CCO-supported landscapes have a positive perception towards conservation projects/ideas. | % of targeted IPLC who have a positive perception towards CCO-supported conservation projects/ ideas | This will be measured on national level not on program level. | Perception survey data | Perception Survey | Annually | Conservation efforts produce tangible social or economic benefits for IPLCs (e.g., jobs, ecosystem services, access rights) | LTMN : TBD Sal : 63% Mayombe/Luki:TBD Vir / Itombwe:58% | LTMN : Sal : 63% Mayombe/Luki Vir / Itombwe | LTMN : Sal : 65% Mayombe/Luki Vir / Itombwe | LTMN : Sal : 66% Mayombe/Luki Vir / Itombwe | LTMN : Sal : 67% Mayombe/Luki Vir / Itombwe | LTMN : Sal : 68% Mayombe/Luki Vir / Itombwe:58%
| Cross Cutting |  |  | Human Wellbeing | Poverty | 4.1.4 | Household income increased | By 2030, targeted IPLC gain at least a 10% increase in household income from WWF-supported activities compared to the 2025 baseline | Average household income of targeted IPLC | Household income could be derived from IGA value chains, tourism, etc. | Household survey data | Household survey on WWF-supported activities | Midline (only measured half way and at the end) | Markets remain stable or grow for the products/services linked to WWF-supported activities Climate and environmental conditions do not severely disrupt production (e.g., droughts, disease, flooding) | LTMN :TBD Vir / Itombwe TBD
[9 empty] | Average total annual income gained by IPLC through direct employment in conservation related activities | The income that is paid to IPLC directly from conservation activities | HR salary data | HR salary checks | Annually |  | LTMN :TBD Vir / Itombwe TBD
| Cross Cutting |  |  | Human Wellbeing | Poverty | 4.1.5 | Access to materials of good life improved | By 2030, the number of targeted IPLC communities in WWF-supported landscapes having access to materials of good life has increased by at least 50% relative to the 2025 baseline | % of targeted IP&LC communities in the WWF-supported landscapes that have access to materials of good life | Access means the ability for the targeted group to make use of the materials. Materials of good life include portable water, health care, natural resources, food, education and traditional sites inside PAs. Communities refers to a group of people living in one village. Numerator: Number of targeted communities with access to the materials of a good life Divided by: Denominator: Number of targeted communities | Community survey as well as program data (with linked database) | Community surveys and program progress reports | Annually | Communities are not subjected to conflict, displacement, or governance instability that disrupt access to basic needs or services. | LTMN :TBD Vir / Itombwe TBD
| Cross Cutting |  |  | Human Wellbeing | Exclusion of IPLCs Inadequate or Weak policy on Protection of IPLC rights | 4.1.6 | policies & decisions promoting IPLC rights enacted | By 2030, at least one new or revised policies or decisions promoting the rights and interests of IPLC enacted with WWF support | Number of new or revised policy or decisions promoting the rights and interests of IP&LC enacted with WWF support | policies include decrees or other circular decisions | Policy and advocacy database (With validated analyses and report) | Policy and advocacy activities | Annually | The government is willing to engage with WWF and partners (incl. IPLC) in the propositions, enacting and reviewing of the policies/ decisions
[21 empty] | ------------------------- | -------------------------
[5 empty] | Freshwater Conservation | 3.1.1.1 |  | By 2030, 36 fishermen's structures will be trained and supported on sustainable fishing practices in spawning grounds. | Number of fishermen's structures supported on sustainable fishing practices | The total count of distinct, formally recognized fishermen's organizations (e.g., GICs - Common Initiative Groups, Cooperatives, or Village Management Committees) operating within the identified spawning ground zones that have received a defined package of support (e.g., governance training, fishing gear, legal registration assistance) from the project during the reporting period. |  |  |  |  | LTMN :0 Salonga:0 Virunga/Itombwe:0 | LTMN :0 Salonga:0 Virunga/Itombwe:0 | LTMN :5 Salonga:5 Virunga/Itombwe:0 | LTMN :4 Salonga:3 Virunga/Itombwe:0 | LTMN :3 Salonga:2 Virunga/Itombwe:2 | LTMN :3 Salonga:2 Virunga/Itombwe2
[5 empty] | Freshwater Conservation |  |  |  | Number of fishermen trained on sustainable fishing practices | The total count of unique individual fishermen/women operating in the target landscape who have physically attended and completed a formal training session on sustainable fishing practices. |  |  |  |  | LTMN : 0 Salonga:250 Virunga/Itombwe:0 | LTMN : 0 Salonga:50 Virunga/Itombwe:0 | LTMN : 50 Salonga:50 Virunga/Itombwe:0 | LTMN : 40 Salonga:50 Virunga/Itombwe:0 | LTMN :30 Salonga:50 Virunga/Itombwe:20 | LTMN : 30 Salonga:20 Virunga/Itombwe:20
[5 empty] | Freshwater Conservation | 3.1.1.2 |  | By 2030, at least 3 specific studies in the fields of freshwater, peatlands, carbon and species will be carried out at the SNP. | Number of studies carried out on freshwater, peatlands, carbon and/or species | The total count of distinct, scientific or technical research initiatives that have been fully executed, with final reports submitted, validated, and archived during the reporting period, which specifically investigate topics related to freshwater ecosystems, peatland hydrology/carbon stocks, carbon sequestration, or key species population/health within the boundaries of Salonga National Park (SNP)
[5 empty] | Freshwater Conservation | 3.1.1.4 |  | By 2030, community fisheries management committees established and operational. | Number community fisheries management committees established | The total count of distinct Community Fisheries Management Committees (CFMCs) or Local Fisheries Committees (CLP - Comités Locaux de Pêche) that have been formally constituted, have adopted internal bylaws/statutes, and are officially recognized by the local administration or traditional authority within the target landscape during the reporting period. |  |  |  |  | LTMN :0 Salonga:20 Virunga/Itombwe:0 | LTMN :0 Salonga:10 Virunga/Itombwe:0 | LTMN :5 Salonga:10 Virunga/Itombwe:0 | LTMN :4 Salonga:10 Virunga/Itombwe:0 | LTMN :3 Salonga:20 Virunga/Itombwe:2 | LTMN :3 Salonga:10 Virunga/Itombwe2
[5 empty] | Freshwater Conservation |  |  |  | Percent of established community fisheries management committees that have held atlest one meeting in a year | The proportion of the 'Established CFMCs' (from Indicator 1) that have convened at least one formal, documented governance or management meeting with a quorum of members present during the 12-month reporting period.
[5 empty] | Freshwater Conservation | 3.1.1.5 |  | By 2030, fisherment are provided with sustainable fishing gear (e.g., appropriate nets, no-fishing signs).?? | Number of supported fishermen provided with sustainable fishing gear | The total count of unique individual fishermen (or fisherwomen) operating within the target seascape/landscape who have physically received a verified package of legal, sustainable fishing equipment (e.g., regulation mesh-size nets, circle hooks, safety gear) provided by the project during the reporting period |  |  |  |  | LTMN : 0 Salonga:0 Virunga/Itombwe:0 | LTMN : 0 Salonga:0 Virunga/Itombwe:0 | LTMN : 50 Salonga:50 Virunga/Itombwe:0 | LTMN : 40 Salonga:30 Virunga/Itombwe:0 | LTMN :30 Salonga:20 Virunga/Itombwe:20 | LTMN : 30 Salonga:20 Virunga/Itombwe:20
[6 empty] | 3.1.1.6 |  | Training modules and workshops conducted on sustainable fishing techniques in local languages. | Number of fishermen trained on sustainable fishing practices | [5 empty] | LTMN : 0 Salonga:250 Virunga/Itombwe:0 | LTMN : 0 Salonga:50 Virunga/Itombwe:0 | LTMN : 50 Salonga:50 Virunga/Itombwe:0 | LTMN : 40 Salonga:50 Virunga/Itombwe:0 | LTMN :30 Salonga:50 Virunga/Itombwe:20 | LTMN : 30 Salonga:50 Virunga/Itombwe:20
[6 empty] | 3.1.1.7 |  | Community fisheries management committees established and operational. | # of fisheries committees established or capacitated in sustainable management of local fisheries | [5 empty] | LTMN :0 Salonga:0 Virunga/Itombwe:0 | LTMN :0 Salonga:0 Virunga/Itombwe:0 | LTMN :5 Salonga:5 Virunga/Itombwe:0 | LTMN :4 Salonga:3 Virunga/Itombwe:0 | LTMN :3 Salonga:2 Virunga/Itombwe:2 | LTMN :3 Salonga:2 Virunga/Itombwe2
[6 empty] | 3.1.1.8 |  | Distribution of sustainable fishing gear (e.g., appropriate nets, no-fishing signs). | # of fisheries adopting sustainable gear | [5 empty] | LTMN :0 Salonga:4923 Virunga/Itombwe:0 | LTMN :0 Salonga:200 Virunga/Itombwe:0 | LTMN :0 Salonga:200 Virunga/Itombwe:0 | LTMN :0 Salonga:200 Virunga/Itombwe:0 | LTMN :0 Salonga:200 Virunga/Itombwe:0
[5 empty] | Freshwater Conservation | 3.1.1.9 |  | By 2028, monitoring and evaluation system established for spawning grounds. | Existence of a functional monitoring system for fishing activities and spawning grounds | The verified operational status (Yes/No) of a dedicated, standardized Monitoring & Evaluation (M&E) framework designed specifically to track fishing effort and ecological health in identified spawning grounds. To be classified as 'Functional,' the system must meet four criteria: (1) Validated Data Collection Protocols, (2) Trained data collectors in place, (3) An active Database (digital or paper) receiving data, and (4) At least one analytical report produced during the reporting period |  |  |  |  | LTMN :0 Salonga:0 Virunga/Itombwe:0
[5 empty] | Freshwater Conservation | 3.1.1.10 |  | Enforcement collaboration protocols with local authorities strengthened. | # of joint monitoring missions conducted annually | The total count of distinct, official surveillance or law enforcement patrol missions that were planned, financed, and executed jointly by project-supported teams (e.g., Community Ecoguards or Park Rangers) AND sworn representatives of Local Authorities (e.g., Police, Gendarmerie, or Ministry Wildlife Officers) within the target landscape during the reporting period |  |  |  |  | LTMN :0 Salonga:6 Virunga/Itombwe:0 | LTMN :0 Salonga:6 Virunga/Itombwe:0 | LTMN :0 Salonga:6 Virunga/Itombwe:0 | LTMN :0 Salonga:6 Virunga/Itombwe:0 | LTMN :0 Salonga:5 Virunga/Itombwe:0
[5 empty] | Freshwater Conservation | 3.1.1.11 |  | By 2030, 75% of IPs/LCs are supported in sustainable lowland rice farming practices. | % of IPs/LCs supported in sustainable lowland rice farming practices in peatlands | The proportion of Indigenous Peoples (IP) and Local Community (LC) households residing in the target landscape who have received verifiable technical training, agricultural inputs (e.g., adapted seeds), or extension support specifically focused on sustainable, climate-smart lowland rice farming techniques compatible with peatland conservation (e.g., paludiculture or zero-drainage methods) during the reporting period |  |  |  |  | LTMN :17% Salonga:0 Virunga/Itombwe:0
[5 empty] | Freshwater Conservation | 3.1.1.12 |  | By 2028, demonstration plots established for climate-resilient rice farming. | Number of demonstration plots showcasing sustainable rice farming techniques | The total count of distinct, geo-referenced agricultural plots that have been demarcated, planted, and actively managed using specific climate-resilient and sustainable rice farming protocols (e.g., System of Rice Intensification - SRI, short-cycle varieties, or zero-drainage paludiculture), specifically established to serve as learning sites for surrounding communities during the reporting period
[5 empty] | Freshwater Conservation | 3.1.1.13 |  |  | Number of IPLC trained through the demonstration plot for climate resilient rice farming | The total count of unique individual Indigenous Peoples (IP) and Local Community (LC) members who have physically attended and completed a structured practical training session or Farmer Field School module conducted at a demonstration plot, focusing on climate-resilient techniques
[5 empty] | Freshwater Conservation | 3.1.1.14 |  | By 2030, Farmer field schools rolled out in key peatland zones. | Number of farmers attending farmer field school per season | The total count of unique individual farmers residing in the identified 'Key Peatland Zones' who have regularly attended and participated in the structured curriculum of a Farmer Field School (FFS) session cycle during the defined agricultural season.
[5 empty] | Freshwater Conservation | 3.1.1.15 |  | By 2030, guidelines/manuals developed for sustainable peatland agriculture. | Number of farmers provided with sustainable peatland agriculture guides or manuals | The total count of unique individual farmers operating in identified peatland zones who have physically received a verified copy (printed or digital) of the standardized 'Sustainable Peatland Agriculture Guide/Manual' produced by the project during the reporting period.
[5 empty] | Freshwater Conservation | 3.1.1.16 |  | By 2030, Farmers are provided with improved rice seed varieties and eco-friendly inputs distributed. | Number of farmers provided with improved rice seeds or organic inputs | The total count of unique individual farmers operating within the target landscape who have physically received a verified package of approved agricultural inputs (specifically high-yielding/climate-resilient rice seed varieties OR certified organic fertilizers/pest control products) provided by the project during the reporting period. |  |  |  |  | LTMN :0 Salonga:80 Virunga/Itombwe:0 | LTMN :0 Salonga:80 Virunga/Itombwe:0 | LTMN :0 Salonga:80 Virunga/Itombwe:0 | LTMN :0 Salonga:80 Virunga/Itombwe:0 | LTMN :0 Salonga:80 Virunga/Itombwe:0 | LTMN :0 Salonga:80 Virunga/Itombwe:0
[5 empty] | Freshwater Conservation | 3.1.1.17 |  | By 2029, Peatland management plans developed with community input. | Number of Peatland management plans developed | The total count of distinct, finalized site-specific Management Plans governing identified peatland areas that have been fully drafted, validated by the project technical team, and—crucially—incorporate documented evidence of participatory development (input and validation) from the local communities and Indigenous Peoples living within or reliant upon that peatland zone during the reporting period |  |  |  |  | LTMN:0
[5 empty] | Freshwater Conservation | 3.1.1.18 |  | Functional grievance redress mechanisms established in all target landscapes. | % of grievances resolved within agreed timelines | [5 empty] | LTMN/Malebo :100% Salonga : 70% Mayombe/Luki: 30% | LTMN/Malebo :100% Salonga : 80% Mayombe/Luki: 100% | LTMN/Malebo :100% Salonga : 100% Mayombe/Luki: 100% | LTMN/Malebo :100% Salonga : 100% Mayombe/Luki: 100% | LTMN/Malebo :100% Salonga : 100% Mayombe/Luki: 100% | LTMN/Malebo :100% Salonga : 100% Mayombe/Luki: 100%
[5 empty] | Freshwater Conservation | 3.1.1.19 |  | Training for WWF and partner staff on Free, Prior, and Informed Consent (FPIC). | # of FPIC trainings conducted for WWF and partner staff
[5 empty] | Freshwater Conservation | 3.1.1.20 |  | Biannual community consultations and feedback meetings held. | % of meetings with documented minutes, including agreed action points and responsible persons
[5 empty] | Freshwater Conservation | 3.1.1.21 |  | Conflict resolution protocols integrated into all project activities. | # of conflict and benefit sharing mechanisms developed and adopted
[5 empty] | Freshwater Conservation | 3.1.1.22 |  | Co-developed conservation action plans with IPLCs. | # of conservation strategies, plans, action plans that incorporate updated threat analyses. (CAL_OP3.2.4)
[5 empty] | Freshwater Conservation | 3.1.1.23 |  | Incentive-based conservation schemes (e.g., community ecotourism) launched. | Number of benefit-sharing schemes for coastal communities promoting wildlife coexistence
[5 empty] | Freshwater Conservation | 3.1.1.24 |  | Cultural integration and communication campaigns developed (e.g., radio programs, storytelling). | # of communication campaigns delivered, supported by flagship knowledge and advocacy materials promoting EPL, MFF, and Footprint landscapes.
[5 empty] | Freshwater Conservation | 3.1.1.25 |  | Community conservation champions identified and supported. | # of supporting organisations with improved technical and organisational capacity to support NRM, livelihood, or conservation actions. (CAL_OP7.1.3)
[5 empty] | Freshwater Conservation | 3.1.1.26 |  | Scholarships and school supplies provided to students from IPLC communities. | % of targeted IP&LC communities in the WWF-supported landscapes that have access to materials of good life
[5 empty] | Freshwater Conservation | 3.1.1.27 |  | School feeding programs supported in partnership with local education authorities. | # of partnerships sustained after 12 months of initiation. (CAL_OP5.2.5b)
[5 empty] | Freshwater Conservation | 3.1.1.29 |  | Teacher training and retention programs implemented in rural schools. | # of trainings on climate smart technologies and practices
[5 empty] | Freshwater Conservation | 3.1.1.30 |  | Education sensitisation campaigns conducted for parents/guardians. | Number of campaigns conducted annually
[5 empty] | Freshwater Conservation | 3.1.1.31 |  | Livelihood diversification programs introduced (e.g., beekeeping, agroforestry, crafts). | percentage of target households that meet the minimum set human wellbeing score | [5 empty] | LTMN :0 Salonga:0 Virunga/Itombwe:0 | LTMN :0 Salonga:0 Virunga/Itombwe:0 | LTMN :0 Salonga:0 Virunga/Itombwe:0 | LTMN :0 Salonga:0 Virunga/Itombwe:0 | LTMN :0 Salonga:0 Virunga/Itombwe:0 | LTMN :0 Salonga:0 Virunga/Itombwe:0
[5 empty] | Freshwater Conservation | 3.1.1.32 |  | Market access support provided (e.g., transport, cooperatives, value chain analysis). | Number of value chains developed in targeted communities | [5 empty] | LTMN :0 Salonga:1 Virunga/Itombwe:0 | LTMN :0 Salonga:1 Virunga/Itombwe:0 | LTMN :0 Salonga:1 Virunga/Itombwe:0 | LTMN :0 Salonga:1 Virunga/Itombwe:0 | LTMN :0 Salonga:1 Virunga/Itombwe:0 | LTMN :0 Salonga:1 Virunga/Itombwe:0
[5 empty] | Freshwater Conservation | 3.1.1.33 |  | Microfinance and savings group models scaled in target areas. | # & % of microfinance services established | [5 empty] | LTMN :0 Salonga:27 Virunga/Itombwe:0 | LTMN :0 Salonga:27 Virunga/Itombwe:0 | LTMN :0 Salonga:27 Virunga/Itombwe:0 | LTMN :0 Salonga:27 Virunga/Itombwe:0 | LTMN :0 Salonga:27 Virunga/Itombwe:0 | LTMN :0 Salonga:27 Virunga/Itombwe:0
[5 empty] | Freshwater Conservation | 3.1.1.34 |  | Business training provided for local entrepreneurs and cooperatives. | Number of fishermen trained on sustainable fishing practices
[5 empty] | Freshwater Conservation | 3.1.1.36 |  | Community action plans developed to identify “materials of good life” (e.g., clean water, energy). | # of consultation meetings conducted
[5 empty] | Freshwater Conservation | 3.1.1.37 |  | Infrastructure support projects implemented (e.g., boreholes, solar systems).- Separate per infrastr | # of water infrastructure that integrate ecological designs and/or social safeguard standards and or recomendations technical assessments | [5 empty] | LTMN :0 Salonga:4 Virunga/Itombwe:0 | LTMN :0 Salonga:4 Virunga/Itombwe:0 | LTMN :0 Salonga:4 Virunga/Itombwe:0 | LTMN :0 Salonga:4 Virunga/Itombwe:0 | LTMN :0 Salonga:4 Virunga/Itombwe:0 | LTMN :0 Salonga:4 Virunga/Itombwe:0
[5 empty] | Freshwater Conservation | 3.1.1.38 |  | Partnerships established with service providers and government institutions. | # of formal agreements to support transboundary conservation initiatives
[5 empty] | Freshwater Conservation | 3.1.1.39 |  | Partnerships established with service providers and government institutions. | # of formal agreements to support transboundary conservation initiatives | [5 empty] | LTMN:2
[5 empty] | Freshwater Conservation | 3.1.1.40 |  | Regular tracking surveys on well-being and basic needs conducted. | # of surveys conducted
[5 empty] | Freshwater Conservation | 3.1.1.41 |  | Policy briefs and legal studies on IPLC rights and tenure developed. | # of policy and strategy documents supported by WWF
[5 empty] | Freshwater Conservation | 3.1.1.42 |  | Multi-stakeholder platforms established for policy dialogue. | # of multi-stakeholder policy dialogues, consultations, or technical working groups facilitated by WWF UCO to strengthen forest policies and legal frame | [5 empty] | LTMN:0
[5 empty] | Freshwater Conservation | 3.1.1.43 |  | Technical and advocacy support provided to relevant government agencies. | # of multi-stakeholder policy dialogues, consultations, or technical working groups facilitated by WWF UCO to strengthen forest policies and legal frame | [5 empty] | LTMN:0
[5 empty] | Freshwater Conservation | 3.1.1.44 |  | Capacity-building workshops held for IPLC leaders on rights-based advocacy. | Number of capacity building on innovation conducted | [5 empty] | LTMN:0
[5 empty] | Freshwater Conservation | 3.1.1.45 |  | The strategy of provinces having peatlands in common benefiting from support in land use planning a | Number of Peatland management plans developed | [5 empty] | LTMN:0 | LTMN:0 | LTMN:1 | LTMN:0 | LTMN:0
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Bruno Xavier Ilunga The OSP risk assessment needs to be completed as already mentioned before
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need to understand what 'intact' means and how it will be measured

## Result Chain (hidden)
| Conservation Focus of the Programme | Priority Threats / Other Factors | Result ID | Program Outcomes | Relevant Geographic Scope | Relevant Thematic Scope | Annual Result - Year 1 | Output (Annual Result) - Year 2 | Output (Annual Result) - Year 3 | Output (Annual Result) - Year 4 | Output (Annual Result) - Year 5 | Key Assumptions & Risks | Sustainability & Exit Plan
READ Me First | Please copy the list of Conservation Focus from the previous tab. | For each Conservation Focus please list the priority threat (or other factors). Please use one line for each threat/factor. If a single threats affect more than one Conservation Focus, please list all the relevant conservation focus/focal interest under the column B. CMP Direct Threat Classification is available here - https://docs.google.com/spreadsheets/d/1rJSNz1LG_KOqoudVFglodx47HZ9LR-M6iVlRYMvn9Wk/edit#gid=310830663 Please ensure that priority threats/other factors are subset of those selected under the OSP. You may define further in detail. |  | Please Describe the desired reduction of threats (or changes to the identified factors). Please make sure the statement is SMART. | Please indicate the relevant Geographic Scope for each Outcome statement. Ensure to use one of the Geographic scope identified in the Scope tab of OSP Design Template. | Please indicate the relevant Thematic Scope for each Goal statement. Ensure to use one of the Thematic scope identified in the Scope tab of OSP Design Template. | Please define measurable Programme Annual Results which are milestones in achieving Programme outcomes. Therefore Programme Outcome must be embedded in the Programme Outputs. Outputs must represent tangible deliverables, within our area of control, that are critical to achieving the Programme Outcomes, in line with the Theory of Change. If there are areas of innovation and/or research, please make sure to include those outputs and activities as well. See the guidance on the approach to the Programme and Project Planning |  |  |  |  | Please identify the key assumptions that underpin the logical sequences linking Outputs, and Outcomes, and to one or more Goals Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment. WWF policies do not require risk assessment at program level but at Office level and at Project level. However each Program team is encouraged to perform Program Risk assessment. Use the Office risk register template in such case. | Please describe how your program aims to ensure the sustainability of the program outcome and an eventual exit by WWF. See Guidance by PPMS Step - Element 2.3
Example | Coral Reef Marine priority species | Overfishing / unsustainable fisheries |  | By 2030, fisheries management plans are in place (implemented & monitored) in 80% of coastal fisheries in ABC coastal communities. | Beta seascape | Ocean | Awareness of unsustainable fisheries increased in ABC coastal communities by 50% | Technical capacity of 10 fisheries communities built on fisheries management plan | 5 fisheries communities developed fisheries management plan | 4 fisheries communities developed fisheries management plan |  | Local communities can improve (or at least maintain) the economic state after the fisheries management plan. | Creation of alternative sustainable income to ensure that the sustainable implementation of the fisheries management plan. Also, inclusion of CSO (and their capacity building) in the project implementation to enable the eventual exit of WWF and transition of responsibility to the local CSO.
[5 empty] | Beta seascape | Ocean | Baseline assessment of current fisheries practices conducted for 10 fisheries in ABC coastal community |  |  | 50% of coastal fisheries are implementing and monitoring fisheries management plan | 80% of coastal fisheries are implementing and monitoring fisheries management plan
Note on I1: @hwilliams@wwfint.org, also here we should be align the language _Assigned to hwilliams@wwfint.org_ -Philip Kahuho

## Programme Implementation Plan
| Outcome ID | Outcome Name | Results ID | Output Statement | FY26 Cost | FY27 Cost | FY28 Cost | FY29 Cost | FY30 Cost | Total Output Cost + Management fee | Current Project (CPM Project #) | Target Funding Source
|  | Sustainable fishing practices improved | 3.1.1.1 | By 2030, 36 fishermen's structures will be supported in sustainable fishing practices in spawning grounds. | 85000 | 85000 | 85000 | 85000 | 85000 | 478125
|  | Sustainable fishing practices improved | 3.1.1.2 | By 2030, at least 3 specific studies in the fields of freshwater, peatlands, carbon and species will be carried out at the SNP. | 0 | 40000 | 0 | 40000 | 40000 | 135000
|  | Sustainable fishing practices improved | 3.1.1.3 | Training modules and workshops conducted on sustainable fishing techniques in local languages. | 40000 | 40000 | 40000 | 40000 | 40000 | 225000
|  | Sustainable fishing practices improved | 3.1.1.4 | Community fisheries management committees established and operational. | 50000 | 50000 | 50000 | 50000 | 50000 | 281250
|  | Sustainable fishing practices improved | 3.1.1.5 | Distribution of sustainable fishing gear (e.g., appropriate nets, no-fishing signs). | 100000 | 100000 | 100000 | 100000 | 100000 | 562500
|  | Sustainable fishing practices improved | 3.1.1.6 | Monitoring and evaluation system established for spawning grounds. | 40000 | 40000 | 40000 | 40000 | 40000 | 225000
|  | Sustainable fishing practices improved | 3.1.1.7 | Enforcement collaboration protocols with local authorities strengthened. | 40000 | 40000 | 40000 | 40000 | 40000 | 225000
|  | Sustainable rice farming practices - peatland | 3.2.1.1 | By 2030, 75% of IPs/LCs are supported in sustainable lowland rice farming practices. | 30000 | 30000 | 30000 | 30000 | 30000 | 168750
|  | Sustainable rice farming practices - peatland | 3.2.1.2 | Demonstration plots established for climate-resilient rice farming. | 50000 | 50000 | 50000 | 50000 | 50000 | 281250
|  | Sustainable rice farming practices - peatland | 3.2.1.3 | Farmer field schools rolled out in key peatland zones. | 40000 | 40000 | 40000 | 40000 | 40000 | 225000
|  | Sustainable rice farming practices - peatland | 3.2.1.4 | Guidelines/manuals developed for sustainable peatland agriculture. | 60000 | 60000 | 60000 | 60000 | 60000 | 337500
|  | Sustainable rice farming practices - peatland | 3.2.1.5 | Improved rice seed varieties and eco-friendly inputs distributed. | 92000 | 92000 | 40000 | 40000 | 40000 | 342000
|  | Sustainable rice farming practices - peatland | 3.2.1.6 | Peatland management plans developed with community input. | 80000 | 80000 | 40000 | 50000 | 0 | 281250
|  | Conservation related complaints reduced | 4.1.1.1 | Functional grievance redress mechanisms established in all target landscapes. | 0 | 0 | 0 | 0 | 0 | 0
|  | Conservation related complaints reduced | 4.1.1.2 | Training for WWF and partner staff on Free, Prior, and Informed Consent (FPIC). | 0 | 0 | 0 | 0 | 0 | 0
|  | Conservation related complaints reduced | 4.1.1.3 | Biannual community consultations and feedback meetings held. | 0 | 0 | 0 | 0 | 0 | 0
|  | Conservation related complaints reduced | 4.1.1.4 | Conflict resolution protocols integrated into all project activities. | 0 | 0 | 0 | 0 | 0 | 0
|  | Positive perception on conservation improved | 4.1.2.1 | Co-developed conservation action plans with IPLCs. | 80000 | 80000 | 80000 | 80000 | 80000 | 450000
|  | Positive perception on conservation improved | 4.1.2.2 | Incentive-based conservation schemes (e.g., community ecotourism) launched. | 0 |  |  |  |  | 0
|  | Positive perception on conservation improved | 4.1.2.3 | Cultural integration and communication campaigns developed (e.g., radio programs, storytelling). | 0 | 30000 | 30000 | 30000 | 30000 | 135000
|  | Positive perception on conservation improved | 4.1.2.4 | Community conservation champions identified and supported. | 10000 | 10000 | 10000 | 10000 | 10000 | 56250
|  | Students supported | 4.1.3.1 | Scholarships and school supplies provided to students from IPLC communities. | 0 | 0 | 0 | 0 | 0 | 0
|  | Students supported | 4.1.3.2 | School feeding programs supported in partnership with local education authorities. | 0 | 0 | 0 | 0 | 0 | 0
|  | Students supported | 4.1.3.3 | Teacher training and retention programs implemented in rural schools. | 40000 | 40000 | 40000 | 40000 | 40000 | 225000
|  | Students supported | 4.1.3.4 | Education sensitisation campaigns conducted for parents/guardians. | 0 | 0 | 0 | 0 | 0 | 0
|  | Household income increased | 4.1.4.1 | Livelihood diversification programs introduced (e.g., beekeeping, agroforestry, crafts). | 0 | 0 | 0 | 0 | 0 | 0
|  | Household income increased | 4.1.4.2 | Market access support provided (e.g., transport, cooperatives, value chain analysis). | 0 | 0 | 0 | 0 | 0 | 0
|  | Household income increased | 4.1.4.3 | Microfinance and savings group models scaled in target areas. | 300000 | 250000 | 300000 | 300000 | 300000 | 1631250
|  | Household income increased | 4.1.4.4 | Business training provided for local entrepreneurs and cooperatives. | 40000 | 40000 | 40000 | 40000 | 40000 | 225000
|  | Access to materials of good life improved | 4.1.5.1 | Community action plans developed to identify “materials of good life” (e.g., clean water, energy). | 0 | 0 | 0 | 0 | 0 | 0
|  | Access to materials of good life improved | 4.1.5.2 | Infrastructure support projects implemented (e.g., boreholes, solar systems).- Separate per infrastructure type | 0 | 0 | 0 | 0 | 0 | 0
|  | Access to materials of good life improved | 4.1.5.3 | Partnerships established with service providers and government institutions. | 50000 | 50000 | 80000 | 80000 | 72000 | 373500
|  | Access to materials of good life improved | 4.1.5.4 | Regular tracking surveys on well-being and basic needs conducted. | 0 | 20000 | 20000 | 20000 | 20000 | 90000
|  | policies & decisions promoting IPLC rights enacted | 4.1.6.1 | Policy briefs and legal studies on IPLC rights and tenure developed. | 50000 | 50000 | 50000 | 50000 | 50000 | 281250
|  | policies & decisions promoting IPLC rights enacted | 4.1.6.2 | Multi-stakeholder platforms established for policy dialogue. | 0 | 0 | 0 | 0 | 0 | 0
|  | policies & decisions promoting IPLC rights enacted | 4.1.6.3 | Technical and advocacy support provided to relevant government agencies. | 100000 | 92000 | 138000 | 89000 | 90000 | 572625
|  | policies & decisions promoting IPLC rights enacted | 4.1.6.4 | Capacity-building workshops held for IPLC leaders on rights-based advocacy. | 51000 | 0 | 0 | 0 | 0 | 57375
|  | policies & decisions promoting IPLC rights enacted | 4.1.6.5 | The strategy of provinces having peatlands in common benefiting from support in land use planning allowing the preservation of peatlands is developed | 110000 | 80000 | 85000 | 85000 | 85000 | 500625
Total Annual Cost + Management Fee |  |  |  |  | 1730250 | 1675125 | 1674000 | 1675125 | 1611000 | 8365500
Note on F15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CaptCaptured under previous programmes ured under previous programmes
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under previous programmes
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under previous programmes
Note on F18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under previous programmes
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under programmes
Note on F23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under previous programmes
Note on F27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under previous grogammes
Note on F28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under previous programme
Note on F31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under previous prgramme
Note on F32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under previous grogramme
Note on F36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Captured under previous programmes

## Learning Questions
Learning Questions
READ Me First | Please articulate specific learning questions that your program will regularly reflect on for the learning priority. Max 100 words.
Example | - To what extent are the program's activities effective in achieving the planned results? - What worked and what didn’t? - Were there any unintended consequences? (positive or negative/ internal or external) - Were there any emergent results? (more than the planned results)