## 1. Resource Acquisition Priorit (hidden)
Resource Acquisition Focus and Analysis: A clear description of the focus/focal interests in resource acquisition (e.g. donor segments, channels, key donors). A short description of the current and desired future status of each focus / focal interest and why they are prioritised, taking into account and cross-calibrating with Conservation Priorities. A description of the context and trends affecting the selected focal interests including direct threats, indirect threats, opportunities, and enabling conditions. Resource Acquisition Goals & Outcomes: A list of SMART Goals describing the desired impact(s) and articulating the desired changes in the prioritised threats and/or factors affecting the Focal Interests. Resource Acquisition Strategies & Targets: A list of prioritised strategies that are optimal in terms of income generation, return on investment, expected impact on conservation priorities, etc. Operational Goals and Objectives, and Optimal Strategies may be organised by key areas such as the following, but limited to: Donor segment (e.g. PSP, Foundations, HNW, Mass) Donor channel (e.g. digital) Specific donors (e.g. USAID, EU)
| Resource Aquisition Focus | Problem Statement | Key Attribute | Relevant Geographic Scope | Relevant Thematic Scope | OSP Goal Short Name | OSP Goal Statement | Comments
READ Me First | Identify key resource acquisition areas your office will prioritize, informed by historical financial data, donor mapping and strategic partner/stakeholder mapping, such as donor diversification, private sector engagement, and innovative fundraising models. Assess gaps in current funding streams, target donor segments (e.g., institutional donors, private sector, high-net-worth individuals), and explore new opportunities for funding expansion. Ensure priority areas are aligned with both immediate funding needs and long-term financial sustainability goals. | Write a problem statement briefly explaining why this focus area is crucial to your organization's financial health. Briefly outline key challenges your office faces such as over-reliance on a limited donor base, dependence on short-term funding cycles, or insufficient in-country fundraising capacity. Address how these issues hinder your ability to scale projects and secure sustainable, long-term funding, and underscore the need for diversification and growth in your resource acquisition strategy. | Identify a key attribute critical to each resource acquisition focus, such as income diversification, donor engagement, or capacity building. Consider how ineffective management of this attribute could jeopardize your strategy and negatively impact the long-term sustainability of your funding efforts. | Specify the geographic scope of your resource acquisition efforts, whether national, regional, or international. Consider focusing on national funding while exploring opportunities in areas with regional, global or high conservation impact/value. | Select the thematic scope for each Resource Acquisition Focus, such as Finance, External Relations, or Partnerships. Ensure it aligns with organizational priorities and supports operational goals. | Provide a concise, 20-word name for each Resource Acquisition Focus goal, capturing its purpose (e.g., "Diversify Funding Sources"). This aids communication and aligns with the OSP. | In 100 words or less, describe the desired future state of the resource acquisition focus. Outline what success looks like (e.g., financial stability, donor base expansion, innovative funding models). Be specific about outcomes to achieve by 2027, ensuring the goal is SMART (Specific, Measurable, Achievable, Relevant, Time-bound).
Example | Donor Concentration | Over-reliance on a narrow set of international PSP donors has limited WWF XXX flexibility and long-term sustainability. Vulnerable to shortfalls if key donors withdraw. | Expanding the donor base across sectors for resilient and flexible funding streams. | National, with international focus. | Finance, External Relations/Partnerships | Secure Funds | WWF XXX will "reduce reliance on PSP sector through diversification of funding streams." That would then lead to a series of outcomes (at current level of detail the outcome would eb the same as the goal), such as; (i) Reliance on PSP has been reduced to 60% of total portfolio value to avoid over concentration; (ii) increase major donor funding proportion from 5% to 15% to offset reliaunce on PSP funding; (iii) increase HNWI donor funding from 0% to 5% to ensure further diversification and creat an additional funding stream." Then, Outputs would be things like; "Hire HNWI expertise to open up opportunites with this donor stream; ." No need for activity level design.
Donor Diversification
Strategic Partnerships / Engagement
Long-Term Sustainable Funding
Innovative Fundraising Models
Effective Donor Stewardship
In-Country Fundraising Capacity
Note on F4: ====== ID#AAABnbip6x8 (2025-07-16 14:08:17) The way the OSP process has been led, the thematic scope has been identified and RA has to be tailored according to conservation priorities - not the other way around. -Lene Andersen

## Revised Version (hidden)
Context and Donor Trends | Localization | Financial Historical Analysis | Donor Engagement Plan | Key Attribute | OSP Goal Short Name | OSP Goal Statement
Utilize existing donor strategies and reports to assess global and regional funding trends and priorities. Engage local stakeholders to understand how these trends influence the national donor landscape and identify opportunities to expand and diversify your donor base. Also, evaluate funding shifts by assessing the stability of funding streams and identifying new gaps or emerging opportunities. Finally, use this information to develop targeted strategies that align your resource acquisition efforts with both global and local donor priorities to enhance WWF’s position in securing new funding opportunities. | To build strong local partnerships, integrate localization into your resource acquisition strategy by a) mapping and engaging local NGOs, community organizations, and stakeholders with valuable regional knowledge and networks, b) provide resources, capacity development and mentoring support to strengthen the fundraising and project management capabilities of local partners, and where possible c) collaborate with local partners on proposals and donor engagement strategies to align shared objectives with the local context, fostering long-term relationships and trust. | Based on your financial analysis and SWOT analysis, review past income trends and funding streams to identify growth and diversification opportunities by a) analyzing historical income, growth, grants, and success rates to understand financial performance and areas for improvement, b) assessing missed opportunities and reasons for unsuccessful proposals (e.g., capacity, quality control), c) identifying top contributors and assess risks related to income concentration by donor, sector, or segment, and exploring opportunities to diversify funding sources, especially within donor segments such as PSP, Foundations, Corporates, and HNWI. | Develop donor engagement plans for your top 10 donors to effectively engage and enhance relationships and secure sustained funding by a) researching donors' thematic focus, decision-making processes, funding preferences, and communication styles, b) review the Office Strategic Plan (OSP) and identify shared objectives with donors, then c) develop individual plans for each key donor, outlining specific strategies for outreach, communication, and collaboration. Focus mainly on donors identified through your donor mapping exercises. | Identify a key attribute critical to each resource acquisition focus, such as income diversification, donor engagement, or capacity building. Consider how ineffective management of this attribute could jeopardize your strategy and negatively impact the long-term sustainability of your funding efforts. | Provide a concise, 20-word name for each Resource Acquisition goal that clearly captures its purpose (e.g., "Diversify Funding Sources"). This simplifies communication and aligns with the Office Strategic Plan (OSP). | In 100 words or less, describe the desired future state of the resource acquisition focus. Outline what success looks like (e.g., financial stability, donor base expansion, innovative funding models). Be specific about outcomes to achieve by 2027, ensuring the goal is SMART (Specific, Measurable, Achievable, Relevant, Time-bound).

## Resource Acquistion Scoping (hidden)
| Funding Needs Analysis/Problem Statements | Donor Landscape Assessment | Partnership & Localisation Opportunities | SWOT Analysis | Theory of Change | Goal | RA Outcome Short Name | RA Outcome Statement
READ Me First | Begin by identifying the main resource requirements and risks to delivery of the OSP's conservation and operational activities. Focus should be on securing funding gaps and maintaining existing funding streams, donor diversification, donor stewardship, resource aquisition capacity and cost recovery | Review and summarise relevant donor trends, funding priorities, and potential funding sources at country, regional and national levels relevant to the needs analysis | Outline potential partnerships including localisation opportunites to address funding needs | Based on your SWOT analysis, identify the barriers and opportunites that can be addressed and leveraged. | Draft a Theory of Change (ToC) based on the key areas of work required for your Resource Aquisition Strategy as identifed in the lines ot the left. Note this will be copied to the MEL framework in the next tab as your Theory of Change. The ToC can be wrriten as a series of IF, AND, THEN statements | Put in your overall Resource Aquisition goal here based on the key areas of work identified and anlysed to the left. Note this will be copied to the MEL framework in the next tab as your goal. | Provide a concise, 10-word name for each Resource Acquisition Outcome that clearly captures its purpose (e.g., "Diversify Funding Sources") and links to the analysis in this line to the left. | In 50 words or less, describe the desired future state of the resource acquisition focus. Outline what success looks like (e.g., financial stability, donor base expansion, innovative funding models). Be specific about outcomes to achieve by 2027, ensuring it is SMART (Specific, Measurable, Achievable, Relevant, Time-bound). Note this will be copied to the MEL framework in the next tab as your goal.
Example | Climate Program has a $2M funding gap for delivering NbS strategy within the OSP | Significant investments in climate-proofing livelihoods in country from ODA donors are being made in country. |  | Lack of track record in NbS space; small team; good relationships with Ministry of Environment/Agriculture leadership and provinvcial departments | IF we can identify a pipeline of credible projects against our OSP technical priorities AND ensure a diversified portfolio beyond PSP AND secure and capacitate a RA team AND develpp and deliver a robust localisation strategy, THEN we will be able to deliver the OSP Strategic Priorities. | Country X has a diversified and sustainable funding base for delivering the Strategic Plan, supported by in-house capacity and leveraging the localisation agenda | Secure NbS funding for climate program delivery | By 2027, a pipeline of credible and competitive NbS related opportunites will be created.
Example | Over reliance on PSP donors in funding mix, with >90% PSP in portfolio | Shrinking investment in country from PSP donors due to transition to middle income country with some current PSP donors set to exit or localise funding | Opportunites to engage implemetnation partner x as a strategic partner who can more readily access localisation funding streams | High donor concentration means high risk should donors exit; high capacity in office for PSP submissions but low capacity in HNWI and corporate engagement |  |  | Reduce reliance on PSP sector through diversification of funding streams | By 2030, PSP portfolio will comprise <80% of funding base without a reduction in total portfolio value through increased diversification into other donor segments.
Example | Increased ambition in total OSP budget from previous years requires additional capacity to secure funding for its delivery | Organisational Development support in WWF network has increased, but still restricted to a few NOs and AP25. Current core budget insufficient for hiring new capacity |  | Low engagenment with OD issues in network; poor conversion rate of Corporate proposals; growing recognition of the growth opportunity in country by network |  |  | Increase capacity in office resource aquisition to deliver the OSP funding requirements | By 2028, a resource aquisition team will be designed, fully funded and onboarded with capacities in PSP, Major Donors and Trusts and Foundations.
Example | PSP donors increasing requiring significant resources allocated to local organisations or bypassing INGOs entirely | PSP donors increasing requiring significant resources allocated to local organisations or bypassing INGOs entirely |  | Lack of strategic partnershps in place; work extensively with local partners; lack of financial capacity in partners doesnt meet WWF DD requirements; |  |  | Build strategic partnerships with local organisations for shared delivery of localisation agenda | By 2029, the CO will have in place and be implementing a localisation strategy which includes strategic partnerships which deliver on the OSP objectives with 25% of funds through local partners .

## DRC Resource Aquistion MEL
RA M&E plan | # | Description | Indicator | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Assumptions | Means of Verification | Data Collection Tool | Frequency of Measurement | Risks | Location | Responsible
Resource Acquisition Theory of Change
Resource Acquisition Goal | 1 | By 2030, WWF DRC has a diversified and sustainable funding base for delivering the Strategic Plan, supported by in-house capacity and leveraging the localisation agenda | Increase of funding by at least 30% relative to the 2021-2025 (OSP) baseline. | 52M$ | 16M$ | 32M$ | 48M$ | 63M$ | 67.6M$ | (i)Donor interest in biodiversity, climate, and nature-based solutions remains strong until 2030. (ii) The political and institutional environment in DRC continues to allow international NGO operations and donor engagement. (iii) WWF-DRC maintains a strong reputation and trust among key partners and donors. (iv) The localisation agenda gains traction with donors, favoring in-country funding mechanisms. (v) Internal WWF-DRC teams remain stable, skilled, and sufficiently resourced to manage complex, multi-donor programs. | (i)KPI reports (including analysis of donor diversification and funding trends, and in-country funding localization initiative ), (ii) Donor contracts and MoUs signed with new funding partners, (iii)Organizational capacity assessment reports (e.g., HR, grant management, QA systems), (iv) Funding Grip analysis and reports with funding gap tracking,(v) GMS report | GMS database, Funding Grid sheet, ORACLE | Annualy | Donor fatigue or shifting priorities. | ------------------- | ------------------
|  |  | At least 30% of funding is secured directly in the country by WWF DRC in the localization agenda approach. | 43% | 40% | 40% | 40% | 40% | 40%
|  |  | Necessary funding to deliver the OSP and cover the funding gaps secured. | 23.8M$ | 1.4M$ | 1.7M$ | 2.7M$ | 8M$ | 10M$ |  |  |  |  | Macroeconomic instability (e.g. inflation, recession).
Resource Acquisition Outcomes | 1.1 | By 2030, WWF-DRC maintains at least 75% of its current donors and adds at least one new PSP donor as well as increase contributions from private donors funding the OSP compared to the 2025 baseline | % of current PSP and NOs donors (2021-2025 baseline) renewed. | 29 PSP& Private and 7 NOs | 10 PSP &Private and 1 NOs | 13 PSP &Private and 3 NOs | 20 PSP &Private and 5 NOs | 21 PSP &Private and 5 NOs | 22 PSP &Private and 5 NOs | Institutional donors (PSP) remain engaged in DRC despite political or security risks, Global macroeconomic conditions allow donors to maintain or increase their funding, The DRC government remains supportive of international NGO funding, WWF-DRC continues to demonstrate credible and measurable results, The regulatory and fiscal environment for NGOs remains stable or improves. | Annual financial and technical reports, Funding grids, Signed grant agreements, Fundraising performance dashboards | Grant tracking tools (Grant Tracker), Consolidated Funding Grid or Country Pipeline, Meeting minutes with donors, Proposal submission and approval in GMS | 6-Monthly |  | ------------------- | ------------------
|  |  | PSP Contribution Ratio | 90% | 90% | 85% | 85% | 80% | 80%
|  |  | Private Sector Yield | 14M$ | 16M$ | 16M$ | 16M$ | 15M$ | 15M$
| 1.2 | By 2030, WWF DRC has positioned as '' agency of choice '' for at least 50% of donors and Government regarding REDD+, PES and inclusive conservation program in DRC | Proportion of Strategic Grants (Multi-year & High Value). | 90% | 90% | 90% | 90% | 90% | 90% | National policies continue to support REDD+ and PES mechanisms, Institutional frameworks (ICCN, MEDD, MINAFFET) remain stable and open to partnership, Donors maintain strategic interest in nature-based solutions and inclusive conservation, WWF-DRC effectively capitalizes and disseminates lessons learned, No major reputational issues damage WWF-DRC's standing with donors or partners. | Official partnership requests from donors and government, Project reports integrating REDD+ or PES, WWF PSE guidelines and technical notes, Records of participation in sectoral dialogues | Partnership request logs, Intranet or SharePoint documentation system, Meeting reports with ICCN, MEDD and Donors , etc, Capitalization tools and summary briefs | 6-Monthly
|  |  | Qualified Inbound Solicitation Volume | 3 | 0 | 1 | 1 | 1 | 4
|  |  | Volume of Funding Secured for REDD+/PES/Inclusive Conservation | 5 | 5 | 7 | 7 | 7 | 7
| 1.3 | By 2030 WWF DRC is implementing at least two new jointly developed projects with credible (with signed MOU) partners (socio economic, CSO, Conservation NGO) relative to 2024 baseline | Number of Active Joint Venture Projects. | 1 | 3 | 3 | 3 | 3 | 3 | Credible and operational partners are available and interested in collaboration, Donors encourage consortium-based project approaches, Trust between INGOs and local NGOs is maintained or improved, Selected partners have minimum capacity for WWF-DRC to support or fund them, Coordination platforms for NGOs remain functional and supportive. | Signed MoUs with partners, Co-financed or consortium project documents, Joint implementation reports, Outgoing list of supported local NGOs | NGO partnership mapping matrix, Partner capacity assessment tools, Meeting minutes with CSOs/NGOs, Capacity building monitoring reports | 6-Monthly
|  |  | Consortium-Funded Project Count | 1 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | Global economic downturns reducing donor capacity. | ------------------- | ------------------
|  |  | Active Partnerships with Development Organizations (DOs) | 0 | 1 | 2 | 2 | 2 | 2
| 1.4 | By 2030, WWF DRC with a dedicated Resources Acquisition staff is compliant with 100% donor’s requirements which increase trust for long term funding. | Staff RA Competency Rate | 2 | 2 | 3 | 2 | 3 | 13 | Qualified human resources are available for key fundraising and project roles, WWF Network continues to support WWF-DRC's internal capacity building, Low staff turnover ensures institutional stability, Internal tools for quality assurance and accountability are functional, Donor requirements remain clear and accessible. | Unqualified external audit reports, Project closure reports without major issues, Donor compliance matrix, Internal quality and performance evaluations | Donor compliance checklists, Internal project management systems (RA PMEL), Funding Grid, Country Project Pipeline, GMS, Quality assessment and control tools, Internal training records and feedback forms | 6-Monthly
|  |  | Grant Compliance Rate (Audit & Reporting) | 6% | 0% | 0% | 0% | 0% | 0%
|  |  | Clean Project Closure Rate | 94% | 100% | 100% | 100% | 100% | 100%
Ressources Acquisition Outputs | 1.1.1. | By 2030 proactively engage with traditional Strategic donors to remain integrated in their strategies | Number of Strategic Donor Engagement Plans Executed | 0 | 5 | 5 | 5 | 5 | 5
| 1.1.2. | By 2030 Influence strategic priorities of institutional donors and the DRC government partner agencies through bilateral discussions and active participation in their programmatic forums, | Number of Policy & Technical Inputs Submitted | 0 | 1 | 1 | 1 | 1 | 1
| 1.1.3. | Proactively engage with new donors to attract them toward WWF-DRC Strategy with a view of possible collaboration and indirect access to their funding sources. | Number of New Donor Value Propositions Presented | 0 | 1 | 1 | 1 | 1 | 1
| 1.1.4. | Develop high quality proposals to be submitted to several donors; | Number of Qualified Proposals Submitted. | 32 | 5 | 5 | 5 | 5 | 5
| 1.1.5. | Strategic program updates and project briefs are delivered to priority donors. | Number of Strategic Donor Briefings Delivered | 4 | 2 | 2 | 2 | 2 | 2
| 1.1.6. | Comprehensive financial gap analyses and full-cost recovery models are developed for all priority Landscapes and Thematic Programs. | Number of priority Landscapes/Thematic Programs with completed Financial Gap Analyses. | 5 | 4 | 4 | 4 | 4 | 4
| 1.1.7. | A comprehensive and segmented database of high-potential non-institutional donors (Foundations/Private) is established and maintained | Number of Qualified Non-Institutional Donor Profiles | 0 | 2 | 2 | 2 | 2 | 2
| 1.1.8. | A continuous stream of qualified funding opportunities (Calls for Proposals, Forecasts) is detected and entered into the pipeline | Number of New Qualified Opportunities Logged | TBD | 5 | 5 | 5 | 5 | 5
| 1.2.1. | Standardized PSE/PES operational guidelines and technical protocols are formally codified and updated based on adaptive management cycles. | Number of PSE Technical Frameworks Validated | 1 | 1 | 1 | 1 | 1 | 1
| 1.2.2 | A cadre of technical staff in all priority landscapes is formally trained and certified in PSE operational protocols. | Number of Landscape Staff Certified in PSE | TBD | 5 | 10 | 10 | 10 | 10
| 1.2.3. | Technical insights and operational lessons from REDD+ implementation are synthesized into formal adaptive management reports and sustainability frameworks. | Number of REDD+ Capitalization Products Published | 0 | 0 | 1 | 1 | 1 | 1
| 1.2.4. | A centralized, fully functional digital platform for Resource Acquisition intelligence and coordination is established and maintained for WWF-DRC staff." | Number of Functional RA Portal Modules Deployed | TBD | 0 | 1 | 1 | 1 | 1
| 1.2.5. | High-quality, donor-centric communication assets and visibility products are produced and disseminated to support the Resource Acquisition strategy | Number of Donor-Centric Communication Assets Published | TBD | 1 | 1 | 1 | 1 | 1
| 1.2.6. | Technical assistance and strategic fundraising inputs are delivered to key government partners (MEDD, ICCN, MINAFET) to strengthen national resource mobilization efforts | Number of Joint Resource Mobilization Initiatives Supported | 0 | 0 | 1 | 1 | 1 | 1
| 1.2.7. | Strategic technical inputs and policy recommendations are delivered to key government ministries (MEDD, ICCN, MINAFET) to shape national conservation frameworks. | Number of Formal Policy Inputs Submitted | 0 | 0 | 1 | 1 | 1 | 1
| 1.2.8. | Formal joint technical frameworks and co-management agreements for Protected Areas are established and maintained with ICCN to unify resource mobilization efforts. | Number of Joint Agreements or Technical Protocols Signed with ICCN | 2 | 1 | 1 | 1 | 1 | 1
| 1.3.1 | A comprehensive database of strategic International NGO (INGO) partners is established to inform consortium building and joint venture opportunities. | Number of Qualified INGO Partner Profiles | TBD | 4 | 4 | 4 | 4 | 4
| 1.3.2 | Formal strategic alignment frameworks and joint priority roadmaps are established with major Development Organizations operating in DRC. | Number of Strategic Alignment Frameworks Established | 2 | TBD | TBD | TBD | TBD | TBD
| 1.3.3 | WWF-DRC strategic priorities and technical positions are formally represented within key International NGO coordination bodies and working groups. | Number of INGO Coordination Events with Active Representation | 1 | 1 | 1 | 1 | 1 | 1
| 1.3.4 | High-potential networking events are leveraged to expand the institutional contact database and gather donor market intelligence. | Number of Qualified New Contacts Added to CRM via Events | TBD | TBD | TBD | TBD | TBD | TBD
| 1.3.5 | Specific, actionable collaboration opportunities (Leads) with International NGOs are identified and qualified for the pipeline | Number of Qualified INGO Collaboration Leads | TBD | 2 | 2 | 2 | 2 | 2
| 1.3.6 | Operational joint workplans and specific collaboration agreements are formalized with priority partners to integrate them into WWF-DRC's conservation delivery | Number of Partners with Active Joint Workplans | 4 | 8 | 8 | 8 | 8 | 8
| 1.3.7 | A vetted roster of priority Local CSO partners is established for each strategic landscape and thematic area to enable rapid consortium formation. | Number of Vetted Local CSO Partners Qualified for Funding | 4 | 8 | 8 | 8 | 8 | 8
| 1.3.8 | Formal organizational capacity assessments (OCA) are conducted for priority local partners to establish baselines for funding readiness. | Number of Partner Capacity Assessments Finalized | 4 | 8 | 8 | 8 | 8 | 8
| 1.3.9 | Tailored capacity building roadmaps are formally established and validated for all priority local partners to address identified organizational gaps. | Number of Partner Capacity Building Plans Validated | 1 | 1 | 1 | 1 | 1 | 1
| 1.4.1 | A cadre of Project Managers and Administrators is formally certified in WWF Contract Management Standards to ensure compliant execution. | Number of Staff Certified in Contract Management | 1 | 8 | 8 | 8 | 8 | 8
| 1.4.2 | Key fundraising staff and program leads are formally certified in Proposal Development standards to ensure high-quality pipeline generation. | Number of Staff Certified in Proposal Development | TBD | 10 | 10 | 10 | 10 | 10
| 1.4.3 | Funding portfolios are consolidated into multi-year, landscape-level Programmatic Framework Agreements (PFAs) to minimize administrative fragmentation. | Number of Programmatic Framework Agreements (PFAs) Signed | TBD | 5 | 4 | 5 | 6 | 8
| 1.4.4 | Full financial coverage for the Fundraising and Grant Officer position is secured through cost-recovery mechanisms to ensure role continuity | Fundraising Officer Funding Coverage Ratio | 30% | 60% | 80% | 100% | 100% | 100%
| 1.4.5 | The Programme Quality and Development function is operationalized and financially secured to enforce Quality Assurance standards across the portfolio. | Programme Quality Coordinator Funding Coverage Ratio | 40% | 40% | 60% | 100% | 100% | 100%

## 2. MEL Plan (Example) (hidden)
Programme M&E plan | # | Description | Indicator | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Assumptions | Means of Verification | Data Collection Tool | Frequency of Measurement | Risks | Location | Responsible
Resource Acquisition Theory of Change | IF we secure significanrt funding from HNWI AND build strong relationships and funding streams with Embassies AND enhance our teams' capacity in RA approaches AND X, Y Z THEN we will establish a robust, diverse and sustainable funding base, capable of fully supporting the delivery of the OSP strategy 2025-2030
Resource Acquisition Goals | 1 | By 2030, WWF Country Office X will achieve financial sustainability by diversifying funding sources, integrating localization into resource acquisition strategies, and reducing reliance on a few major donors | By 2030, at least 50% of WWF Country Offices’ annual revenue will come from a diversified portfolio comprising of no more than 25% dependency on any single donor, with at least 30% sourced from partnering with local partners within any funding mechanisms | [10 empty] | ------------------------- | ------------------------- | -------------------------
| 2 | By 2030 the Country Office capacity in Resource Aquistion is increased to ensure a sustaianble funding base | By 2030, all COs will demonstrate enhanced resource acquisition capacity, with at least 80% meeting established competency benchmarks in proposal development, donor engagement, and strategic funding alignment, measured through annual capacity assessments & increased proposal success rates by 20% | [10 empty] | ------------------------- | ------------------------- | -------------------------
Resource Acquisition Outcomes (the WHAT - priorities we want to change through our RA strategy) | 1.1 | Reduce reliance on PSP sector through diversification of funding streams | Increase in donor segments & funding from new sources | [6 empty] | Donors are receptive to new engagement strategies | Donor database /tracker, engagement plans, funding reports |  |  |  | ------------------------- | -------------------------
| 1.2 | Strategic Donor/Partnership Engagement - Strengthening donor consortia, networks and alliances | Number of active donor consortia, network engagements, funding from/to networks | [6 empty] | Donor networks remain key to regional conservation funding | Meeting notes, partnership agreements, network engagement reports |  |  |  | ------------------------- | -------------------------
| 1.3 | Innovative Fundraising Models | Number of innovative models used; % of funding from new sources | [6 empty] | Successful implementation of innovative models will result in a percentage increase of funding sourced from new and diverse channels. | Funding agreements, partnership reports, market analysis |  |  |  | ------------------------- | -------------------------
| 2.1 | Capacity Building for Resource Acquisition | Number of staff trained, concept/proposal success rate | [6 empty] | New skills will translate into improved funding outcomes | Training records, staff feedback, donor proposal success tracker |  |  |  | ------------------------- | -------------------------
| 3.1 | Localisation of Resource Acquisition | % of funding allocated to local partners, number of local partnerships established | [6 empty] | International, regional and national donors and goverments will invest in local conservation partners/organisations | Local donor agreements signed, partner reports
Resource Aquisition Priority Outputs (HOW) (High level) Refers to the non-negotiable outputs that are critical for the success of the programme, based on the Theory of Change | 1.1.1 | Diversified donor portfolio, reducing reliance on a small number of major donors | Diversified donor portfolio, reducing reliance on a small number of major donors | [6 empty] | The diversification of the donor portfolio will lead to a reduction in reliance on a small number of major donors, ensuring a more resilient and sustainable funding base for COs |  |  |  | -------------------------
| 1.1.2 | Reliance on PSP has been reduced to 60% of total portfolio value to avoid over concentration | By 2030, the contribution of Public Sector Partnerships (PSP) to the total funding portfolio of each CO will be reduced to no more than 60%, ensuring a more balanced funding structure with at least three other funding sources each contributing a minimum of 10% | 90% | 80% | 70% | 65% | 60% | 60% | We can maintain our current funding levels with reduced proportion of PSP | Financial analysis of secured grants | Oracle | 6-monthly
| 1.1.3 | Increase major donor funding proportion from 5% to 15% to offset reliaunce on PSP funding | By 2030, the proportion of total funding contributed by major donors will increase from 5% to 15%, effectively offsetting reliance on Public Sector Partnerships (PSP) funding | [6 empty] | Increase in the proportion of total funding contributed by major donors from 5% to 15% will effectively offset reliance on PSPfunding, leading to a more balanced and resilient funding structure for COs
| 1.1.4 | Increase HNWI donor funding from 0% to 5% to ensure further diversification and creat an additional funding stream | Percentage increase in funding from High Net Worth Individuals (HNWIs) as a proportion of total donor contributions, aiming for a target of 5% by 2030 | [6 empty] | Percentage increase in funding from High Net Worth Individuals (HNWIs) as a proportion of total donor contributions will reach a target of 5% by 2030, driven by enhanced engagement strategies |  |  |  | -------------------------
| 1.2.1 | Tailored donor engagement strategies that align donor interests with WWF’s strategic goals | 100% of donor engagement strategies developed and implemented that explicitly align donor interests with WWF’s strategic goals | [6 empty] | 100% of donor engagement strategies developed and implemented will align donor interests with WWF’s strategic goals, subject to thorough stakeholder analysis and regular communication |  |  |  | -------------------------
| 2.1.1 | Implementation of innovative fundraising models (such as blended finance, impact investments, digital campaigns) | Number of innovative fundraising models implemented, including blended finance, impact investments, and campaigns | [6 empty] | Successful implementation of innovative fundraising models depends on the availability of adequate resources, techncal expertise, and stakeholder engagement to support such new initiatives |  |  |  | -------------------------
| 2.1.2 | [12 empty] | -------------------------
| 2.2.1 | [12 empty] | -------------------------
| 2.2.2 | Enhanced capacity of WWF Country Offices to implement effective resource acquisition strategies | Percentage increase in WWF Country Offices reporting enhanced capacity to implement effective resource acquisition strategies | [6 empty] | Increase in reported capacity to implement effective RA strategies is subject to availability of tailored training, resources, and ongoing mentoring support for RA staff in COs |  |  |  | -------------------------
| 2.2.3 | Strengthened local capacity and partnerships, with increased fundraising from national and regional sources. | Percentage increase in fundraising revenue from national and regional sources, reflecting strengthened local capacity and partnerships | [6 empty] | Percentage increase in fundraising revenue from national & regional sources is subject to successful development of strong local partnerships, effective capacity-building initiatives, and alignment of fundraising strategies (that includes local community needs and priorities)
Programme Activities (High level) Refers to the necessary activities to deliver the non-negotiable outputs listed above | 1.1.1.1 | Analyse current funding trends and donor interests to identify gaps and opportunities for new engagement | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.1.1.2 | Identify potential new donor segments, including foundations, corporations, high-net-worth individuals (HNWIs), and community fundraising initiatives | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.1.1.3 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.1.2.1 | Conduct a comprehensive donor mapping exercise to identify potential non-PSP funding sources such as foundations, high-net-worth individuals (HNWIs), private sector partnerships, and innovative financing mechanisms | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.1.2.2 | Prioritize donors whose funding objectives align with WWF’s mission and strategic goals, particularly those in sectors like conservation, sustainability, and climate resilience | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.1.2.3 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.2.1.1 | Facilitate multi-stakeholder workshops and networking events to bring together donors, partners, and key stakeholders to exchange knowledge, share best practices, and discuss opportunities for collaboration | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.2.1.2 | Develop joint proposals with donor consortia to co-create proposals that address shared goals and priorities, increasing the potential for pooled funding | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.2.1.3 | Establish regular communication channels and set up structured communication channels, such as quarterly newsletters, virtual meetings, or donor briefings, to keep donors and partners informed of progress, opportunities, and upcoming initiatives | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.2.2.1 | Explore opportunities for joint fundraising campaigns with donor networks and alliances, promoting shared objectives | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.2.2.2 | Leverage digital platforms and social media to coordinate multi-partner fundraising events or awareness campaigns, increasing visibility and engagement from diverse donor groups | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 1.2.2.3 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.1.1.1 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.1.1.2 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.1.1.3 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.1.2.1 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.1.2.2 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.1.2.3 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.2.2.1 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.2.2.2 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.2.2.3 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 3.1.1.1 | Map local partner organizations per thematic conservation outcome | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 3.1.1.2 | Collaborate with local organizations and NGOs to enhance fundraising efforts and tap into both global and regional funding sources | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 3.1.1.3 | Provide training and resources to local partner teams to improve their fundraising skills and build relationships with potential donors | [7 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 3.1.1.4 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
| 2.2.2.3 | [8 empty] | ------------------------- | ------------------------- | ------------------------- | ------------------------- | ------------------------- | -------------------------
Note on A2: ====== ID#AAABnbip6yE (2025-07-16 14:08:17) Resource Acquisition specific Theory of Change that describes the pathways of change for the resource aquisition strategies (interventions) - -Lene Andersen
Note on C20: ====== ID#AAABnbip6yA (2025-07-16 14:08:17) A few examples of activities under each output -Lene Andersen

## Donor Mapping Template
Donor Type | Donor Name | Thematic Alignment | Aligned OSP Programmes | Current Relationship Level | Funding (Grant Size) | Funding Mechanisms | Strategies & Action Plan | GMS Tracking | MDL | CAL | EPL
[9 empty] | Y | N | N

## Implementation Plan
| Output Number | Output Statement | FY26 Cost (€ ) | FY27 Cost (€ ) | FY28 Cost (€ ) | FY29 Cost (€ ) | FY30 Cost (€ ) | Total (€ ) | Current Project (CPM Project #) | Target Funding Source | Target Funding Source
READ Me First. RA Costs should include: Personnel Costs: Funding required for fundraising staff, donor engagement specialists, financial analysts, etc. Capacity Building: Training programs for proposal writing, donor relations, and financial management. Engagement & Outreach: Costs for donor engagement activities, stakeholder meetings, travel, and communication. Research & Analysis: Expenses related to donor landscape analysis, SWOT assessments, and donor mapping. Technology & Systems: Investments in data management tools, CRM software, and performance tracking systems. Proposal Development & Submission: Costs related to proposal writing, external consultants, or technical support. Monitoring & Evaluation: Resources needed for tracking KPIs, conducting quarterly reviews, and preparing reports. |  | Please list all the outputs identified under the Factors & Outcome tab as well as the M&E plan. During the annual planning and budgeting process, the Programme will have opportunities to further refine and detail the activities and costs. The initial costing of the priority outputs can be estimated, which will be used to estimate the cost of total OSP implementation and the development of the financial plan. Please make sure to include outputs related to M&E, ESSF and other risk mitigation, etc. | [5 empty] | This column will be automatically sum up the total. | If the activity is already funded, please indicate the relevant CPM number(s). | If there is a funding gap and have prospective funding sources, please indicate the source. | If there is a funding gap and have prospective funding sources, please indicate the source.
Example | 1.1.1 | Training for staff in proposal writing | [5 empty] | 0
| 1.1.2 | Landscape Analysis | [5 empty] | 0
| 1.1.3 | Donor Engagement | [5 empty] | 0
|  | Staff/Personnel Costs | [5 empty] | 0
|  | WWF DRC Personnel Costs (staff time): | [5 empty] | 0
|  | Capacity Building: | [5 empty] | 0
|  | Training programmes on proposal writing and donor mapping and engagement | [5 empty] | 0
|  | Training on grant management for programme managers, thematic leads, legal/compliance and PMEL staff | [5 empty] | 0
|  | Engagement & Outreach: | [5 empty] | 0
|  | Donor engagement cost (meetings, seminars, emails, webinars) | [5 empty] | 0
|  | Stakeholders' engagement meetings | [5 empty] | 0
|  | Travel for Donor conference and external network engagement | [5 empty] | 0
|  | Communication (newsletters, bulletins, information products) | [5 empty] | 0
|  | Conducting quarterly reviews, and preparing annual reports. | [5 empty] | 0
|  | Donor research & analysis: | [5 empty] | 0
|  | Expenses related to donor landscape analysis, SWOT assessments, and donor mapping. | [5 empty] | 0
|  | Donor research intern | [5 empty] | 0
TOTAL |  | Technology & Systems: | [5 empty] | 0
|  | Donor sourcing and information tools (Devex, DevAid etc). Registration fees | [5 empty] | 0
|  | Donor performance tracking and CRM software (GMS, etc) | [5 empty] | 0
|  | Proposal Development & Submission: | [5 empty] | 0
|  | Costs related to proposal writing, external consultants, or technical support. (Min 4 proposals per year of 500,000) | [5 empty] | 0
|  | Joint proposal development related travel with NOs and partners | [5 empty] | 0
|  | Partner proposal development workshops | [5 empty] | 0
|  | Monitoring & Evaluation: | [5 empty] | 0
|  | Resources needed for tracking RA KPIs | [5 empty] | 0
|  | Equipment: | [5 empty] | 0
|  | Equipment costs for RA intern | [5 empty] | 0
| 1.1.1. | By 2030 proactively engage with traditional Strategic donors to remain integrated in their strategies | 0 | 0 | 0 | 0 | 0 | 0 |  | By 2030 proactively | By 2030 proactively | 1
| 1.1.2. | By 2030 Influence strategic priorities of institutional donors and the DRC government partner agencies through bilateral discussions and active participation in their programmatic forums, | 0 | 0 | 0 | 0 | 0 | 0 |  | By 2030 Influence st | By 2030 Influence st | 2
| 1.1.3. | Proactively engage with new donors to attract them toward WWF-DRC Strategy with a view of possible collaboration and indirect access to their funding sources. | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 |  | Proactively engage w | Proactively engage w | 3
| 1.1.4. | Develop high quality proposals to be submitted to several donors; | 0 | 0 | 0 | 0 | 0 | 0 |  | Develop high quality | Develop high quality | 4
| 1.1.5. | Strategic program updates and project briefs are delivered to priority donors. | 0 | 0 | 0 | 0 | 0 | 0 |  | Strategic program up | Strategic program up | 5
| 1.1.6. | Comprehensive financial gap analyses and full-cost recovery models are developed for all priority Landscapes and Thematic Programs. | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 |  | Comprehensive financ | Regularly assess c | #N/A
| 1.1.7. | A comprehensive and segmented database of high-potential non-institutional donors (Foundations/Private) is established and maintained | 0 | 0 | 0 | 0 | 0 | 0 |  | A comprehensive and | Mapping foundations | #N/A
| 1.1.8. | A continuous stream of qualified funding opportunities (Calls for Proposals, Forecasts) is detected and entered into the pipeline | 0 | 0 | 0 | 0 | 0 | 0 |  | A continuous stream | A comprehensive and | 7
| 1.2.1. | Standardized PSE/PES operational guidelines and technical protocols are formally codified and updated based on adaptive management cycles. | 0 | 0 | 0 | 0 | 0 | 0 |  | Standardized PSE/PES | A continuous stream | 8
| 1.2.2 | A cadre of technical staff in all priority landscapes is formally trained and certified in PSE operational protocols. | 0 | 0 | 0 | 0 | 0 | 0 |  | A cadre of technical | Standardized PSE/PES | 9
| 1.2.3. | Technical insights and operational lessons from REDD+ implementation are synthesized into formal adaptive management reports and sustainability frameworks. | 0 | 0 | 0 | 0 | 0 | 0 |  | Technical insights a | Technical insights a | 11
| 1.2.4. | A centralized, fully functional digital platform for Resource Acquisition intelligence and coordination is established and maintained for WWF-DRC staff." | 0 | 0 | 0 | 0 | 0 | 0 |  | A centralized, fully | A centralized, fully | 12
| 1.2.5. | High-quality, donor-centric communication assets and visibility products are produced and disseminated to support the Resource Acquisition strategy | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 |  | High-quality, donor- | High-quality, donor- | 13
| 1.2.6. | Technical assistance and strategic fundraising inputs are delivered to key government partners (MEDD, ICCN, MINAFET) to strengthen national resource mobilization efforts | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 |  | Technical assistance | Technical assistance | 14
| 1.2.7. | Strategic technical inputs and policy recommendations are delivered to key government ministries (MEDD, ICCN, MINAFET) to shape national conservation frameworks. | 0 | 0 | 0 | 0 | 0 | 0 |  | Strategic technical | Strategic technical | 15
| 1.2.8. | Formal joint technical frameworks and co-management agreements for Protected Areas are established and maintained with ICCN to unify resource mobilization efforts. | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 |  | Formal joint technic | Formal joint technic | 16
| 1.3.1 | A comprehensive database of strategic International NGO (INGO) partners is established to inform consortium building and joint venture opportunities. | 0 | 0 | 0 | 0 | 0 | 0 |  | A comprehensive data | A comprehensive data | 17
| 1.3.2 | Formal strategic alignment frameworks and joint priority roadmaps are established with major Development Organizations operating in DRC. | 10000 | 0 | 0 | 0 | 0 | 10000 |  | Formal strategic ali | Formal strategic ali | 18
| 1.3.3 | WWF-DRC strategic priorities and technical positions are formally represented within key International NGO coordination bodies and working groups. | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 |  | WWF-DRC strategic pr | WWF-DRC strategic pr | 19
| 1.3.4 | High-potential networking events are leveraged to expand the institutional contact database and gather donor market intelligence. | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 |  | High-potential netwo | High-potential netwo | 20
| 1.3.5 | Specific, actionable collaboration opportunities (Leads) with International NGOs are identified and qualified for the pipeline | 0 | 0 | 0 | 0 | 0 | 0 |  | Specific, actionable | Specific, actionable | 21
| 1.3.6 | Operational joint workplans and specific collaboration agreements are formalized with priority partners to integrate them into WWF-DRC's conservation delivery | 0 | 0 | 0 | 0 | 0 | 0 |  | Operational joint wo | Operational joint wo | 22
| 1.3.7 | A vetted roster of priority Local CSO partners is established for each strategic landscape and thematic area to enable rapid consortium formation. | 10000 | 0 | 0 | 0 | 0 | 10000 |  | A vetted roster of p | A vetted roster of p | 23
| 1.3.8 | Formal organizational capacity assessments (OCA) are conducted for priority local partners to establish baselines for funding readiness. | 5000 | 0 | 0 | 5000 | 0 | 10000 |  | Formal organizationa | Formal organizationa | 24
| 1.3.9 | Tailored capacity building roadmaps are formally established and validated for all priority local partners to address identified organizational gaps. | 0 | 0 | 0 | 0 | 0 | 0 |  | Tailored capacity bu | Tailored capacity bu | 25
| 1.4.1 | A cadre of Project Managers and Administrators is formally certified in WWF Contract Management Standards to ensure compliant execution. | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 |  | A cadre of Project M | A cadre of Project M | 26
| 1.4.2 | Key fundraising staff and program leads are formally certified in Proposal Development standards to ensure high-quality pipeline generation. | 20000 | 0 | 20000 | 0 | 0 | 40000 |  | Key fundraising staf | Key fundraising staf | 27
| 1.4.3 | Funding portfolios are consolidated into multi-year, landscape-level Programmatic Framework Agreements (PFAs) to minimize administrative fragmentation. | 10000 | 0 | 0 | 0 | 0 | 10000 |  | Funding portfolios a | Funding portfolios a | 28
| 1.4.4 | Full financial coverage for the Fundraising and Grant Officer position is secured through cost-recovery mechanisms to ensure role continuity | 0 | 0 | 0 | 0 | 0 | 0 |  | Full financial cover | Full financial cover | 29
| 1.4.5 | The Programme Quality and Development function is operationalized and financially secured to enforce Quality Assurance standards across the portfolio. | 0 | 0 | 0 | 0 | 0 | 0 |  | The Programme Qualit | The Programme Qualit | 30
|  |  | 115000 | 60000 | 80000 | 65000 | 60000 | 380000 |  |  |  | #N/A