## OM Results Chain
| OSP Goal Statment | Priorities Outcomes | Relevant Geographic Scope | Relevant Thematic Scope | Output (Annual Result) - Year 1 | Activities - Year 1 | Output (Annual Result) - Year 2 | Activities - Year 2 | Output (Annual Result) - Year 3 | Activities - Year 3 | Output (Annual Result) - Year 4 | Activities - Year 4 | Output (Annual Result) - Year 5 | Activities - Year 5 | Key Assumptions | Sustainability & Exit Plan
READ Me First | Please copy the list of Conservation Focus from the previous tab. | is stabilized | Please indicate the relevant Geographic Scope for each Outcome statement. Ensure to use one of the Geographic scope identified in the Scope tab of OSP Design Template. | Please indicate the relevant Thematic Scope for each Goal statement. Ensure to use one of the Thematic scope identified in the Scope tab of OSP Design Template. | Please define measurable Programme Annual Results which are milestones in achieving Programme outcomes. Therefore Programme Outcome must be embedded in the Programme Outputs. Outputs must represent tangible deliverables, within our area of control, that are critical to achieving the Programme Outcomes, in line with the Theory of Change. If there are areas of innovation and/or research, please make sure to include those outputs and activities as well. See the guidance on the approach to the Programme and Project Planning | [9 empty] | Please identify the key assumptions that underpin the logical sequences linking Activities, Outputs, and Outcomes, and to one or more Goals Assumptions may also express how external variables may influence the achievement of results. Once the assumptions are identified, make sure to reflect them when completing the risk assessment. See Risk Hub for risk assessment templates and resources. | Please describe how your program aims to ensure the sustainability of the program outcome and an eventual exit by WWF. See Guidance by PPMS Step - Element 2.3
READ Me First | Copy the gaol stament form the OSP template. | For each OSP goal, describe the specific, measurable outcomes you aim to achieve. Outcomes should focus on addressing gaps in organizational management identified through capacity assessments. Ensure these are SMART (Specific, Measurable, Achievable, Relevant, Time-bound) and directly contribute to the OSP goal. |  |  | For each year, define measurable annual outputs that serve as milestones in achieving the program outcomes. Outputs should be tangible, within the organization’s control, and directly linked to program outcomes. | For each year, outline the specific activities that will contribute to achieving the annual outputs. These are the tasks or initiatives the office will undertake to reach the targets. | [8 empty] | Identify the assumptions that underpin the success of activities, outputs, and outcomes. These are external factors or conditions necessary for success that may be beyond the office’s direct control. | Outline how the outcomes will be sustained beyond the period of active intervention. Focus on building internal capacities, integrating new systems, and ensuring the office can independently manage its operations.
Example | By 2027, WWF [Office Name] demonstrates operational excellence by achieving streamlined financial processes and enhanced leadership capacity across all departments. | By 2025, WWF [Office Name] implements a robust financial management system, improving budget tracking and resource allocation accuracy by 80%. |  |  | Develop and implement a financial management training program for finance staff | Conduct financial management workshops for finance and administration teams | 50% of finance staff demonstrate improved budget management skills as assessed by internal reviews | Implement quarterly budget reviews and staff performance assessments | WWF [Office Name] reduces financial reporting errors by 60% through the use of automated systems | Install and train staff on new financial management software | 80% of departmental heads have been trained on resource allocation and budget monitoring | Host resource allocation training for department heads | WWF [Office Name] achieves full financial compliance across all projects, with zero audit flags. | Conduct internal audits and finalize reporting for all projects. | Staff will be available and motivated to participate in all training sessions, and the new financial software will be compatible with existing systems | Develop a long-term financial sustainability plan and ensure key staff are trained in system maintenance and financial oversight to guarantee continued compliance and operational efficiency.
1. P&C | By 2030, WWF DRC has committed, satisfied and good-performing staff, working within a strong, inclusive organizational culture that lives WWF’s values. | by 2030, WWF DRC structure is aligned with its conservation plan and its financial possibilities and key roles are filled |  |  | Structure revised at the HQ/Core and within each landscape; Workforce plan in place and implemented | • revise the structure to meet new challenges with scenarios: ideal/minimal at HQ/Core level (P&C) and at landscape level • develop workforce planning • implement recruitment plan and/or revision of JD • communicate the changes with the staff | Revised Recruitment Plan & JDs | • review and improve recruitment & retention strategies & tools • implement recruitment plan and/or revision of JD | Revised Structure evaluated (Mid-term) for the HQ/Core and within each landscape; Workforce plan evaluated | • Evaluate the revised structure to meet new challenges with scenarios: ideal/minimal at HQ/Core level (P&C) and at landscape level • Evaluate workforce planning • implement recruitment plan and/or revision of JD (if needed) • communicate the changes with the staff (if any changes) | Revised Recruitment Plan & JDs | • implement recruitment plan and/or revision of JD | Revised Recruitment Plan & JDs | • implement recruitment plan and/or revision of JD | Expecting new funding to support proposed activities; If no additional or lack of funding, the proposed revised plan and JDs will be saved for future | With the current funding, everything will remain the same, or implement the proposed plans
|  | By 2030, WWF DRC P&C policies systems, tools are up to date with internal & external context and are relevant to its challenges |  |  | • Policies & procedures updated toward changes at Network level (Performance, HSS; • Automated HRIS tools in place for HR database, absence & timesheet • P&C Dashboard revised & completed regularly on time | • update policies & procedures (performance, HSS, • hold sessions around the revised/new policies, guidelines • roll out canopy (HR data, absence & timesheet) • hold discussions around use of AI | • Policies & procedures updated; • Automated HRIS tools in place for Talent Acquisition, Onboarding • P&C Dashboard revised & completed regularly on time • compensation & benefits survey available | • update policies & procedures toward changes at Network level • hold sessions around the revised/new policies • roll out canopy (Talent Acquisition / Onboarding) | • compensation & benefit are aligned with the market; | • review salary scale
|  | By 2030, WWF DRC staff performance and development opportunities have improved by 50% in reference to the baseline FY25. |  |  | • At least 80% of eligible staff have individual objectives and performance conversations. • Reward & recognition based on performance implemented; • revised sustainable & equitable development programmes; • staff development implemented at 20% | • Implement the revised performance management framework and guidelines • Consolidate workforce capacity assessment by department; • Define capacity needs and recruitment/training plans; • promote internal training/exchanges; • identify, mobilize source of funding for staff development; • coordinate staff development (group training, online, panda swap, | Reward & recognition based on performance continuously implemented; • Sustainable & equitable development plan implemented for 25 % of existing staff (through peer coaching, online, formal) | • Develop and communicate an internal career development and training catalogue; • roll out initial offerings; • promote internal training/exchanges; • revised salary scale & benefits; | Reward & recognition based on performance continuously implemented; • new internal development initiatives (job shadowing, peer-learning, coaching) in place • career progression and succession plan implemented | • Develop succession and career progression plans for key roles. • launch new internal development initiatives (job shadowing, peer-learning, coaching) | Reward & recognition based on performance continuously implemented; Ensure at least 70% of staff participate in one professional development activity annually. | Establishment of the recognition system based on performance; Implement the system | Reward & recognition based on performance continuously implemented; Staff survey results show a minimum 50% improvement over baseline | Establishment of the recognition system based on performance; Implement the system; Perform a staff survey
2. Operational Excellence | By 2030, WWF DRC demonstrates operational excellence, through full compliance, modern infrastructure, and digital systems. | By 2030, WWF DRC has achieved 90% compliance with required policies and procedures for quality delivery in the implementation of its 2026-2030 OSP. |  |  | A comprehensive compliance framework, including a policy register and compliance monitoring plan aligned with WWF Network and local regulatory requirements for OSP delivery, is finalized and endorsed by SMT | Review, update, and disseminate core operational and programmatic policies and procedures. Conduct staff training on revised policies | At least 80% of WWF DRC staff and project managers are trained and certified on the updated policies and procedures. | Assement of staff gap in understanding policies & procedures; Training of staff on updated policies and procedures | At least 90% of WWF DRC staff and project managers are trained and certified on the updated policies and procedures | Assement of staff gap in understanding policies & procedures; Training of staff on updated policies and procedures
|  | By 2027, WWF DRC operates a functional, accessible, and regularly updated knowledge management system covering at least 90% of key operational and programmatic documents by theme and landscape. |  |  | An approved design and implementation plan for a knowledge management system, including document classification standards by theme and landscape, is finalized and endorsed. All landscapes and departments achieve a quarterly document update rate of at least 75% in the knowledge management system, | -Ensure the infracructure is in place and where needed new infrastructure purachsea- (Scanner, Internet Kit etc) -Identify the responsible persons per landscape to ensure regular updates - Proceeses and guidelines to be trained to all staff so as to ensure correct documents are filed | At least 90% of all identified key operational and programmatic documents are uploaded, properly classified, and accessible in the knowledge management system, as verified by a formal year-end internal audit. | Monitoring the progress and recommend any changes if need be | [6 empty] | The Mara migration will be done in the prescribed timelines
|  | By 2030, a green energy system is installed in 100% of field offices to solve electricity problems and to ensure optimal operations in reference to 2025 baseline |  |  | Conduct feasibility studies and business cases for solar installations in all field offices. Secure funding for at least 3 installations. | - Evaluation of the system needed for the landscape - Fund raisethe funds needed to implement - Procure and install equipment in the first sites identified | Install green energy systems in 3 out of 5 field offices. Monitor and report on operational uptime improvements. | Hire a specialist in Green Energy who will maintain the equipment | Install systems in remaining 2 field offices. Achieve 60% reduction in diesel generator reliance compared to 2025. |  | Conduct energy efficiency audit for all offices. Implement identified operational optimisations |  | Achieve 100% operations on green energy systems. Publish operational savings and CO2 emissions reduction report. |  | The funding for this project will be available as per the plan. The importation process will go on with minimal delays
|  | By 2030, infrastructure and equipment in the national office and in the field meets at least 70% of the organizational infrastructure and equipment standards as per WWF International guidelines and minimum operating requirements |  |  | Define the Standard for WWF DRC for the equipment required to meet organisational goals. Develop upgrade plan and secure budget for priority areas to improve which do not meet the set standards.G11 | -conduct an inventory of equipment that does not meet the required recommendations in the IT system at the national level. This plan will allow for the gradual decommissioning of unsuitable equipment. | Procure and install equipment upgrades in 3 offices. Reach 50% alignment with WWF standards. | Implement upgrade that is possible depending on the availability of funds for each office. This upgrade also depends on the priority within the department! A well-developed plan will be proposed before we decide. | Upgrade infrastructure in 2 remaining offices. Achieve 60% compliance. | At this stage, we must reassure ourselves that the IT infrastructure across the country has reached a level of 70-80% of the recommendations required for the proper functioning of each country office. Some cases could also be reviewed for improvement. | Conduct comprehensive infrastructure quality audit. Address gaps to reach 70% compliance. | Plan and schedule field visits for an IT Audit (software and hardware audit) for all offices. A visit to correct and plan for possible readjustments. The offices can also offer certain recommendations. | Maintain 70% compliance or higher through routine maintenance, asset management, and annual office audits. | In the national IT park, some equipment requires software or hardware IT maintenance. Depending on availability and arrangements, the park should be maintained at least once a year to further increase its operating time. | Financial resources will be available to be able to upgrade IT equipment
3. Governance and Leadership | By 2030, WWF DRC is led by an effective, stable, and high-performing Country Leadership Team (CLT) and Country Management Team (CMT) that ensure strategic clarity, operational oversight, and smooth implementation of the OSP. | By 2030, at least 90% of staff is satisfied with leadership effectiveness, decision-making transparency, and management accountability as compared to 2026 baseline. |  |  | A baseline staff perception survey on leadership effectiveness, decision-making transparency, and management accountability is conducted and results formally validated by SMT. | baseline staff survey on governance and leadership satisfaction (minimum 70% response rate). Develop and communicate action plan based on results. | Implement at least 80% of actions from 2026 plan. Establish communication and feedback mechanisms for CLT/CMT decisions. | Conduct staff dialogue sessions on leadership and workplace culture. | At least 70% of planned leadership and management accountability improvement measures are implemented, with quarterly progress updates shared with all staff. | Conduct follow-up survey. Achieve minimum 80% satisfaction. Organize leadership and decision-making workshops for CLT/CMT and staff. | Institutionalize quarterly governance check-ins (minimum 4 per year) with anonymous feedback loops. Reach 85% satisfaction rate. | Establish a regular staff forum for proposals to CMT. | Conduct final survey with a target of 90% satisfaction. Produce a lessons learned report and governance improvement plan for the next strategic cycle. | Organize external validation or moderated feedback session for review and lessons learned.
|  | By 2030, 95% of key strategic and operational decisions taken by leadership are shared on time, explained, applied and followed 100% by staff and management. |  |  | Define ‘key decisions’ and set standards for communication and implementation timelines. Introduce a decision-tracking tool. |  | Ensure 80% of key decisions are communicated within agreed timelines. Introduce decision feedback mechanisms. |  | Increase on-time communication and documentation to 85%. Launch a CLT/CMT decision dashboard for tracking. |  | Achieve a 90% performance rate on decision communication, implementation, and follow-up. Conduct at least two decision review and lessons learned workshops. |  | Reach 95% rate of implementation, communication, and tracking for key decisions. Produce an end-of-cycle governance and decision-making review report.
4. Communication | By 2030, WWF DRC has significantly enhanced its public profile and visibility, leading to greater impact of its programmes, strengthened partnerships, and increased public awareness for nature conservation. | By 2030, the stakeholder and public perception score of WWF DRC has improved by at least 10% relative to 2026 baseline |  |  | Conduct a stakeholder and public perception baseline survey (including trust, leadership, professionalism, partnership effectiveness). Develop and communicate a perception improvement action plan. | - Design and Disseminate a Targeted Perception Survey Campaign - Facilitate Multi-Stakeholder Listening Sessions - Produce a Communication Brief on Survey Findings - Launch the Perception Improvement Action Plan | Implement at least 70% of planned actions. Launch by-yearly stakeholder engagement meetings and digital perception campaigns. | - Host biannual Stakeholder Forums - Run Thematic Digital Perception Campaigns - Develop a Perception Tracker Dashboard - Design action plan for future improvement. | Conduct mid-term perception survey. Achieve minimum 5% improvement over 2026 baseline. Adjust action plan based on findings. | - Plan and Conduct the Mid-Term Perception Survey - Produce a Mid-Term Perception Report - Adjust Action Plan Based on Findings - Update Campaign Calendars and Editorial Plans - Monitor Implementation of Adjusted Plan | Maintain perception campaigns and engagement efforts. Conduct partner-specific perception interviews. | - Continue Thematic Digital Campaigns - Conduct Partner-Specific Perception Interviews - Prepare for Final Year (2026–2030) Push - Begin Drafting a “State of WWF Perception” Summary | Conduct final perception survey. Achieve a 10% improvement over the 2026 baseline. Produce a perception and visibility review report for strategy 2030–2035. | - Plan and Conduct Final Perception Survey - Collect and Analyze Data - Compare trends and identify turning points. - Host a National Visibility & Perception Review Workshop
|  | By 2030, WWF DRC has increased its public visibility by at least 25% relative to 2026 baseline |  |  | Establish a visibility baseline (media mentions, digital impressions, social media followers, partnership events). Define annual growth targets. | - Baseline Data Collection and Analysis - Digital Performance Assessment - Develop a Monitoring and Reporting Framework - Create standard templates for digital metrics management | Increase visibility by 10% through expanded media campaigns, digital content series, and conservation events. Secure at least 3 high-profile partnerships for joint visibility actions. | - Expand Media Campaigns (Traditional + Digital) - Develop Strategic Media Partnerships - Host two high visibility national conservation events - Organize a Strategic Visibility Partnership Roundtable or workshop | Enhanced multimedia presence and strategic communications partnerships to increase WWF-DRC's visibility. Reach cumulative 18% increase in visibility metrics. . | - Scale Up the Digital Content creation and expand social media investment - Create regular (weekly or monthly) WWF-DRC radio segment - Partner with influencers/content creators -Negotiate corporate co-branding opportunities - Create partnership with an external media monitoring agency | Maintain and consolidate media presence. Publish an annual visibility performance report. Achieve 22% increase over baseline. | - Maintain and Consolidate Media Presence - Continue and Evolve Digital Storytelling - Co-produce environmental debate panels in partnership with local media. - Leverage Evergreen Content | Reach 25% increase over 2026 baseline in all tracked visibility indicators. Produce a digital and media engagement toolkit for sustained post-2030 outreach. | - Conduct a National Review of WWF-DRC’s Digital and Media Practices - Co-Design the Toolkit with Internal and External Communication Experts -
|  | By 2030, awareness of key nature conservation issues and challenges and WWF-DRC's contribution to resolving them has increased by at least 25% compared to 2026 baseline. |  |  | Conduct public awareness baseline survey (knowledge of conservation issues, threats, and WWF DRC’s role). Design awareness campaign plan. | - Develop and Deploy a National Awareness Baseline Survey - Conduct Focus Groups and Key Informant Interviews - Analyze Data and Produce a Public Awareness Diagnostic Report - Design a National Awareness Campaign Plan | Strengthened national visibility and public awareness of WWF’s conservation work, with consistent messaging across media platforms and priority landscapes | - Launch a National Conservation Awareness Campaign -Negotiate Visibility Agreements with 2–3 National Media Outlets - Broadcast Field-Based Success Stories - Create a plan for regular creation of video/photo series | Conduct mid-term awareness survey. Achieve minimum 20% increase over baseline. Expand campaign content to schools and community groups. | - Design and Administer a Mid-Term Awareness Survey - Launch a Education Initiative with schools - Roll Out Community-Based Awareness Campaigns - Produce and Disseminate a Mid-Term Results Brief | Maintain awareness campaign activities. Produce annual conservation awareness bulletins and digital campaigns on endangered species and climate issues. | - Collect stories, data, and expert insights from WWF landscapes and partners. - Launch Digital Awareness Campaigns - Create framework for collaborative authentic content creation - Create media kits for Journalists on issues related to species and climate change | Conduct final awareness survey. Achieve 40% increase over 2025 baseline. Document impact stories and community awareness case studies for publication. | - Launch a “Legacy for Nature” National Visibility Campaign - Conduct a Visibility Capacity Review - Host a Final-Year Learning & Sharing Forum - Conduct a Final Visibility Impact Assessment - Publish a “5 Years of Visibility” Legacy Report
5. Financial Management | By 2030, WWF DRC is financially sustainable through transparent management, strong cost recovery, diversified income, and effective financial oversight. | By 2030, WWF DRC has implemented a fully operational, transparent financial management and develop a cost recovery policy aligned with WWF Network standards and local regulatory requirements. |  |  | At least 85% of active projects implement the standardized cost recovery rates and financial reporting templates in line with the new policy by December 2026. | -develop and approve a standardized, documented cost recovery policy and financial management manual aligned with WWF Network standards and DRC regulations | Systematic update of financial management dashboard, reporting on burn rates, cost recovery performance, and compliance indicators, is operational and generating quarterly reports for SMT and NOs. An external financial management and cost recovery audit confirms at least 90% compliance with WWF Network standards and local regulatory requirements . | - Intergrate the NEW GMS system in the management of burn rates in the country office
|  | By 2030, WWF-DRC has eliminated its core deficit and achieved a balanced or positive unrestricted reserve position, as verified by audited financial statements. |  |  | Rigorously Monitor the implemntation of the turnaround strategy action plan with quarterly financial performance reviews. Achieve a minimum 30% reduction in deficit compared to FY25 closing figures. | -Accurate and Updated financial information on a monthly basis - Monitor Project burn rates to ensure maximum management fees collection - Cost control of Core costs | Reach a 60% reduction in the accumulated deficit. Implement full cost recovery enforcement for all new projects. Secure increased core allocations from NOs or unrestricted funding sources. | Continue avec year 1 activities | Achieve an 80% reduction in the deficit. Conduct mid-term financial sustainability review and adjust strategies based on income and cost trends. |  | Reduce remaining deficit to no more than 10% of FY25 baseline value. Secure multi-year core funding agreements where possible. |  | Fully clear the deficit and close the financial year with a positive unrestricted reserve balance, as validated by the annual audit. Publish a financial turnaround achievement report.
6. Procurement & Logistics | By 2030, WWF DRC provides high-quality, timely, and transparent procurement and logistics services that fully support the smooth and efficient implementation of its strategic and operational priorities. | By 2030, at least 90% of procurement and logistics service requests and transactions meet standards for timeliness, cost-efficiency, quality, transparency, and supply chain responsiveness, compared to 2025 baseline performance levels. |  |  | Standardized procurement and logistics service level benchmarks and KPIs for timeliness, cost-efficiency, quality, transparency, and responsiveness are defined, approved, and operationalized across all DRC offices. | - Define Logistics timelines and KPIs. -Conduct a baseline assessment of procurement and logistics service quality and timeliness. - Establish procurement transaction performance tracking system. - systematic update of procurement plans for each landscape each quarter - program leads to consult and follow procument plans for 80 % of procurements | Implement priority improvements based on baseline findings. Achieve at least 50% improvement in key services compared to 2025. Reach 70% compliance with transaction standards. Review and adjust procurement workflows for efficiency. | conduct an internal compliance review confirming reduction and closure of at least 90% of previous audit issues. Integrate procurement risk controls into operational procedures. | Internal compliance reviews confirm that at least 75% of procurement and logistics transactions meet the established benchmarks for quality, transparency, and responsiveness | Conduct mid-term procurement transaction performance review. | Corrective action plans from FY28 compliance reviews are fully implemented, resulting in at least 85% of procurement and logistics transactions meeting performance standards. |  | An external operational audit verifies that at least 90% of procurement and logistics service requests and transactions comply with standards for timeliness, cost-efficiency, quality, transparency, and responsiveness. | Publish annual procurement performance and value-for-money report. | Will be able to increase Logistics personnel to be able to develop some of the reports The risk and compliance manager will include part of the compliance issues here in his TOR
|  | By 2026, procurement audit recommendations will be reduced by at least 90% compared to 2025. |  |  | Implement corrective actions for at least 90% of procurement audit recommendations from 2025. | conduct a comprehensive procurement compliance review action plan addressing 90% of 2025 audit recommendations is finalized and approved by SMT. Track monthly progress through management action plans. | [8 empty] | There are no new audit findings in the subsequant years
|  | By 2026, WWF DRC has established a transparent, compliant, and efficient logistics management system that effectively mitigates the risk of fraud, ensures full adherence to procurement and asset management policies, and fosters a culture of accountability and integrity across all operational levels- DEPENDING ON THE AVAILABILTY OF FUNDS |  |  | At least 85% of logistics transactions and asset management processes comply with the new framework, verified through quarterly compliance reports and an internal mid-year logistics compliance review. | complete baseline asset inventory , with findings documented and action plan developed for system improvements. - Conduct survey across landscaped to gauge the understanding of procurement policy develop. Refresher training of the WWF International Procureement Manual which is in use in the country office. | [8 empty] | Funds will be available to carry out these activities
7. Programme Quality, Risk and Compliance | By 2030, WWF DRC ensures institutional reliability through an effective quality, risk, and compliance management system, aligned with WWF Network standards and good practice. | By 2030, 100% of project proposals are processed with quality and sent on time to QAC by WWF-RDC. |  |  | A standardized project proposal development and internal quality assurance framework, including timelines, review steps, and submission protocols to QAC, is finalized and operational across WWF DRC. |  | At least 80% of project proposals submitted in FY27 comply with the new quality assurance framework and are delivered to QAC within agreed timelines, as confirmed by internal tracking reports. |  | A quarterly internal proposal review committee is operational and reviews 100% of draft proposals prior to QAC submission, ensuring adherence to quality and timeline standards. |  | At least 90% of project proposals submitted in FY29 meet QAC quality requirements on first submission and are processed within the defined deadlines. |  | 100% of all project proposals submitted in FY30 meet QAC quality standards and submission deadlines, as verified by internal proposal management records and QAC feedback.
By 2030, the annual rate of solved complaints related to WWF’s conservation activities is reduced by at least 90% compared to the 2024 baseline, and 100% of registered complaints are addressed within agreed timelines.
|  | By 2030, at least 80% of priority risks identified in the landscapes are mitigated, and operational risk registers are actively maintained and reviewed quarterly. |  |  | Implement a proactive risk management system, Update landscape risk registers. Prioritize top 10 risks per landscape. Conduct quarterly reviews with CLT and landscape managers. | Activity 1 : Update risk registers for each landscape by 30 June 2026, in collaboration with Landscape Managers, identifying and ranking the top 10 risks based on a standardized risk scoring grid. Activity 2 : Conduct quarterly risk review sessions with the CLT and Landscape Managers, starting July 2025, using a consolidated reporting format and a risk tracking matrix. | Mitigate at least 80% of identified priority risks. Integrate risk reporting into project review meetings. | Activity 1 : Implement mitigation plans of identified priority risks at the beginning of year, and document actions in a risk tracking table per landscape. Activity 2 : Ensure that mitigation actions are integrated into the project workplans and that a “risk monitoring” item is systematically included in the agenda of monthly or quarterly project review meetings, starting from July 2025. A summary report should be produced to track the evolution of risks and the mitigation measures implemented. | Reach 80% risk mitigation. Organize annual risk management refresher sessions for operational and field teams. | Activity 1 : Organize at least one annual risk management refresher session for all operational and field teams by 30 November 2025, including local case studies and updated procedures. Activity 2 : Implement and close mitigation actions for at least 80% of priority risks by 31 March 2026, with validation by CLT and documentation in the risk register. | Achieve 80% mitigation of priority risks. Update risk management SOPs based on lessons learned. | Activity 1: Revise SOPs based on lessons from mitigation efforts FY24–FY25. Activity 2: Distribute updated SOPs to all relevant staff (operations and field teams). Activity 3: Integrate an annual training module on SOPs into the HR development plan. | Reach 80% risk mitigation. Publish an operational risk management performance report and updated landscape risk profiles. | Activity 1: Organize annual training and reflection sessions on risk management. Activity 2: Establish a network of “risk focal points” in each landscape by 2026.
|  | By 2027, 90% of internal and external audit recommendations are implemented within agreed deadlines. |  |  | A centralized audit recommendation tracking and accountability system is established and operational, covering 100% of internal and external audit recommendations with assigned deadlines and responsible officers. | Activity 1: Design, validate, and deploy a centralized tracking system for internal and external audit recommendations by 30 September 2025, including a shared database or dashboard with: recommendation description, status, responsible officer, deadline, and audit source. Activity 2: Register 100% of audit recommendations from 2022–2025 reports in the system by 31 October 2025, with assigned responsible officers and deadlines approved by SLT. | 100% of internal and external audit recommendations due in FY27 are implemented within the agreed deadlines, as verified through quarterly progress reports and end-of-year validation by SMT. | Activiy 1: Update the implementation status of all FY27 due audit recommendations quarterly starting January 2026, with a summary report to be presented to the SMT each quarter (Q1 to Q4). Activity 2: Establish an automated alert mechanism for overdue recommendations starting March 2026, with monthly notifications sent to responsible officers and the Risk & Compliance Manager. Activity 3: Hold a validation session with the SlT by December 2027, confirming that 100% of due audit recommendations have been implemented or formally justified as closed or rescheduled.
|  | By 2030, WWF DRC achieves full compliance with WWF Network operational, risk, security, and safeguarding standards, as evidenced by regular internal reviews and no high-risk unresolved cases. |  |  | including regular safety training Conduct a full compliance gap assessment against WWF Network standards. Develop a compliance improvement action plan. | Activity 1: By December 2025, complete a compliance gap assessment against WWF Network standards across all operational units using the latest compliance checklist. Activity 2: By December 2025, develop and validate a compliance improvement action plan with prioritized actions, responsible persons, and deadlines. Activity 3: Conduct one safety training session per quarter for all staff, starting in Q3 2025, with attendance recorded and training materials archived. | At least 70% of compliance gaps identified in 2025 are closed with supporting documentation, and no new high-risk cases remain unresolved without an active mitigation plan. | Activity 1: implement and document closure of at least 70% of compliance gaps identified in the 2025 compliance action plan. Activity 2: ensure all new high-risk compliance issues are addressed within 30 days with a written mitigation plan, tracked in the compliance dashboard. | Quarterly internal compliance reviews are institutionalized and integrated into SMT reporting, with at least 85% compliance achieved across all key standards. | Activity 1: conduct internal compliance reviews each quarter using a standardized tool, covering all operational units. Activity 2: integrate compliance results and trends into SLT quarterly reporting, with corrective actions tracked. Activity 2: achieve at least 85% average compliance across all standards as shown in the quarterly dashboards. | An embedded compliance culture is evidenced by 90% compliance, continuous policy revision, and reduction of high-risk cases to under 2%. | Activity 1: maintain or exceed 90% compliance rate in quarterly internal reviews. Activity 2: Review and update at least three key compliance policies (e.g: Security, procurement etc.). Activity 3: Reduce unresolved high-risk compliance cases to under 2% of total cases, based on audit logs and issue trackers. | An external compliance review is conducted in preparation for 2030, confirming system maturity, alignment with WWF standards, and no critical non-compliance. | Activity 1: Engage/work with an external/Regional auditor or compliance consultant to conduct a full compliance maturity assessment. Activity 2: Validate that the organization meets WWF compliance maturity standards with no critical non-conformities, and publish a summary report with recommendations for 2030.
8. PMEL | By 2030, WWF DRC systematically measures, learns, and adapts its work through a strong and coherent Programme Monitoring, Evaluation, and Learning (PMEL) system that enables strategic decision-making and demonstrable conservation impact. | By 2030, WWF DRC has a functional and reliable PMEL system and adaptive management practices in place at national and landscape levels, with at least 90% of programme results systematically tracked, reported, and used to inform decision-making. |  |  | Finalize and validate a national PMEL framework aligned to the OSP. Conduct baseline PMEL capacity and system assessment in all landscapes. Establish data collection protocols and minimum indicators for all programmes. |  | Roll out PMEL tools and digital reporting templates to all landscapes. Train 100% of programme and MEL staff in PMEL standards, data collection, and adaptive management. Pilot annual reflection and learning sessions in at least 3 landscapes. |  | Achieve 70% of programme results tracked through the PMEL system. Institutionalise annual learning and reflection sessions at national and landscape levels, linked to quarterly KPI reviews. Update PMEL framework based on pilot lessons. |  | Reach 80% of programme results systematically tracked and used in decision-making. Document 3 cases where PMEL evidence directly informed strategic or operational adjustments. Strengthen programme data quality control mechanisms. |  | Achieve 90% programme result tracking and reporting coverage. Conduct an external PMEL system performance review. Publish a PMEL and adaptive management lessons learned report for the strategy cycle.
Note on F9: ====== ID#AAABkN0D6V0 tc={8FF172B7-98CA-47C2-B5F3-398000ADAC62} (2025-05-26 11:56:29) [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: who would be the custodian of this especially for program docs
Note on C10: ====== ID#AAABlVsQ1-U Maren Helmbold (2025-06-06 13:40:06) See infrastructure investment proposal
Note on F10: ====== ID#AAABm5WGOeE Bruno Xavier Ilunga (2025-07-02 13:42:59) i suggest to delete these row @rboundja@wwfdrc.org
Note on C11: ====== ID#AAABlVsQ1-M Maren Helmbold (2025-06-06 13:39:55) See infrastructure investment proposal ------ ID#AAABlVsQ1-s Margaret Madira (2025-06-06 14:02:18) @Maren.Helmbold@wwf.de is there a WWF standard on equipment? ------ ID#AAABlVsQ1-8 Maren Helmbold (2025-06-06 14:23:48) I haven't actually found any such standard / guidelines, but we can ask Viviane about this in our meeting on Wednesday. From my point of view, the Digital Infrastructure Investment Proposal is a good reference point, because I think it defines what should be available as standard equipment and infrastructure.
Note on A17: ====== ID#AAABm5WGOeA Margaret Madira (2025-07-02 13:31:14) @zrakotonomenjanahary@wwfdrc.org may you check the outcomes. outputs and activities. make any edits as you see fit _Assigned to zrakotonomenjanahary@wwfdrc.org_
Note on C19: ====== ID#AAABlVsQ198 Maren Helmbold (2025-06-06 13:39:11) Confort
Note on C22: ====== ID#AAABlVsQ19s Maren Helmbold (2025-06-06 13:37:05) @jlisandela@wwfdrc.org : Merci de ne pas oublier de créer la chaîne de résultats pour cet outcome. _Assigned to jlisandela@wwfdrc.org_ ------ ID#AAABjfALxtA Julva Lisandela Ngongo (2025-06-25 08:55:42) bien noté
Note on G22: ====== ID#AAABm5Auyec Bruno Xavier Ilunga (2025-07-02 16:27:21) A completer par Julva selon le commentaire de Maren dans l'onglet C22 @jlisandela@wwfdrc.org _Assigned to jlisandela@wwfdrc.org_
Note on C23: ====== ID#AAABkN0D6V4 tc={50F7E9CA-42A7-4AD2-BA78-28F6DFBFCBA5} (2025-05-26 11:56:29) [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Déjá couvert / intégré dans la stratégie de conservation
Note on C27: ====== ID#AAABlVsQ190 Maren Helmbold (2025-06-06 13:37:52) Patrick

## OSP M&E Plan
OM M&E plan | # | Description | Indicator | Baseline | Year 1 Target | Year 2 Target | Year 3 Target | Year 4 Target | End-line Target | Assumptions | Means of Verification | Data Collection Tool | Frequency of Measurement | Risks | Location | Responsible
OM Priorities Theory of Change
OM Goals | 1 | By 2030, WWF DRC has committed, satisfied and good-performing staff, working within a strong, inclusive organizational culture that lives WWF’s values. | Staff Engagement Index | 3,71/5 (SES - Sep24) | 3,8 | 3,9 | 4,1 | 4,17 | 4,25/5 |  |  |  |  | ------------------------- | ------------------------- | -------------------------
| 2 | By 2030, WWF DRC demonstrates operational excellence, through full compliance, modern infrastructure, and digital systems. | Audit & Risk Mitigation Rate | 70% | 70% of operational activities are completed on time | 75% of operational activities are completed on time | 85% of operational activities are completed on time | 80% of operational activities are completed on time | 90% of operational activities are completed on time | There is funding to support the digital infrasture upgrade | - spot Checks results - audit reports - Burn rate reports - Inventory reports - Satisfaction surveys |  |  | ------------------------- | ------------------------- | -------------------------
|  |  | Digital Workflow Adoption Rate | 40% | 40% of activities are digitalized | 45% of activities are digitalized | 55% of activities are digitalized | 70% of activities are digitalized | 90% of activities are digitalized
| 3 | By 2030, WWF DRC is led by an effective, stable, and high-performing Country Leadership Team (CLT) and Country Management Team (CMT) that ensure strategic clarity, operational oversight, and smooth implementation of the OSP. | Leadership Effectiveness Index | behaviors: decision making process : 3,11/5 - (SES - Sep 24) impact on the team: trust in leadership: 4,14/5 (SES - Sep 24); |  |  |  |  | behaviors: decision making process : 3,5/5 - (SES - Sep 24) impact on the team: trust in leadership: 4,14/5 (SES - Sep 24); | There is funding to maintain the positions
| 4 | By 2030, WWF DRC has significantly enhanced its public profile and visibility, leading to greater impact of its programmes, strengthened partnerships, and increased public awareness for nature conservation. | Brand Recognition and Impact Index (BRII) | TBD
| 5 | By 2030, WWF DRC achieves financial sustainability through efficient, transparent, and effective financial management, improved cost recovery, diversified income streams, and strengthened financial planning and oversight. | Unrestricted Funding reserve (UNR) |  | - Annual +ve result of more than 500K - 70 % cost recovery of Core costs | - Annual +ve result of more than 500K - 80 % cost recovery of Core costs | - Annual +ve result of more than 500K - 85 % cost recovery of Core costs | - Annual +ve result of more than 500K - 90 % cost recovery of Core costs | - Breakeven from the deficit -95% cost recovery | the current Core structure is maintained so as not to increwase CORE costs | - Level of cost recovery from Projects - Annual Managemnt reports
| 6 | By 2030, WWF DRC provides high-quality, timely, and transparent procurement and logistics services that fully support the smooth and efficient implementation of its strategic and operational priorities. | % of Procurement requests done on time | 70% | 75% | 75% | 80% | 85% | 90%
| 7 | By 2030, WWF DRC ensures institutional reliability through an effective quality, risk, and compliance management system, aligned with WWF Network standards and good practice. | % of audit recommendation have been implement | 93% | 93% | 95% | 97% | 98% | 100%
|  |  | High-Risk Mitigation Rate | 70% | 70% | 80 % | 80 % | 90 % | 90 %
| 8 | By 2030, A new PMEL system at WWF-RDC is implemented and used to improve operation and make strategic decision. | % of active projects are tracked via Panda Impact-PMEL for ongoing monitoring and reporting as a whole | 10% | 70% | 100% | 100% | 100% | 100%
OM Priorities Outcomes | 1.1 | By 2030, WWF DRC structure is aligned with its conservation plan and its financial possibilities and key roles are filled | Critical Position Occupancy Rate | 80% (vacant positions: PMEL, Fundrasing & Grant, P&Cmanager (50%), Proc officer | 85% | 90% | 92% | 97% | 100% | [5 empty] | ------------------------- | -------------------------
| 1.2 | By 2030, WWF DRC P&C policies systems, tools are up to date with internal & external context and are relevant to its challenges | HR Process Digitalization Rate | 57% (not yet: recruitment & onboarding (starting April), performance & learning) | 60% | 70% | 80% | 90% | 100% | [5 empty] | ------------------------- | -------------------------
| 1.3 | By 2030, WWF DRC staff performance and development opportunities have improved by 50% in reference to the baseline FY25. | PDR & Development Plan Completion Rate | 70% of staff are solid performers in FY25; 12% of staff completed their development plans | 75% of staff are solid performers ; | 80% of staff are solid performers | 80% of staff are solid performers | 85% of staff are good performers | 90% of staff are solid performers in FY25; 20% of staff completed their development plans
| 2.1 | By 2030, WWF DRC has achieved 90% compliance with required policies and procedures for quality delivery in the implementation of its 2026-2030 OSP. | % of compliance with procedures and policies | [11 empty] | ------------------------- | -------------------------
| 2.2 | By 2027, Staff are at least 90% satisfied annually with information services, and logistics support based on survey report | Score of staff satisfaction survey | TBD
| 2.3 | By 2030, a green energy system is installed in 100% of field offices to solve electricity problems and to ensure optimal operations in reference to 2025 baseline | Green Energy Utilization Rate | 50% | 60% | 80% | 90% | 100% | 100%
| 2.4 | By 2030, infrastructure and equipment in the national office and in the field responds at least 70% to organizational standards. | Infrastructure & Equipment Standards (MOS) Index | 75% | 80% | 85% | 90% | 95% | 100%
| 2.5 | By 2030, WWF DRC has at least 70% of right capacity in place to implement efficiently processes and procedures in reference to 2025 baseline | Number of staff trained on internal process (Operational Competency Coverage Rate) | 62% of staff attended refresher training on Fraud & corruption in Jan 2025 | 85% | 90% | 95% | 100% | 100%
| 3.1 | By 2030, at least 90% of staff is satisfied with the governance and leadership system as compared to 2026 baseline. | Leadership & Governance Effectiveness Index | 3,71/5 (SES - Sep24) | 3,8 | 3,9 | 4,1 | 4,17 | 4,25/5
| 3.2 | By 2030, the Score on staff satisfaction is increased to at least 4,5 (baseline of 2024: 3,81). | Overall Staff Satisfaction Mean Score | 3,81 (SES 2024) | 3,85 (SES 2024) | 3,89 (SES 2024) | 3,90 (SES 2024 | 3,95 (SES 2024) | 3,95
| 3.3 | By 2030,100% of decisions taken by leadership are shared on time, explained, applied and followed 100% by staff and management. | # of management decisions informed by programs & project assessments | 90% | 100% | 100% | 100% | 100% | 100%
| 4.1 | By 2030, the perception of WWF DRC has improved by at least 10% relative to 2026 baseline | Stakeholder Perception & Trust Index | TBD
| 4.2 | By 2030, WWF DRC has improved its visibility by at least 25% relative to 2026 baseline | Digital Engagement & Reach Growth Rate | TBD
| 4.3 | By 2030, WWF-DRC improved awareness of nature conservation challenges outside core thematic areas | Conservation Awareness Index (KAP Score) | TBD
| 5.1 | By 2030, WWF-DRC has cleared its deficit | Total Value of Accumulated Operational Deficit | -1194000000 | -894000 | -594000 | -294000 | 0 | 20000 | the current structure will be maintained so as not to increase core costs
| 5.2 | By 2035, WWF DRC core funding is sustainable and can cover at least 6 months of gross core expenditure | Months of Core Operations Covered by Unrestricted Reserves | -0.8 | -0.447 | -0.297 | -0.147 | 0 | 0.01
| 6.1 | By 2028, WWF DRC has improved at least 90% of quality and timely logistics and procurement services in reference to 2025 base line. | Percentage of Procurement Requisitions Completed within SLA Standards | 70% | 70% | 80% | 90% | 95% | 100%
| 6.2 | By 2026, procurement audit recommendations will be reduced by at least 90% compared with 2025. | Percentage of Audited Procurement Transactions Meeting Full Compliance Standards | TBD
| 6.3 | By 2030,cost-effective and transparent purchasing processes, with an efficient and responsive supply chain in place | Average Procurement Cycle Time (Lead Time) | 21 | 30 | 30 | 30 | 30 | 30
| 7.1 | By 2030, the annual rate of complaints related to WWF's conservation activities is reduced by at least 90% compared to the 2024 baseline. | Volume of Substantiated Environmental & Social Grievances | 0
| 7.2 | By 2030, the risks identified in the priority landscapes have been mitigated by at least 90% compared with the 2024 baseline. | Percentage of Critical/High Risks with Residual Risk Reduced to Acceptable Levels | TBD
| 7.3 | By 2030, 100% of project proposals are processed with quality and sent on time to QAC by WWF-RDC. | Percentage of Proposals Submitted to QAC Meeting Full Quality and SLA Timelines | 80% | 80% | 85% | 90% | 95% | 100%
| 7.4 | By 2030, no case of noncompliance acts is detected. | Number of Substantiated Material Non-Compliance Incidents | 24 | 20 | 18 | 16 | 14 | 12
| 7.5 | By 2027, 100% of audit recommendations are implemented | Percentage of Audit Recommendations Fully Implemented by Due Date | 93% | 95% | 97% | 99% | 100% | 100%
| 7.6 | By 2030, 100% of security incidents affecting WWF DRC are treated according to WWF International standards | Percentage of Reported Security Incidents Managed in Full Compliance with Network Standards | 100% | 100% | 100% | 100% | 100% | 100%
| 8.1 | By 2030, a reliable PMEL system and adaptive managment practices are implemented l in WWF DRC both at national and landscape levels demonstrating at least 90% of tracked results. | Percentage of Strategic Indicators with Complete and Valid Data Reported on Schedule | 40% | 50% | 60% | 70% | 76% | 76% | [5 empty] | ------------------------- | -------------------------
| 1.1.1 | Updated P&C policies and automated HRIS systems are fully operational and aligned with WWF Network standards | % of core P&C processes fully digitized and compliant with Network Standards | 57% (core hr, absence, timesheet, payroll) | 57% | 60% | 70% | 80% | 90% |  |  | Report from canopy | annually |  |  | P&C
| 1.1.2 | The Performance Management and Staff Development framework is operational and actively utilized by staff. | % of eligible staff with completed individual performance objectives and reviews (PDR) | 98% | 100% | 100% | 100% | 100% | 100% | funding available to cover the increase |  |  | annually |  |  | P&C
| 1.1.3 | Recruitment Framework and Job Descriptions (JDs) updated, compliant with Network Standards, and approved. | Percentage of Compensation & Benefits (C&B) framework documents revised and formally approved. | 90% (approximately: a few requests on JD to be reviewed) | 90% | 95% | 100% | 100% | 100% |  |  | report from Canopy | annually |  |  | P&C
| 1.1.4 | Compensation & Benefits (C&B) benchmarking report completed and new salary scale approved. | Status of Salary Scale & Benefits review and approval | review of salary scale suspended in FY25 due to financial constraints |  |  |  |  | Salary scale improved and implemented
| 2.1.1 | A comprehensive compliance framework, including a policy register and compliance monitoring plan aligned with WWF Network and local regulatory requirements for OSP delivery, is finalized and endorsed by SMT | Percentage of mandatory compliance policy documents updated and endorsed by SMT | TBD
| 2.1.2 | Knowledge Management (KM) System operational and populated with legacy data. | Percentage of identified key operational documents successfully migrated to the KM System
| 2.1.3 | Procure and install equipment upgrades in 3 offices. Reach 50% alignment with WWF standards. | % of target offices with standardized equipment upgrades | 75% | 78% | 83% | 85% | 90% | 90%
| 2.1.4 | Maintain 70% compliance or higher through routine maintenance, asset management, and annual office audits. | Proportion of assets and facilities that remain at or above the 70% quality threshold | 70% | 75% | 80% | 85% | 95% | 100%
| 2.1.5 | Institutionalize quarterly governance check-ins (minimum 4 per year) with anonymous feedback loops. Reach 85% satisfaction rate. | Average staff satisfaction score | 75%
| 2.1.6 | Green energy systems installed and operational in priority field offices. | Number of field offices with fully operational solar energy systems | 70% ( 7 offices) | 70% ( 7 offices) | 8 | 9 | 10 | 11
| 2.1.7 | Install systems in remaining 2 field offices. Achieve 60% reduction in diesel generator reliance compared to 2025. | Litres of diesel fuel consumed for office operations | TBD
| 2.1.8 | Staff capacity building program on updated policies delivered. | Percentage of eligible staff certified in updated operational policies
| 2.1.9 | At least 90% of WWF DRC staff and project managers are trained and certified on the updated policies and procedures | % of staff and project managers certified on updated policies | 80% | 90% | 90% | 100% | 100% | 100%
| 2.1.10 | Systematic update of financial management dashboard, reporting on burn rates, cost recovery performance, and compliance indicators, is operational and generating quarterly reports for SMT and NOs. | % of Financial Dashboards updated and reported on schedule | 80% | 80% | 90% | 90% | 90% | 100%
| 2.1.11 | Implement at least 80% of actions from 2026 plan. Establish communication and feedback mechanisms for CLT/CMT decisions. | Implementation rate of 2026 Governance Action Plan | 90% | 100% | 100% | 100% | 100% | 100%
| 3.1.1 | Ensure 80% of key decisions are communicated within agreed timelines. Introduce decision feedback mechanisms. | % of leadership decisions communicated within SLA timelines | 90% | 100% | 100% | 100% | 100% | 100%
| 3.1.2 | Annual Governance Improvement Action Plan implemented | Percentage of planned governance improvement actions completed on schedule | 90% | 100% | 100% | 100% | 100% | 100%
| 3.1.3 | Annual Governance Review and Lessons Learned Report produced | Status of the Annual Governance Review & Lessons Learned Report | 90% | 100% | 100% | 100% | 100% | 100%
| 3.1.4 | Annual Staff Perception Survey on Leadership & Governance completed and validated. | Completion status of the Annual Leadership Perception Survey | TBD
| 3.1.5 | Establish a visibility baseline (media mentions, digital impressions, social media followers, partnership events). Define annual growth targets. | Visibility Baseline Completion Status | TBD
| 3.1.7 | Annual Environmental Footprint & Operational Savings Report published. | Status of the Annual CO2 & Operational Savings Report | TBD
| 3.1.8 | Integrated Communications & Brand Strategy (informed by baselines) finalized | Status of the Integrated Communications & Brand Strategy | TBD
| 4.1.1 | High-level stakeholder engagement events delivered. | Number of strategic stakeholder engagement events organized | 0 | 1 | 1 | 1 | 1 | 1
| 4.1.4 | Strategic communication partnerships established and joint visibility campaigns executed to amplify WWF-DRC's conservation voice. | Number of active high-profile media partnerships | 2 | 1 |  | 1 |  | 4
| 4.1.5 | Conduct public awareness baseline survey (knowledge of conservation issues, threats, and WWF DRC’s role). Design awareness campaign plan. | Awareness Baseline & Campaign Design Status | TBD
| 4.1.6 | High-quality conservation awareness materials produced and disseminated to priority audiences. | Number of strategic communication products disseminated | 0 | 2 | 2 | 2 | 2 | 2
| 4.1.7 | Organizational financial health restored through deficit elimination and reserve accumulation. | Amount of unrestricted Funds Deficit | -1194 k USD
| 4.1.8 | Reach a 60% reduction in the accumulated deficit. Implement full cost recovery enforcement for all new projects. Secure increased core allocations from NOs or unrestricted funding sources. | Audit Compliance Rate (Financial & Cost Recovery) | TBD
| 4.1.12 | Full Cost Recovery (FCR) policy operationalized across all active grants to ensure financial sustainability. | Proportion of active grants that are billing the maximum allowable Indirect Cost Recovery | 50% | 50% | 60% | 60% | 70% | 80%
| 5.1.1 | Comprehensive Energy & Infrastructure Audit Reports finalized for all field offices | Percentage of field offices with finalized Energy & Infrastructure Audit Reports | TBD |  |  |  |  | 80%
| 5.1.2 | Conduct comprehensive infrastructure quality audit. Address gaps to reach 70% compliance | Infrastructure Quality Compliance Score | 20% | 60% | 70% | 80% | 90% | 100%
| 5.1.3 | Procurement processes optimized to deliver goods and services within agreed Service Level Agreement (SLA) timeframes. | Average Procurement Cycle Time (Lead Time) | 21 | 30 | 30 | 30 | 30 | 30
| 6.1.2 | Operational risks mitigated through timely implementation of audit recommendations (Procurement & Logistics). | Audit Recommendation Closure Rate | 80% | 90% | 90% | 95% | 95% | 100%
| 7.1.2 | Implement a proactive risk management system, Update landscape risk registers. Prioritize top 10 risks per landscape. Conduct quarterly reviews with CLT and landscape managers. | % of Landscapes with updated and reviewed Risk Registers | 80% | 90% | 90% | 95% | 95% | 100%
| 7.1.3 | Priority risks identified in landscape risk registers are effectively mitigated to within the organization's risk appetite. | Critical Risk Mitigation Rate | 50% | 60% | 70% | 80% | 90% | 100%
| 7.1.4 | A standardized project proposal development and internal quality assurance framework, including timelines, review steps, and submission protocols to QAC, is finalized and operational across WWF DRC. | Operational Status of QA Framework | TBD
| 7.1.5 | Quality Assurance (QA) protocols enforced for all funding proposals to maximize win-rates and minimize contractual risk. | Proposal Quality & Timeliness Compliance Rate | 90% | 100% | 100% | 100% | 100% | 100%
| 7.1.6 | A quarterly internal proposal review committee is operational and reviews 100% of draft proposals prior to QAC submission, ensuring adherence to quality and timeline standards. | Proposal Quality & Timeliness Compliance Rate | 80% | 80% | 85% | 90% | 95% | 100%
| 7.1.7 | IT & Equipment Upgrade Plan implemented in priority offices. | Percentage of staff workstations meeting the defined "WWF DRC IT Standard" | 50% | 60% | 65% | 70% | 80% | 90%
| 7.1.8 | Upgrade infrastructure in 2 remaining offices. Achieve 60% compliance. | % of remaining offices reaching 60% infrastructure compliance | 50% | 50% | 55% | 60% | 70% | 80%
| 7.1.9 | At least 70% of compliance gaps identified in 2025 are closed with supporting documentation, and no new high-risk cases remain unresolved without an active mitigation plan. | Compliance Gap Closure Rate | 93% | 93% | 93% | 97% | 98% | 98%
| 7.1.10 | A quarterly internal proposal review committee is operational and reviews 100% of draft proposals prior to QAC submission, ensuring adherence to quality and timeline standards. | Proposal Quality Review Rate | 93% | 93% | 93% | 97% | 98% | 98%
| 7.1.11 | 100% of internal and external audit recommendations due in FY27 are implemented within the agreed deadlines, as verified through quarterly progress reports and end-of-year validation by SMT. | % Audit Implementation Timeliness Rate | 40% | 80% | 80% | 85% | 90% | 100%
| 7.1.12 | Staff and partners fully trained and compliant with WWF’s Environmental & Social Safeguards (ESSF) and Security protocols. | Staff Safety & Safeguards Training Compliance Rate | 93% | 93% | 95% | 97% | 98% | 100%
| 8.1.1 | A centralized, digital PMEL system covers the entire conservation portfolio, ensuring data availability for real-time reporting. | PMEL System Operational Effectiveness Index | 20% |  |  |  |  | 100%
| 8.1.2 | Adaptive management institutionalized through regular, evidence-based reflection sessions that drive strategic adjustments. | Adaptive Management Action Implementation Rate | 50% |  |  |  |  | 100%
Note on D3: ====== ID#AAABloVC-zs Maren Helmbold (2025-06-12 15:03:23) further suggestions: Annual staff retention rate (%) % of staff participating in professional development opportunities per year Number of staff well-being initiatives implemented per year % of leadership and staff demonstrating alignment with WWF values (via culture survey)
Note on D4: ====== ID#AAABloVC-zw Maren Helmbold (2025-06-12 15:04:07) further suggestions: % of procurement and logistics requests fulfilled on time and within cost limits % of operational services (finance, admin, ICT) meeting service standards per quarterly review Number of digital systems fully operational and integrated across offices % infrastructure and equipment meeting WWF operational standards Annual operational services satisfaction score from internal surveys
Note on D6: ====== ID#AAABloVC-z0 Maren Helmbold (2025-06-12 15:04:28) further suggestions: % of strategic decisions communicated within agreed timelines Average tenure of CLT/CMT members (stability indicator) % of annual operational and strategic priorities fully delivered as planned
Note on D7: ====== ID#AAABloVC-z4 Maren Helmbold (2025-06-12 15:04:51) further suggestions: % increase in media mentions and digital engagement compared to 2026 baseline Number of high-profile events or campaigns organized per year Number of formal partnerships with media and public platforms Public awareness score on key conservation issues (biennial survey)
Note on C44: ====== ID#AAABkN0D6V0 tc={8FF172B7-98CA-47C2-B5F3-398000ADAC62} (2025-05-26 11:56:29) [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: who would be the custodian of this especially for program docs
Note on C45: ====== ID#AAABm5WGOeE Bruno Xavier Ilunga (2025-07-02 13:42:59) i suggest to delete these row @rboundja@wwfdrc.org

## Implementation Plan
| Fiscal Year | Output Total | Cost | Total | Current Project (CPM Project #) | Target Funding Source
READ Me First. OD Costs should include: A. Human Resources and Capacity Development B. Organisational Governance and Compliance C. Operational Efficiency and Process Improvement D. Technology and Systems E. Stakeholder Engagement and Communications | Please enter the FY of planned Annual Results. It should capture the full length of the OSP. | Please list all the outputs identified under the Factors & Outcome tab as well as the M&E plan. During the annual planning and budgeting process, the Programme will have opportunities to further refine and detail the activities and costs. The initial costing of the priority outputs can be estimated, which will be used to estimate the cost of total OSP implementation and the development of the financial plan. Please make sure to include outputs related to M&E, ESSF and other risk mitigation, etc. |  | This column will be automatically sum up the total. | If the activity is already funded, please indicate the relevant CPM number(s). | If there is a funding gap and have prospective funding sources, please indicate the source.
Example | 2025 | Capacity Development |  | 0
| 2025 | IT system development |  | 0
| 2025 | Communications |  | 0
A. Human Resources and Capacity Development | 2026 | Structure revised at the HQ/Core and within each landscape; Workforce plan in place and implemented | 75000 | 75000
|  | • Policies & procedures updated toward changes at Network level (Performance, HSS; • Automated HRIS tools in place for HR database, absence & timesheet • P&C Dashboard revised & completed regularly on time | 0 | 0
|  | • At least 80% of eligible staff have individual objectives and performance conversations. • Reward & recognition based on performance implemented; • revised sustainable & equitable development programmes; • staff development implemented at 20% | 0 | 0
| 2027 | Revised Recruitment Plan & JDs | 60000 | 60000
|  | • Policies & procedures updated; • Automated HRIS tools in place for Talent Acquisition, Onboarding • P&C Dashboard revised & completed regularly on time • compensation & benefits survey available | 10000 | 10000 |  |  | K4
|  | Reward & recognition based on performance continuously implemented; • Sustainable & equitable development plan implemented for 25 % of existing staff (through peer coaching, online, formal) | 25000 | 25000
| 2028 | Revised Structure evaluated (Mid-term) for the HQ/Core and within each landscape; Workforce plan evaluated | 20000 | 20000
|  | • compensation & benefit are aligned with the market; | 40000 | 120000 |  |  | K4
|  | Reward & recognition based on performance continuously implemented; • new internal development initiatives (job shadowing, peer-learning, coaching) in place • career progression and succession plan implemented | 15000 | 15000
| 2029 | Revised Recruitment Plan & JDs | 20000 | 0
|  | Reward & recognition based on performance continuously implemented; Ensure at least 70% of staff participate in one professional development activity annually. | 55000 | 55000
| 2030 | Revised Recruitment Plan & JDs | 70000 | 70000
|  | Reward & recognition based on performance continuously implemented; Staff survey results show a minimum 50% improvement over baseline | 25000 | 25000
2. Operational Excellence | 2026 | A comprehensive compliance framework, including a policy register and compliance monitoring plan aligned with WWF Network and local regulatory requirements for OSP delivery, is finalized and endorsed by SMT | 800 | 800
|  | An approved design and implementation plan for a knowledge management system, including document classification standards by theme and landscape, is finalized and endorsed. All landscapes and departments achieve a quarterly document update rate of at least 75% in the knowledge management system, | 0 | 0
|  | Conduct feasibility studies and business cases for solar installations in all field offices. Secure funding for at least 3 installations. | 20000 | 20000 |  |  | J10
|  | Define the Standard for WWF DRC for the equipment required to meet organisational goals. Develop upgrade plan and secure budget for priority areas to improve which do not meet the set standards.G11 | 10000 | 10000 |  |  | J13
| 2027 | At least 80% of WWF DRC staff and project managers are trained and certified on the updated policies and procedures. | 0 | 0
|  | At least 90% of all identified key operational and programmatic documents are uploaded, properly classified, and accessible in the knowledge management system, as verified by a formal year-end internal audit. | 0 | 0
|  | Install green energy systems in 3 out of 5 field offices. Monitor and report on operational uptime improvements. | 150000 | 150000 |  |  | K10
|  | Procure and install equipment upgrades in 3 offices. Reach 50% alignment with WWF standards. | 0 | 0
| 2028 | At least 90% of WWF DRC staff and project managers are trained and certified on the updated policies and procedures | 105600 | 105600
|  | Install systems in remaining 2 field offices. Achieve 60% reduction in diesel generator reliance compared to 2025. | 50000 | 50000 |  |  | L10
|  | Upgrade infrastructure in 2 remaining offices. Achieve 60% compliance. | 0 | 0
| 2029 | Conduct energy efficiency audit for all offices. Implement identified operational optimisations | 10000 | 10000 |  |  | M10
|  | Conduct comprehensive infrastructure quality audit. Address gaps to reach 70% compliance. | 10000 | 10000 |  |  | M18
| 2030 | Achieve 100% operations on green energy systems. Publish operational savings and CO2 emissions reduction report. | 45000 | 45000 |  |  | N15
|  | Maintain 70% compliance or higher through routine maintenance, asset management, and annual office audits. | 15000 | 15000 |  |  | N20
3. Governance and Leadership | 2026 | A baseline staff perception survey on leadership effectiveness, decision-making transparency, and management accountability is conducted and results formally validated by SMT. | 20000 | 20000 |  |  | J21
|  | Define ‘key decisions’ and set standards for communication and implementation timelines. Introduce a decision-tracking tool. | 10000 | 10000 |  |  | J22
| 2027 | Implement at least 80% of actions from 2026 plan. Establish communication and feedback mechanisms for CLT/CMT decisions. | 60000 | 60000 |  |  | K23
|  | Ensure 80% of key decisions are communicated within agreed timelines. Introduce decision feedback mechanisms. | 15000 | 15000 |  |  | K24
| 2028 | At least 70% of planned leadership and management accountability improvement measures are implemented, with quarterly progress updates shared with all staff. | 0 | 0
|  | Increase on-time communication and documentation to 85%. Launch a CLT/CMT decision dashboard for tracking. | 50000 | 50000 |  |  | L23
| 2029 | Institutionalize quarterly governance check-ins (minimum 4 per year) with anonymous feedback loops. Reach 85% satisfaction rate. | 25000 | 25000 |  |  | M24
|  | Achieve a 90% performance rate on decision communication, implementation, and follow-up. Conduct at least two decision review and lessons learned workshops. | 50000 | 50000 |  |  | x
| 2030 | Conduct final survey with a target of 90% satisfaction. Produce a lessons learned report and governance improvement plan for the next strategic cycle. | 50000 | 50000 |  |  | N25
|  | Reach 95% rate of implementation, communication, and tracking for key decisions. Produce an end-of-cycle governance and decision-making review report. | 25000 | 25000 |  |  | X
Communication | 2026 | Conduct a stakeholder and public perception baseline survey (including trust, leadership, professionalism, partnership effectiveness). Develop and communicate a perception improvement action plan. | 60000 | 60000 |  |  | X
|  | Establish a visibility baseline (media mentions, digital impressions, social media followers, partnership events). Define annual growth targets. | 20000 | 20000 |  |  | J30 and L30
|  | Conduct public awareness baseline survey (knowledge of conservation issues, threats, and WWF DRC’s role). Design awareness campaign plan. | 0 | 0
| 2027 | Implement at least 70% of planned actions. Launch by-yearly stakeholder engagement meetings and digital perception campaigns. | 10000 | 10000 |  |  | J29
|  | Increase visibility by 10% through expanded media campaigns, digital content series, and conservation events. Secure at least 3 high-profile partnerships for joint visibility actions. | 30000 | 30000 |  |  | K34
|  | Strengthened national visibility and public awareness of WWF’s conservation work, with consistent messaging across media platforms and priority landscapes | 20000 | 20000 |  |  | K31
| 2028 | Conduct mid-term perception survey. Achieve minimum 5% improvement over 2026 baseline. Adjust action plan based on findings. | 10000 | 10000 |  |  | K30
|  | Enhanced multimedia presence and strategic communications partnerships to increase WWF-DRC's visibility. Reach cumulative 18% increase in visibility metrics. . | 30000 | 30000 |  |  | L33
|  | Conduct mid-term awareness survey. Achieve minimum 20% increase over baseline. Expand campaign content to schools and community groups. | 20000 | 20000 |  |  | M30
| 2029 | Maintain perception campaigns and engagement efforts. Conduct partner-specific perception interviews. | 20000 | 20000 |  |  | L32
|  | Maintain and consolidate media presence. Publish an annual visibility performance report. Achieve 22% increase over baseline. | 20000 | 20000 |  |  | M31
|  | Maintain awareness campaign activities. Produce annual conservation awareness bulletins and digital campaigns on endangered species and climate issues. | 20000 | 20000 |  |  | M32
| 2030 | Maintain perception campaigns and engagement efforts. Conduct partner-specific perception interviews. |  | 0
|  | Maintain and consolidate media presence. Publish an annual visibility performance report. Achieve 22% increase over baseline. | 20000 | 20000 |  |  | N31
|  | Maintain awareness campaign activities. Produce annual conservation awareness bulletins and digital campaigns on endangered species and climate issues. |  | 0
5. Financial Management | 2026 | At least 85% of active projects implement the standardized cost recovery rates and financial reporting templates in line with the new policy by December 2026. | 0 | 0
|  | Rigorously Monitor the implemntation of the turnaround strategy action plan with quarterly financial performance reviews. Achieve a minimum 30% reduction in deficit compared to FY25 closing figures. | 0 | 0
| 2027 | Systematic update of financial management dashboard, reporting on burn rates, cost recovery performance, and compliance indicators, is operational and generating quarterly reports for SMT and NOs. An external financial management and cost recovery audit confirms at least 90% compliance with WWF Network standards and local regulatory requirements . | 0 | 0
|  | Reach a 60% reduction in the accumulated deficit. Implement full cost recovery enforcement for all new projects. Secure increased core allocations from NOs or unrestricted funding sources. | 0 | 0
| 2028 | Achieve an 80% reduction in the deficit. Conduct mid-term financial sustainability review and adjust strategies based on income and cost trends. | 0 | 0
0
| 2029 | Reduce remaining deficit to no more than 10% of FY25 baseline value. Secure multi-year core funding agreements where possible. | 0 | 0
0
| 2030 | Fully clear the deficit and close the financial year with a positive unrestricted reserve balance, as validated by the annual audit. Publish a financial turnaround achievement report. | 0 | 0
6. Procurement & Logistics | 2026 | Standardized procurement and logistics service level benchmarks and KPIs for timeliness, cost-efficiency, quality, transparency, and responsiveness are defined, approved, and operationalized across all DRC offices. | 25400 | 25400 |  |  | J39
|  | Implement corrective actions for at least 90% of procurement audit recommendations from 2025. | 0 | 0
|  | At least 85% of logistics transactions and asset management processes comply with the new framework, verified through quarterly compliance reports and an internal mid-year logistics compliance review. | 0 | 0
| 2027 | Implement priority improvements based on baseline findings. Achieve at least 50% improvement in key services compared to 2025. Reach 70% compliance with transaction standards. Review and adjust procurement workflows for efficiency. | 0 | 0
| 2028 | Internal compliance reviews confirm that at least 75% of procurement and logistics transactions meet the established benchmarks for quality, transparency, and responsiveness | 0 | 0
| 2029 | Corrective action plans from FY28 compliance reviews are fully implemented, resulting in at least 85% of procurement and logistics transactions meeting performance standards. | 25000 | 25000 |  |  | M39
| 2030 | An external operational audit verifies that at least 90% of procurement and logistics service requests and transactions comply with standards for timeliness, cost-efficiency, quality, transparency, and responsiveness. | 25000 | 25000 |  |  | N40
7. Programme Quality, Risk and Compliance | 2026 | A standardized project proposal development and internal quality assurance framework, including timelines, review steps, and submission protocols to QAC, is finalized and operational across WWF DRC. | 0 | 0
|  | Implement a proactive risk management system, Update landscape risk registers. Prioritize top 10 risks per landscape. Conduct quarterly reviews with CLT and landscape managers. | 0 | 0
|  | A centralized audit recommendation tracking and accountability system is established and operational, covering 100% of internal and external audit recommendations with assigned deadlines and responsible officers. | 0 | 0
|  | including regular safety training Conduct a full compliance gap assessment against WWF Network standards. Develop a compliance improvement action plan. | 21000 | 21000
| 2027 | At least 80% of project proposals submitted in FY27 comply with the new quality assurance framework and are delivered to QAC within agreed timelines, as confirmed by internal tracking reports. | 42000 | 42000
|  | Mitigate at least 80% of identified priority risks. Integrate risk reporting into project review meetings. |  | 0
|  | 100% of internal and external audit recommendations due in FY27 are implemented within the agreed deadlines, as verified through quarterly progress reports and end-of-year validation by SMT. | 15000 | 15000 |  |  | K47
|  | At least 70% of compliance gaps identified in 2025 are closed with supporting documentation, and no new high-risk cases remain unresolved without an active mitigation plan. | 0 | 0
| 2028 | A quarterly internal proposal review committee is operational and reviews 100% of draft proposals prior to QAC submission, ensuring adherence to quality and timeline standards. | 20000 | 20000
|  | Reach 80% risk mitigation. Organize annual risk management refresher sessions for operational and field teams. | 20000 | 20000
|  | Quarterly internal compliance reviews are institutionalized and integrated into SMT reporting, with at least 85% compliance achieved across all key standards. | 25000 | 25000
| 2029 | At least 90% of project proposals submitted in FY29 meet QAC quality requirements on first submission and are processed within the defined deadlines. | 20000 | 20000
|  | Achieve 80% mitigation of priority risks. Update risk management SOPs based on lessons learned. | 10000 | 10000
|  | An embedded compliance culture is evidenced by 90% compliance, continuous policy revision, and reduction of high-risk cases to under 2%. | 12000 | 12000
| 2030 | 100% of all project proposals submitted in FY30 meet QAC quality standards and submission deadlines, as verified by internal proposal management records and QAC feedback. |  | 0
|  | Reach 80% risk mitigation. Publish an operational risk management performance report and updated landscape risk profiles. | 22000 | 22000
|  | An external compliance review is conducted in preparation for 2030, confirming system maturity, alignment with WWF standards, and no critical non-compliance. | 20000 | 20000
8. PMEL | 2026 | Finalize and validate a national PMEL framework aligned to the OSP. Conduct baseline PMEL capacity and system assessment in all landscapes. Establish data collection protocols and minimum indicators for all programmes. | 15000 | 15000
|  | Recruit PMEL staff | 84000 | 84000
| 2027 | Roll out PMEL tools and digital reporting templates to all landscapes. Train 100% of programme and MEL staff in PMEL standards, data collection, and adaptive management. Pilot annual reflection and learning sessions in at least 3 landscapes. | 84000 | 84000
| 2028 | Achieve 70% of programme results tracked through the PMEL system. Institutionalise annual learning and reflection sessions at national and landscape levels, linked to quarterly KPI reviews. Update PMEL framework based on pilot lessons. | 84000 | 84000
| 2029 | Reach 80% of programme results systematically tracked and used in decision-making. Document 3 cases where PMEL evidence directly informed strategic or operational adjustments. Strengthen programme data quality control mechanisms. | 89000 | 89000
| 2030 | Achieve 100% programme result tracking and reporting coverage. Conduct an external PMEL system performance review. Publish a PMEL and adaptive management lessons learned report for the strategy cycle. | 94000 | 94000
|  |  | 2168800 | 2228800
Note on E1: ====== ID#AAABkN0D6WY (2025-05-26 11:56:29) @hwilliams@wwfint.org , we need to remove this based on the latest discussion as well as in RA. _Assigned to hwilliams@wwfint.org_ -Philip Kahuho
Note on C21: ====== ID#AAABkN0D6V0 tc={8FF172B7-98CA-47C2-B5F3-398000ADAC62} (2025-05-26 11:56:29) [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: who would be the custodian of this especially for program docs
Note on C22: ====== ID#AAABm5WGOeE Bruno Xavier Ilunga (2025-07-02 13:42:59) i suggest to delete these row @rboundja@wwfdrc.org
Note on A60: ====== ID#AAABm5WGOeA Margaret Madira (2025-07-02 13:31:14) @zrakotonomenjanahary@wwfdrc.org may you check the outcomes. outputs and activities. make any edits as you see fit _Assigned to zrakotonomenjanahary@wwfdrc.org_